## Slide 1: Designing a Safeguards Information System
Victor Chiiba
ZAMBIA

## Slide 2: Process: what we did
Zambia undertook the following process :
  Process undertaken: Consultative Process with a consultant who worked with a local Technical Working Group
  Narrative report done at inception and also validation stages of document Preparation
  SIS Definition: Done through Analysis Reporting including mixed approaches
  Sources of Information for the SIS: Existing policies /laws and REDD+ Strategy
  Lead Institution: Zambia Enviromental Management Agency( ZEMA)
  Creation of a dedicated web-based platform t share/disseminate information: YES
  Currently managed by the Forestry Department
  The actual SIS was funded by UNEP . The new activities are been funded by UNREDD and WB while working worth the Zambia Government

## Slide 3: Strengths & Opportunities: what worked
Please provide details of the challenges you encountered:
  Very Few Challenges if any as funds f0r various meetings were mobilised on time that were used for the inception report and the validation process
  We had no challenges in getting the technical input as Technical Advisors from the Africa and Global team were available in most sessions
  Multistakeholders participation is the design

## Slide 4: Weaknesses & Challenges: what didn’t work
  Cooperating partners included the UNEP, UNDP, WB and FAO operating at various levels
  SIS improvements: Currently reviewing the SIS V.1.0 to include other information from the recently drafted National Interpretation of the Cancun Safeguards.
  Further, works shall include a critical look at the WB/GCF safeguards through the use f information from the SESA and ESMF in order to inform THE SIS.

## Slide 5
20
30
ZEMA
Planning & Info. Dept (Host)
- coordination
- information compilation
- analysis and interpretation
- national & international dissemination
Forestry Department
NFMS
(ILUA II + FLES)
national dissemination (web portal)
Ministry of Mines
Ministry of Chiefs and Traditional Affairs
Ministry of Agriculture
Central Statistics Office
- National dissemination
Climate Change Dept.
Analysis/interpretation
Coordinating Body
Energy Department
Water Resources Management Authority
Department of Water Affairs
Department of National Parks and Wildlife
Ministry of Gender
Ministry of Local Government
Research and academic institutions
Private associations
Zambia Farmers’ Union
Chamber of Mines
Ministry of Finance)
Financing operational costs
Notes: Overall proposed (national) institutional arrangements for Zambia’s SIS
Need to stress that this is not SIS v1.0. This is full picture of national institutional arrangements for the SIS in the fullness of time. Note that subnational institutional arrangements are not shown for clarity (and not covered in the ppt due to time constraints).

## Slide 6: Lessons
  COLLARABORATION WITH ALL RELEVANT INSTITUTION IS IMPORTANT IN ORDER TO EHNANCE SIS INFORMATION FLOW

## Slide 7: END !!