13 July 2012

NPWG call

Participants: Maria Sanz, Julie Greenwalt, Tim Clairs, Clea Paz

AGENDA

- Zambia.

  - Targeted support vis-à-vis NP. Please see attached the TS letter and the links to the NPD and latest report here and here

  - NPWG to discuss:

    - overlaps if any between proposed TS activities and the NP

    - agreed recommendations to be send to FAO/GPWG for the response

Background information

Zambia is one of the first NPs (signed in 2010) and has suffered significant implementation delays. Latest delivery information as of December 2012 shows a 14% delivery rate based on the transferred funds. Outputs 1.1, 3.3, and 5.1, have planned activities on capacity needs assessment, legal analysis, and data collection for REDD+ readiness (which can include safeguards). This year implementation has progressed significantly, in particular for the FAO components. Latest figures for expenditure will need to be updated.

Action points

- After discussing, participants agreed that there is a clear overlap between the proposed Targeted Support request and National Programme activities

- While the issue of safeguards is very relevant, the timing of starting activities in this area needs to be considered vis-à-vis the overall progress on REDD+ readiness work in the country, which has just started to pick up.

- There is need of further discussion at a country level and management level before sending a response. The discussion with the country team could clarify:

  - Understanding  the country perception on the potential of the NP to support the safeguards work

  - Understanding the needs and gaps to be filled out

- The group emphasized the need to have a coordinated response and communicate better our work on safeguards

- The NPWG confirmed it understanding that as per the Targeted Support procedures, the response to Zambia should be sent by the Secretariat.  This understanding is to be communicated to the GPWG by Clea Paz

- Upcoming inter-sessional decisions for NPs (information)

  - Sending the decisions is pending the PB confirmation that we can operate with one Co-Chair

  - Once this is resolved the Sec will send 2 inter-sessional decisions: Colombia, and new requests to join the Programme (Morocco and Lao PDR)

- NP reports due in September (JE to join)

  - Message with revised template was sent to RTAs copying the Gov focal points in June (June 6 in English and June 14 in Spanish and French). Set deadline is September 3. For Viet Nam deadline is set for September 24 (so they can produce a final report)

  - JE is preparing a revised template for the consolidated report, to be agreed with the MPTF-O

Action points

- The Secretariat will send reminders on the deadline for the reports

- As the semi-annual report is not a requirement for the MPTF-O, the Secretariat will analyze if the consolidated report is needed or the annexes are sufficient

- Update the information on lead agencies (in charge of coordinating the inputs for the other agencies to the report) on the tracking tool –DONE

- UNEP nominated temporarily (until the decision is done at a country level) to act as lead agency for Panama, to be confirmed by Gabriel when he is back

- NP session on the next PB meeting

  - Based on the latest PB meeting, the Secretariat is proposing to have a dedicated session for implementation of NPs, please see attached a preliminary agenda for the session-

  - NPWG to discuss the preliminary agenda, discuss if all the NP issues are covered, and provide inputs on the topics and organization of the session

Action points

- NPWG to provide inputs to the draft agenda for this session, including the contribution of the new Action Team on implementation of NPs to the session

- Time and date of next NPWG calls – Holiday period has started and most will be unavailable next month

Action point: Calls will resume on August 24

- AOB

Ecuador: The Secretariat informed there is a call on Ecuador today regarding revising the budget. The Secretariat proposes that considering: funds have been transferred, the Government counterpart is ready to move forward, and there is a significant delay in starting implementation; activities should start with the existing funds, and a budget revision should be postponed for next year if needed. The NPWG agreed with this proposed response.