TERMS OF REFERENCE

Individual Contractor

##### Assignment Information

| Assignment Title: | Preparatory work for the Development of National Protected Areas Strategic Management Plan |
| --- | --- |
| Post Level: | Senior Specialist |
| Contract Type: | # Individual Contractor (IC) |
| Duty Station: | # Home based and non-home-based (Phnom Penh) |
| Expected Place of Travel: | # N/A |
| Contract Duration: | # 56 days, and from 1 April 2014 to 1 October 2014 |

##### Background

In 1993, His Majesty King Norodom Sihanouk introduced a Royal Decree designating 23 areas, covering about 3.3 million ha (18.3 % of total land area), as protected areas. The current national protected areas system includes seven national parks, ten wildlife sanctuaries, three protected landscapes, three multiple use areas managed by the Ministry of Environment.  These areas are governed by a variety of policy, including the Constitution of Cambodia (1993), the Protected Area Law (2008) and the Law on Environmental Protection and Natural Resources Development (1996).

These regulations will be complemented by the National Protected Areas Strategic Management Plan that will also act as an important tool to link REDD+ and protected area management at a national level. A future mechanism on REDD+ provides an opportunity for Cambodia to be rewarded for its efforts to protect and sustainably use its forests and can as such help to support the implementation of the National Protected Areas Strategic Management Plan in particular when this leads to reducing emissions from deforestation and forest degradation and/or enhancing removals of greenhouse gasses from the restoration and establishment of new forests.

The management of the Protected Area system is mainly regulated by the Protected Area Law (PA Law 2008) and the Law on Environmental Protection and Natural Resources Development (1996). The objectives of these laws are to ensure the management, conservation of biodiversity, and sustainable use of natural resources in protected areas. The GDANCP of MoE is the designed Ministry responsible for the planning and management of the protected areas system, their supervision and coordination (Art. 4). In particular, it is the duty of GDANCP to develop strategic plans, action plans, and technical guidelines for managing the protected areas (Art. 5). In this regards the PA Law prescribes that a National Protected Areas Strategic Management Plan (NPASMP) should be developed (Art 15). The National Biodiversity Strategy and Action Plan (MoE 2002), that was developed to meet the obligation of the international Convention on Biological diversity (CBD), also recognizes the need to “develop a management plan for  protected  and buffer zones in collaboration with local communities and relevant ministries” such as MoE, MAFF, MRD, MLMUPC and MoI (Objective and Priority Action 1.1.1).

The NPASMP, as a regulatory instrument, will indicate how to implement the national protected area policies effectively. The NPASMP is expected to be a concise document of focused and detailed set of policies for defining the overall institutional arrangements and priority strategies that are required to design, manage and financing protected areas. This includes the definition of economic development and biodiversity conservation goals that are aimed to be achieved through Protected Areas and the provision of information for developing further guidelines and sub-decrees, sustainable funding arrangements, management planning and zoning, monitoring and reporting, and the further elaboration of a set of community protected areas.

The NPASMP should be seen in context of existing work on a framework document that will inform and guide the development of a National Protected Areas Strategic Management Plan which currently is being developed. This framework will among other things seek to enhance coherence in the implementation of sectoral policies and plans, bearing in mind the ecosystem approach, the Addis Ababa Principles and Guidelines for the Sustainable Use of Biodiversity, the Sustainable Development Goals (currently under development) and other international and regional agreements to which Cambodia is a party.

The work carried out under this assignment is to deliver two important assessments for the development of the NPASMP namely an assessment of existing approaches to Protected Area management and an assessment of current state of Protected Area management.

##### Scope of Work

Assessment of existing approaches to Protected Area management

- Conduct an assessment of existing approaches to Protected Area management through a collation of existing initiatives and frameworks and associated capacity building strategies related to protected area management and conduct a SWOT analysis as part of the assessment in order to:

  - clarify objectives of the conservation, rehabilitation, prevention, suppression of illegal activities and sustainable use of natural resources and ecosystem within individual protected area (PA Law Art. 16.1), including monitoring systems;

  - suggest recommended actions for successful achievement of the protected area objectives (PA Law Art. 16.4);

  - suggest steps to implement management plans for priority protected areas (PA Law Art. 16.4),

  - suggest possibilities of financing Protected Area management (Payment of Ecosystem Services, REDD+ etc.)

- This should be done through:

  - Review and collation of existing policy, regulations and plans related to protected area functions and management

  - Review of existing sub-national approaches and practices related to PA management

  - Review of international plans and guidelines related to PA management

  - Collation of existing initiatives and frameworks and associated capacity building strategies related to protected area management

  - Information gathered from the sub-regional stakeholder consultation meetings (these meetings will be organized and conducted by the two national consultants with technical input from the International Consultant)

Assessment of current status of Protected Area management

- Conduct an assessment of current status of Protected Area management through the assessment of:

  - the current status of natural resources and ecosystems within each zone including flora and fauna species, genetic resources and socio-cultural aspects (PA Law Art. 16.2),

  - the contribution of each protected area to achieving biodiversity and natural resources protection and conservation (PA Law Art 16.3), as well as the role of PA in rural poverty reduction and economic development

  - increase the understanding of the role of communities and stakeholders in PA management

- This will be done through:

  - Literature and inventory data review

  - Review the lessons learned and best practices observed at sub-national level and in as pilot projects

Follow-up

- Organize a national consultation meeting to present and discuss findings:

  - In collaboration with the REDD+ Taskforce Secretariat, the consultant team should design and organize a consultation meeting to be held in Phnom Penh. For the meeting organization, the team will be responsible for 1) preparing the meeting agenda, 2) identify key national stakeholders for Cambodia for protected areas management, 3) identifying relevant speakers and 4) preparing presentations to facilitate discussions.

- Write a synthesis report outlining existing approaches, practices and lessons learnt on Protected Area management including considerations on improved linkages between protected areas planning and management and other forms of land and forest management, including REDD+ and provide recommendations for the development of the Protected Areas Strategic Management Plan;

- Provide technical support and inputs to the working group developing the NPASMP as required;

##### Expected Outputs and Deliverables

- An assessment of existing approaches to Protected Area management including a SWOT analysis;

- An assessment of current status of Protected Area management;

- A synthesis report outlining existing approaches, practices and lessons learnt on Protected Area management

| N | Deliverables/Outputs | Estimated Duration to Complete | Target Due Dates | Review and Approvals Required |
| --- | --- | --- | --- | --- |
| 1 | Work plan of the assignment | 4 days | 10 April 2014 | UN-REDD NPD |
| 2 | Report on the assessment of existing approaches to Protected Area management | 20 days | 25 May 2014 | UN-REDD NPD |
| 3 | Report on the assessment of current status of Protected Area management | 20 days | 15 August 2014 | UN-REDD NPD |
| 4 | Organize a national consultation meeting | 4 days | 29 August 2014 | UN-REDD NPD |
| 5 | Synthesis report outlining existing approaches, practices and lessons learnt on Protected Area management | 8 days | 15 September 2014 | UN-REDD NPD |
| Total 56 of Days: |  |  |  |  |

##### Institutional Arrangement

- The Consultant will report to the UN-REDD National Programme Deputy Director and will be supervised by Deputy Director General, GDANCP and the Technical Specialist, REDD+ Taskforce Secretariat on day-to-day basis.

- The Consultant will be accountable for timely and quality outputs and report monthly to the REDD+ Taskforce Secretariat on progress compared to the work plan.

- The Consultant will work in close collaboration with the national consultant.

- The Consultant is furthermore expected to consult relevant stakeholders involved in Protected Areas Management. The national consultant is expected to have the necessary network and to assist the international consultant in conducting consultations with relevant stakeholders.

##### Duration of the Work

The duration of the work from 1 April 2014 to 1 October 2014 for a total of 56 working days.

##### Duty Station

The duty stations for this assignment are Phnom Penh, Cambodia and home country. During the assignment the consultant is expected to be in Phnom Penh, Cambodia for a total of 35 days, two times, first time for 15 days, between 1 April and 15 May, second for 20 days between 1 August and 15 September 2014.

The consultant will be hosted at and be allocated an office space by the GDANCP. Travelling costs in Phnom Penh will be borne by the consultant.

##### Minimum Qualifications of the Individual Contractor

| Education: | - At minimum, Master’s degree or equivalent in natural resource management or a related field; |
| --- | --- |
| Experience: | - A minimum of 10 years of relevant experience; - Substantial and diverse experience in management of natural resources, protected areas strategies or programs. |
| Competencies: | - Good analytical and communication skills, including the ability to draft and to articulate ideas in a clear and concise manner; - Good interpersonal skills, previous exposure to cross cultural environments is an advantage; ability to work well in a team whilst also having the capacity and initiative to work independently; - Sound knowledge of disciplines relevant to development work and climate change, with added consideration given to those with experience in protected area management and REDD+ policy-related in general. |
| Language Requirement: | - Highly developed oral and written communications skills with excellent writing skills in English. |
| Other Requirements (if any): | - Prior experience of working in Cambodia is a significant asset. |

##### Criteria for Evaluation of Level of Technical Compliance of Individual Contractor

| Technical Evaluation Criteria | Obtainable Score |
| --- | --- |
| Relevant educational background | 25 |
| Proved relevant technical skills related to the fields of natural resource management and policy | 35 |
| Proved experience in producing high quality reports | 25 |
| Prior working experience with Cambodia | 15 |
| Total Obtainable Score: | 100 |

##### Payment Milestones

The consultant will be paid on a lump sum basis under the following installments.

| N | Outputs/Deliveries | Payment Schedule | Payment Amount |
| --- | --- | --- | --- |
| 1 | Upon satisfactory completion of the assessment of existing approaches to Protected Area management | May 2014 | 30% |
| 2 | Upon satisfactory completion of the assessment of current status of Protected Area management | August 2014 | 35 % |
| 3 | Upon satisfactory completion of the summary report outlining existing approaches, practices and lessons learnt on Protected Area management | September 2014 | 35 % |

##### Annexes

- The Protected Area Law