CONCEPT PAPER

| Title of activity | Sun-national consultation meeting on benefit sharing for REDD+ in Cambodia |
| --- | --- |
| Outcome/output from Results Framework | 2.3c: Consultation on results from the assessment under 2.3b |
| Anticipated timing | 1st March to 1 June 2014 |
| Duration | 45 days |

Objective of activity:

The meetings has the following specific objective: - To present pros and cons of using different benefit distribution models in terms of effectiveness, efficiency and equity; - To consult with key stakeholders at sub-national level on option of benefit sharing for REDD+ in Cambodia.

Justification:

Output 2.3b of the UN-REDD National Programme include an activity to assess existing benefit sharing distribution models used in Cambodia and other parts of the world relevant for REDD+ in Cambodia. The meetings will provide an opportunity to present and discuss the findings from an assessment of existing benefit sharing models used in Cambodia and other parts of the world relevant for REDD+ and collect views from sub-national level.

Approach:

First, the meeting will introduce the REDD+ readiness in Cambodia and then the REDD+ Concept.​Second, the consultancy team hired will present the options of benefit sharing on REDD+ assessment and third, the team will facilitate into key group to consult the options for benefit sharing for REDD+. The meetings will provide an opportunity to collect information on relevant REDD+ activities at the local level and how this can be supported through benefit sharing. The key stakeholders at sub-national including the Forestry Administration Cantonment (FAC), Fisheries Administration Cantonment (FiAC), relevant provincial department (Agriculture, Environment, Land Management, Rural Development, Economic and Finance,​Industry Mine and Energy)local authority (Provincial Administration, District),local NGOs, and community representatives (CF, CFi, CPA, IP) in total 43 people for each meeting. ​The meeting will be organized in 10 provinces including Siem Reap, Kampong Thom, Ratanakiri, Stung Treng, Kratie, Mundulkiri, Pursat, Preah Vihear, Oddar Meanchey, and Battambang. The consultants will seek the active involvement of members of the technical team on benefit sharing in carrying out the assignment and the end product will be useful for designing a future benefit sharing mechanism for Cambodia.

Key Outputs:

The outputs of the activity will be: the participant understand the REDD+ Concept and benefit sharing models in terms of effectiveness, efficiency and equity and they provide an assessment of existing benefit sharing models used in Cambodia for REDD+. Increased awareness on the requirements for a sub-national benefit sharing models relevant to REDD+ in Cambodia. A report documenting the results of the sub-national meetings including possible recommendations for the further work.

Agenda: (will be revised later)

| Time | Topic | Speaker/Presenter |
| --- | --- | --- |
| 08.00-08.30 | Registration | Mr. Neab Keng, |
| 08.30-09.00 | Opening Ceremony - National Anthem - Opening speech | UNREDD+ Secretariat/ FAC/FiAC/DoE |
| 09.00-09.10 | Group photo | Mr. Yim Heng |
| 09.10-09.20 | Introducing and Objective of the Meeting | Mr. Heng Hong |
| 09.20-09.45 | Concept of REDD+ | Mr. Long Ratanakoma |
| 09.45-10.00 | Why benefit sharing | Mr. Heng Hong |
| 10.00-10.30 | Coffee break |  |
| 10.30-11.00 | Experience of BS from CF/CPA/CFi | CF Representative |
| 11.00-11.30 | Possible option for REDD+ BS in Cambodia | Mr. Long Ratanakoma |
| 11.30-12.00 | Q and A | Mr. Long Ratanakoma |
| 12.00-14.00 | Lunch |  |
| 14.00-14.30 | Group discussion: - Provincial department; - Local authority; - Local community; - NGOs. Key questions: - What is your role and activities in REDD+? - What kind of benefit from your activities? - What is your existing BS mechanism? - What is fund flow? | Mr. Long Ratanakoma Mr. Heng Hong Mr. Neab Keng Mr. Yim Heng |
| 14.30-15.00 | Group presentation and plenary discussion | Mr. Heng Hong |
| 15.00-16.00 | Wrap up | Mr. Long Ratanakoma |

Suggested participants:46 people

| No. | Institution | No. of Participants | Remark |
| --- | --- | --- | --- |
|  | Provincial department | 10 |  |
|  | District governor | 5 |  |
|  | Commune Council | 5 |  |
|  | CF, CFi, CPA; IP | 16 |  |
|  | BS Technical Team (BST) | 2 |  |
|  | National Consultant and Meeting Organizing team (FA, MoE, FiA) | 5 |  |
|  | Local NGOs | 5 |  |
|  | Total | 48 |  |

- Budget Estimated for Kampong Thom Province

| No | Description | Unit | P/S | W/D | Rate ($) | Time | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DSA for Nat Consultant (NC) | Person | 2 | 2 | 31.50 | 1 | 126.00 |
| 2 | DSA for meeting organizing team(FA, MoE, FiA) | Person | 3 | 2 | 31.50 | 1 | 189.00 |
| 3 | Fee for local FA to facilitate the meeting | Person | 1 | 4 | 11.50 | 1 | 46.00 |
| 4 | DSA for BS Technical Team (BST) | Person | 4 | 2 | 31.50 | 1 | 252.00 |
| 5 | DSA for district governor (DGv) | Person | 7 | 2 | 15.75 | 1 | 220.50 |
| 6 | DSA for commune council (CC) | Person | 7 | 2 | 15.75 | 1 | 220.50 |
| 7 | DSA for CF/CPA/CFi/IP (4 of each) | Person | 14 | 2 | 15.75 | 1 | 441.00 |
| 8 | DSA for provincial department | Person | 11 | 2 | - | 1 | - |
| 9 | DSA for local NGOs | Person | 5 | 2 | - | 1 | - |
| 10 | DSA presenter to sharing Experience on BS | Person | 1 | 2 | 31.30 | 1 | 62.60 |
| 11 | Fee for presenter to sharing experience on BS | Person | 1 | 1 | 50.00 | 1 | 50.00 |
| 12 | Fee for Hornorable guest | Person | 1 | 1 | 100.00 | 1 | 100.00 |
| 13 | Transportation for NC | Person | 2 | 2 | 30.00 | 1 | 120.00 |
| 14 | Transportation for Organizing team | Person | 3 | 2 | 30.00 | 1 | 180.00 |
| 15 | Transportation for BST | Person | 2 | 2 | 30.00 | 1 | 120.00 |
| 16 | Transportation for DGv | Person | 7 | 2 | 10.00 | 1 | 140.00 |
| 17 | Transportation for CC and CF/CPA/CFi | Person | 21 | 2 | 10.00 | 1 | 420.00 |
| 18 | Transportation for provincial department | Person | 11 | 2 | - | 1 | - |
| 19 | Transportation for local NGOs | Person | 5 | 2 | - | 1 | - |
| 20 | Local transport for NC | set | 1 | 1 | 50.00 | 1 | 50.00 |
| 21 | Invitation deliver to Province (Taxi) | Set | 1 | 1 | 20.00 | 1 | 20.00 |
| 22 | Invitation deliver at Province | Person | 1 | 1 | 100.00 | 1 | 100.00 |
| 23 | Backdrop | Unit | 1 | 1 | 100.00 | 1 | 100.00 |
| 24 | Hire LCD projector | Unit | 1 | 1 | 80.00 | 1 | 80.00 |
| 25 | Hire laptop | Unit | 1 | 1 | 50.00 | 1 | 50.00 |
| 26 | Communication (cellcard) | Unit | 2 | 1 | 30.00 | 1 | 60.00 |
| 27 | Logistic | Person | 55 | 1 | 3.00 | 1 | 165.00 |
| 28 | Venue (refreshment & include lunch) | Person | 55 | 1 | 20.00 | 1 | 1,100.00 |
|  |  |  |  | Grant Total |  |  | 4,412.60 |

- Budget Estimated for Preah Vihear, Oddar Meanchey, Siem Reap Province

| No | Description | Unit | P/S | W/D | Rate ($) | Time | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DSA for Nat Consultant (NC) | Person | 2 | 2 | 31.50 | 3 | 378.00 |
| 2 | DSA for meeting organizing team(FA, MoE, FiA) | Person | 3 | 2 | 31.50 | 3 | 567.00 |
| 3 | Fee for local FA to facilitate the meeting | Person | 1 | 4 | 11.50 | 3 | 138.00 |
| 4 | DSA for BS Technical Team (BST) | Person |  | 2 | 31.50 | 3 | - |
| 5 | DSA for district governor (DGv) | Person | 5 | 2 | 15.75 | 3 | 472.50 |
| 6 | DSA for commune council (CC) | Person | 5 | 2 | 15.75 | 3 | 472.50 |
| 7 | DSA for CF/CPA/CFi/IP (4 of each) | Person | 16 | 2 | 15.75 | 3 | 1,512.00 |
| 8 | DSA for provincial department | Person | 11 | 2 | - | 3 | - |
| 9 | DSA for local NGOs | Person | 5 | 2 | - | 3 | - |
| 10 | DSA presenter to sharing Experience on BS | Person | 1 | 2 | 31.30 | 3 | 187.80 |
| 11 | Fee for presenter to sharing experience on BS | Person | 1 | 1 | 50.00 | 3 | 150.00 |
| 12 | Fee for Hornorable guest | Person | 1 | 1 | 100.00 | 3 | 300.00 |
| 13 | Transportation for NC | Person | 2 | 2 | 30.00 | 3 | 360.00 |
| 14 | Transportation for Organizing team | Person | 3 | 2 | 30.00 | 3 | 540.00 |
| 15 | Transportation for BST | Person |  | 2 | 30.00 | 3 | - |
| 16 | Transportation for DGv | Person | 5 | 2 | 10.00 | 3 | 300.00 |
| 17 | Transportation for CC and CF/CPA/CFi | Person | 21 | 2 | 10.00 | 3 | 1,260.00 |
| 18 | Transportation for provincial department | Person | 11 | 2 | - | 3 | - |
| 19 | Transportation for local NGOs | Person | 5 | 2 | - | 3 | - |
| 20 | Local transport for NC | set | 1 | 1 | 50.00 | 3 | 150.00 |
| 21 | Invitation deliver to Province (Taxi) | Set | 1 | 1 | 20.00 | 3 | 60.00 |
| 22 | Invitation deliver at Province | Person | 1 | 1 | 100.00 | 3 | 300.00 |
| 23 | Backdrop | Unit | 1 | 1 | 100.00 | 3 | 300.00 |
| 24 | Hire LCD projector | Unit | 1 | 1 | 80.00 | 3 | 240.00 |
| 25 | Hire laptop | Unit | 1 | 1 | 50.00 | 3 | 150.00 |
| 26 | Communication (cellcard) | Unit | 2 | 1 | 30.00 | 3 | 180.00 |
| 27 | Logistic | Person | 48 | 1 | 3.00 | 3 | 432.00 |
| 28 | Venue (refreshment & include lunch) | Person | 48 | 1 | 20.00 | 3 | 2,880.00 |
|  |  |  |  | Grant Total |  |  | 11,329.80 |

- Budget Estimated for Pursat, Battambang Province

| No | Description | Unit | P/S | W/D | Rate ($) | Time | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DSA for Nat Consultant (NC) | Person | 2 | 2 | 31.50 | 2 | 252.00 |
| 2 | DSA for meeting organizing team(FA, MoE, FiA) | Person | 3 | 2 | 31.50 | 2 | 378.00 |
| 3 | Fee for local FA to facilitate the meeting | Person | 1 | 4 | 11.50 | 2 | 92.00 |
| 4 | DSA for BS Technical Team (BST) | Person | 4 | 2 | 31.50 | 1 | 252.00 |
| 5 | DSA for district governor (DGv) | Person | 8 | 2 | 15.75 | 2 | 504.00 |
| 6 | DSA for commune council (CC) | Person | 8 | 2 | 15.75 | 2 | 504.00 |
| 7 | DSA for CF/CPA/CFi/IP (4 of each) | Person | 16 | 2 | 15.75 | 2 | 1,008.00 |
| 8 | DSA for provincial department | Person | 11 | 2 | - | 2 | - |
| 9 | DSA for local NGOs | Person | 5 | 2 | - | 2 | - |
| 10 | DSA presenter to sharing Experience on BS | Person | 1 | 2 | 31.30 | 2 | 125.20 |
| 11 | Fee for presenter to sharing experience on BS | Person | 1 | 1 | 50.00 | 2 | 100.00 |
| 12 | Fee for Hornorable guest | Person | 1 | 1 | 100.00 | 2 | 200.00 |
| 13 | Transportation for NC | Person | 2 | 2 | 30.00 | 2 | 240.00 |
| 14 | Transportation for Organizing team | Person | 3 | 2 | 30.00 | 2 | 360.00 |
| 15 | Transportation for BST | Person | 4 | 2 | 30.00 | 1 | 240.00 |
| 16 | Transportation for DGv | Person | 8 | 2 | 10.00 | 2 | 320.00 |
| 17 | Transportation for CC and CF/CPA/CFi | Person | 24 | 2 | 10.00 | 2 | 960.00 |
| 18 | Transportation for provincial department | Person | 11 | 2 | - | 2 | - |
| 19 | Transportation for local NGOs | Person | 5 | 2 | - | 2 | - |
| 20 | Local transport for NC | set | 1 | 1 | 50.00 | 2 | 100.00 |
| 21 | Invitation deliver to Province (Taxi) | Set | 1 | 1 | 20.00 | 2 | 40.00 |
| 22 | Invitation deliver at Province | Person | 1 | 1 | 100.00 | 2 | 200.00 |
| 23 | Backdrop | Unit | 1 | 1 | 100.00 | 2 | 200.00 |
| 24 | Hire LCD projector | Unit | 1 | 1 | 80.00 | 2 | 160.00 |
| 25 | Hire laptop | Unit | 1 | 1 | 50.00 | 2 | 100.00 |
| 26 | Communication (cellcard) | Unit | 2 | 1 | 30.00 | 2 | 120.00 |
| 27 | Logistic | Person | 58 | 1 | 3.00 | 2 | 348.00 |
| 28 | Venue (refreshment & include lunch) | Person | 58 | 1 | 20.00 | 2 | 2,320.00 |
|  |  |  |  | Grant Total |  |  | 9,123.20 |

- Budget Estimated for Kratie, Mundulkiri Province

| No | Description | Unit | P/S | W/D | Rate ($) | Time | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DSA for Nat Consultant (NC) | Person | 2 | 2 | 31.50 | 2 | 252.00 |
| 2 | DSA for meeting organizing team(FA, MoE, FiA) | Person | 3 | 2 | 31.50 | 2 | 378.00 |
| 3 | Fee for local FA to facilitate the meeting | Person | 1 | 4 | 11.50 | 2 | 92.00 |
| 4 | DSA for BS Technical Team (BST) | Person |  | 2 | 31.50 | 2 | - |
| 5 | DSA for district governor (DGv) | Person | 6 | 2 | 15.75 | 2 | 378.00 |
| 6 | DSA for commune council (CC) | Person | 6 | 2 | 15.75 | 2 | 378.00 |
| 7 | DSA for CF/CPA/CFi/IP (4 of each) | Person | 16 | 2 | 15.75 | 2 | 1,008.00 |
| 8 | DSA for provincial department | Person | 11 | 2 | - | 2 | - |
| 9 | DSA for local NGOs | Person | 5 | 2 | - | 2 | - |
| 10 | DSA presenter to sharing Experience on BS | Person | 1 | 2 | 31.30 | 2 | 125.20 |
| 11 | Fee for presenter to sharing experience on BS | Person | 1 | 1 | 50.00 | 2 | 100.00 |
| 12 | Fee for Hornorable guest | Person | 1 | 1 | 100.00 | 2 | 200.00 |
| 13 | Transportation for NC | Person | 2 | 2 | 30.00 | 2 | 240.00 |
| 14 | Transportation for Organizing team | Person | 3 | 2 | 30.00 | 2 | 360.00 |
| 15 | Transportation for BST | Person |  | 2 | 30.00 | 2 | - |
| 16 | Transportation for DGv | Person | 6 | 2 | 10.00 | 2 | 240.00 |
| 17 | Transportation for CC and CF/CPA/CFi | Person | 32 | 2 | 10.00 | 2 | 1,280.00 |
| 18 | Transportation for provincial department | Person | 11 | 2 | - | 2 | - |
| 19 | Transportation for local NGOs | Person | 5 | 2 | - | 2 | - |
| 20 | Local transport for NC | set | 1 | 1 | 50.00 | 2 | 100.00 |
| 21 | Invitation deliver to Province (Taxi) | Set | 1 | 1 | 20.00 | 2 | 40.00 |
| 22 | Invitation deliver at Province | Person | 1 | 1 | 100.00 | 2 | 200.00 |
| 23 | Backdrop | Unit | 1 | 1 | 100.00 | 2 | 200.00 |
| 24 | Hire LCD projector | Unit | 1 | 1 | 80.00 | 2 | 160.00 |
| 25 | Hire laptop | Unit | 1 | 1 | 50.00 | 2 | 100.00 |
| 26 | Communication (cellcard) | Unit | 2 | 1 | 30.00 | 2 | 120.00 |
| 27 | Logistic | Person | 50 | 1 | 3.00 | 2 | 300.00 |
| 28 | Venue (refreshment & include lunch) | Person | 50 | 1 | 20.00 | 2 | 2,000.00 |
|  |  |  |  | Grant Total |  |  | 8,251.20 |

- Budget Estimated for Stung Treng, Ratanakiri Province

| No | Description | Unit | P/S | W/D | Rate ($) | Time | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DSA for Nat Consultant (NC) | Person | 2 | 2 | 31.50 | 2 | 252.00 |
| 2 | DSA for meeting organizing team(FA, MoE, FiA) | Person | 3 | 2 | 31.50 | 2 | 378.00 |
| 3 | Fee for local FA to facilitate the meeting | Person | 1 | 4 | 11.50 | 2 | 92.00 |
| 4 | DSA for BS Technical Team (BST) | Person |  | 2 | 31.50 | 2 | - |
| 5 | DSA for district governor (DGv) | Person | 6 | 2 | 15.75 | 2 | 378.00 |
| 6 | DSA for commune council (CC) | Person | 6 | 2 | 15.75 | 2 | 378.00 |
| 7 | DSA for CF/CPA/CFi/IP (4 of each) | Person | 16 | 2 | 15.75 | 2 | 1,008.00 |
| 8 | DSA for provincial department | Person | 11 | 2 | - | 2 | - |
| 9 | DSA for local NGOs | Person | 5 | 2 | - | 2 | - |
| 10 | DSA presenter to sharing Experience on BS | Person | 1 | 2 | 31.30 | 2 | 125.20 |
| 11 | Fee for presenter to sharing experience on BS | Person | 1 | 1 | 50.00 | 2 | 100.00 |
| 12 | Fee for Hornorable guest | Person | 1 | 1 | 100.00 | 2 | 200.00 |
| 13 | Transportation for NC | Person | 2 | 2 | 40.00 | 2 | 320.00 |
| 14 | Transportation for Organizing team | Person | 3 | 2 | 30.00 | 2 | 360.00 |
| 15 | Transportation for BST | Person |  | 2 | 30.00 | 2 | - |
| 16 | Transportation for DGv | Person | 6 | 2 | 10.00 | 2 | 240.00 |
| 17 | Transportation for CC and CF/CPA/CFi | Person | 32 | 2 | 10.00 | 2 | 1,280.00 |
| 18 | Transportation for provincial department | Person | 11 | 2 | - | 2 | - |
| 19 | Transportation for local NGOs | Person | 5 | 2 | - | 2 | - |
| 20 | Local transport for NC | set | 1 | 1 | 50.00 | 2 | 100.00 |
| 21 | Invitation deliver to Province (Taxi) | Set | 1 | 1 | 20.00 | 2 | 40.00 |
| 22 | Invitation deliver at Province | Person | 1 | 1 | 100.00 | 2 | 200.00 |
| 23 | Backdrop | Unit | 1 | 1 | 100.00 | 2 | 200.00 |
| 24 | Hire LCD projector | Unit | 1 | 1 | 80.00 | 2 | 160.00 |
| 25 | Hire laptop | Unit | 1 | 1 | 50.00 | 2 | 100.00 |
| 26 | Communication (cellcard) | Unit | 2 | 1 | 30.00 | 2 | 120.00 |
| 27 | Logistic | Person | 50 | 1 | 3.00 | 2 | 300.00 |
| 28 | Venue (refreshment & include lunch) | Person | 50 | 1 | 20.00 | 2 | 2,000.00 |
|  |  |  |  | Grant Total |  |  | 8,331.20 |

LIST OF PARTICIPANTS

The Sub-National Consultation Meeting on BS for REDD+ in Cambodia

| No. | Name | Position | Institution | Others |
| --- | --- | --- | --- | --- |
| II | ខេត្តកំពង់ធំ |  |  |  |
|  | មន្ទីរជុំវិញខេត្ត និងខណ្ឌ |  |  |  |
| ១ |  | ប្រធាន | មន្ទីរបរិស្ថាន |  |
| ២ |  | ប្រធាន | មន្ទីរអភិវឌ្ឍន៍ជនបទ |  |
| ៣ |  | ប្រធាន | មន្ទីររៀបចំដែនដី នគរូបនីយកម្មនិង​សំណង់ |  |
| ៤ |  | ប្រធាន | មន្ទីរកសិកម្ម |  |
| ៥ |  | ប្រធាន | មន្ទីរឧស្សាហកម្ម រ៉ែ​ និង​ថាមពល |  |
| ៦ |  | ប្រធាន | មន្ទីរសេដ្ចកិច្ច​ និងហិរញ្ញវត្ថុ |  |
| ៧ |  | ប្រធាន | រដ្ឋបាលសាលា |  |
| ៨ |  | នាយ | ខណ្ឌរដ្ឋបាលពព្រៃឈើ |  |
| ៩ |  | នាយ | ខណ្ឌរដ្ឋបាលជលផល |  |
| ១០ |  | នាយ | អធិការដ្ឋានរដ្ឋបាលព្រៃឈើ |  |
|  | អាជ្ញាធរស្រុក |  |  |  |
| ១ |  |  | ស្រុកបា្រសាទបាល្ល័ង្ក |  |
| ២ |  |  | ស្រុកប្រាសាទសំបូរ |  |
| ៣ | លោក រស់ សារីម | អភិបាលរង | ស្រុកសន្ទុក |  |
| ៤ | លោក ទួត​ ម៉ារី | អភិបាលរង | ស្រុកសណ្តាន់ |  |
| ៥ |  |  | ស្រុកកំពង់ស្វាយ |  |
| ៦ |  |  | ស្រុកស្ទោង |  |
| ៧ |  |  | ស្រុកស្ទឹងសែន |  |
|  | អាជ្ញាធរឃុំ |  |  |  |
| ១ |  | ក្រុមប្រឹក្សា | ឃុំទំរីង |  |
| ២ |  | ក្រុមប្រឹក្សា | ឃុំដំរីស្លាប់ |  |
| ៣ | លោក ព្រាប​ ហាវ | ជំទប់ទី១ | ឃុំទួលគ្រើល | 012392541 |
| ៤ | លោក កាំង មួង | ជំទប់ទី២ | ឃុំទីពោ | 077289088 |
| ៥ |  |  | ឃុំមានរទ្ធិ |  |
| ៦ | លោក ជឹម ងួន | ក្រុមប្រឹក្សា | ឃុំក្រយា | 092860124 |
| ៧ |  |  | ឃុំដំរីស្លាប់ |  |
|  | អង្គការមិនមែនរដ្ឋាភិបាល |  |  |  |
| ១ | លោក រទ្ធិ ប៊ុនរឿន | នាយកប្រតិបត្តិ | AFD | 012928553 |
| ២ | លោក ផុន សុផាន | នាយកប្រតិបត្តិ | APA | 012869412 |
| ៣ | លោក ខេ ឆេង | នាយកប្រតិបត្តិ | ESSD | 012311458 |
| ៤ | លោក បី​ គឹមអឿន | នាយកប្រតិបត្តិ | DKK | 092931450 |
| ៥ | លោក កៅ វុត្ថា | បុគ្គលិក | RECOFTC | 012672434 |
|  | សហគមន៍ព្រៃឈើ |  |  |  |
| ១ |  | ប្រធាន | បណ្តាញស.ពខេត្តកំពង់ធំ | 0121832263 |
| ២ |  | ប្រធាន | បណ្តាញស.ពស្រុកប្រសាទសំបូរ |  |
| ៣ |  | ប្រធាន | បណ្តាញស.ពស្រុកទំរីង |  |
| ៤ |  | ប្រធាន | បណ្តាញស.ពស្រុកមានរទ្ធិ |  |
| ៥ |  | ប្រធាន | បណ្តាញស.ពស្រុកសណ្តាន់ |  |
| ៦ |  | ប្រធាន | បណ្តាញស.ពស្រុកស្ទោង |  |
| ៧ |  | ប្រធាន | បណ្តាញស.ពស្រុកស្ទឹងសែន |  |
|  | សហគមន៍តំបន់ការពារ |  |  |  |
| ១ |  |  |  |  |
| ២ |  |  |  |  |
| ៣ |  |  |  |  |
| ៤ |  |  |  |  |
|  | សហគមន៍ជលផល |  |  |  |
| ១ |  |  |  |  |
| ២ |  |  |  |  |
| ៣ |  |  |  |  |
| ៤ |  |  |  |  |
|  | សហគមន៍ជនជាតិដើមភាគតិច |  |  |  |
| ១ | លោក អ៊ុំ​ មិច | តំណាង | ជនជាតិដើមភាគតិច ក.ធំ |  |
| ២ | លោក គង់ ដូ | តំណាង | ជនជាតិដើមភាគតិច ក.ធំ |  |
| ៣ |  |  |  |  |
| ៤ |  |  |  |  |

Schedule for Sub-national Consultation Meeting

March

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1 |
|  | Develop Work plan, prepare and deliver invitation letters |  |  |  |  |  |
| 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 9 | 10 | 11 | 12 | 13 | 14 | 15 |
|  | Kg Thom |  |  | CF Champion | FCPF Launching |  |
| 16 | 17 | 18 | 19 | 20 | 21 | 22 |
|  | Famer Conference for 2013 |  |  |  |  |  |
| 23 | 24 | 25 | 26 | 27 | 28 | 29 |
| Travel | Preah Vihear | Travel | O. Meanchey | Travel | Siem Reap | Travel |
| 30 | 31 |  |  |  |  |  |

April

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  | Prepare Invitation and deliver |  |  |  |  |  |
| 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Travel | Pursat | Travel | Battambang | Travel | New year Ceremony |  |
| 13 | 14 | 15 | 16 | 17 | 18 | 19 |
|  | KhmerNewYear |  |  |  |  |  |
| 20 | 21 | 22 | 23 | 24 | 25 | 26 |
|  |  | Travel | Mundulkiri | Travel | Kratie | Travel |
| 27 | 28 | 29 | 30 |  |  |  |
|  | Stung Treng | Travel | Ratanakiri |  |  |  |

May

| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 |
|  |  |  |  | Travel |  |  |
| 4 | 5 | 6 | 7 | 8 | 9 | 10 |
|  | Report Writing |  |  |  | get comments |  |
| 11 | 12 | 13 | 14 | 15 | 16 | 17 |
|  | get comments | Official Holiday |  |  |  |  |
| 18 | 19 | 20 | 21 | 22 | 23 | 24 |
|  | Official Holiday | Final Report on BS |  |  |  |  |
| 25 | 26 | 27 | 28 | 29 | 30 | 31 |
|  | Prepare for BS National Consultation |  |  |  |  |  |

Target Provinces

26

24

25

7

9

28

23

30

28

10

Group Discussion

Groups will be divided into 3 groups including

- Provincial department;

- Local authority;

- Local community;

- NGOs

Key Question

- What is your role and activities in REDD+?

- What kind of benefit from your activities?

- What is your existing BS mechanism?

- What is fund flow?

| Roles and Activities | kind of benefits |
| --- | --- |