Term of References

Consultation on the assessment of existing benefit sharing models used in Cambodia and other parts of the world relevant for REDD+ in Cambodia

| ### Level | ### 1 National Consultant (Individual Contract) |
| --- | --- |
| ### Practice Area: | ### Benefit sharing, REDD+ (Forests and Climate Change) |
| ### Duration: | 55 Days |
| ### Duty Station: | ### Phnom Penh |
| ### Supervisor: | ### Technical Specialist, Programme Coordinator and REDD+ Taskforce Secretariat |
| ### Activity | ### 2.3c |

Background:

The Cancun Agreements issued at the Conference of Parties (COP) 16 held in Mexico in 2010 provides strong support for policy approaches that deliver positive incentives for countries and their actors to engage in REDD+ (reducing emissions from deforestation and forest degradation in developing countries; and the role of conservation, sustainable management of forests and enhancement of forest carbon stocks in developing countries).

Thus far, a number of decisions related to REDD+ have been made on subjects including implementation, principles and safeguards, assessment of results, and reference levels. However, decisions are yet to be made regarding how to deliver positive incentives for countries and their actors to reduce emissions from the forest sector through REDD+. As of now, it is up to each country to decide upon how REDD+ should be implemented within the framework agreed, including  issues related to how to distribute benefits at the national, regional and local levels, considering their national circumstances but also following the inter alia the safeguards listed in the Cancun Agreement.

Forests support the livelihoods of millions of rural indigenous peoples and communities who depend on forest resources for subsistence and income. Given the importance of forests for rural livelihoods, participating countries are required to apply safeguards in order to ensure “full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities” in REDD+ (as stated in the Cancun agreement).  The application of such safeguards is not only an important means of avoiding and mitigating possible negative impacts of REDD+ on these people but it can also serve to promote their active participation in forest and land conservation, as well as to reduce rural poverty which may contribute to achieving long term sustainable management of forests and carbon sequestration. On the contrary, the failure to involve local people and institutions in REDD+ and benefit sharing may risk lowering their incentives to engage in sustainable forest and land management, and thus may undermine the ultimate purpose of REDD+. Hence, it is imperative that indigenous peoples and local communities are also included in benefit sharing and that benefits are distributed in a manner that are equitable, transparent and cost-effective equitable.

Benefits are not limited to a monetary value but also include non-monetary values that may arise from improved forest governance. For instance, effective forest policies, programmes and measures to achieve REDD+ goals may not only generate income from carbon related payments but also deliver a broad range of multiple non-monetary benefits. REDD+ can contribute to new job opportunities, clarification and likely issuance of land tenure for communities and increased rural incomes and preservation of important ecosystem and environmental services and biodiversity.

With the completion of the REDD+ roadmap (2011) which defines key steps for Cambodia to be ready for REDD+ implementation, Cambodia has taken a first important step towards REDD+. The national REDD+ programme in Cambodia has also been supported by UN-REDD, CamREDD and other supporting frameworks that aim to build the national capacity to plan and implement REDD+. Since 2008, two REDD pilot projects have been implemented to test and learn from on the ground REDD+ activities. Despite numerous important initiatives having been undertaken, there remains a critical need for capacity building efforts for various actors involved in REDD+ including the issues of benefits sharing, and multiple benefits and costs associated with REDD+.

A decision on how to distribute benefits and to whom and in what forms at different levels will require careful analysis of possible options suitable to the national circumstance of Cambodia. For this reason, there is a need to assess and learn from national as well as international experiences with regard to benefit sharing mechanisms used in the forest sector (e.g. Payments for Environmental Services (PES) and REDD+ pilot projects). Such decisions will also require extensive consultation with relevant governments at national, provincial and local levels as well as discussions with all relevant stakeholders in order to ensure a common understanding and broad acceptance of a benefit sharing mechanism that is suitable for Cambodia. At the same time, ensuring the full and effective participation of all relevant stakeholders will contribute to avoiding the creation of unrealistic expectations about REDD+ benefits which in some cases has been noted as a problem in the past.

# Expected Outputs and Deliverables:

- A comprehensive consultation process on benefit sharing for REDD+ in Cambodia.

- A report on the consultations process highlighting key findings and concerns in English and Khmer with possible recommendations for further consultations.

| Expected delivery/output | Estimated duration to complete | Time period |
| --- | --- | --- |
| Development of consultation plan | 5 days | January |
| 15 local consultation meetings | 38 days | January to February |
| National consultation meeting in Phnom Penh | 3 day | March |
| Report for approval | 4 days | March |
| Final report with all comments included | 5 days | March |
| Total | 55 days |  |

The exact timing of this activity depends on the successful completion of the assessment of existing benefit sharing models.

# Duty Station

The duty station for this assignment is Phnom Penh with travel to the province. During the assignment the consultants are expected to be in Cambodia for all consultations.

Supervision, teamwork and administrative support:

There will be a team of two National Consultant who will work closely together in order to complete this task. They will report to the UN-REDD National Programme Director and on day-to-day basis will be supervised by the Technical Specialist and the REDD+ Taskforce Secretariat.

Monitoring and Progress Control

The consultancy teams will be accountable for the timely and quality output and report weekly to the REDD+ Taskforce Secretariat on progress compared to the workplan.

Payment milestones

Consultant will be paid on a lump sum basis under the following installments

- (20 %) 1st payment, upon submission and acceptance of the workplan for the consultation meetings.

- (40 %) 2nd payment, upon finalization of all consultation meetings in the province.

- (40 %) 3rd payment, upon submission and acceptance of the final report from activity.

Application

Applicants are requested to send CV, together with a letter of interest to REDD+ Taskforce Secretariat by either mail (N. 40, PreahNorodom Blvd. SangkatPhsarKandal 2, Khan Daun Penh, Cambodia) or e-mail (redd.secretariat@cambodia-redd.org).

# Detailed list of tasks for the national Consultant:

- Support the preparation of a plan for a country wide consultation process including one final consultation meeting in Phnom Penh on the results of the assessment of existing benefit sharing models including initial proposals for benefit sharing models;

- Consult with relevant stakeholders, including representatives from local government, and make any necessary adjustments to the consultation plan;

- Assist in the preparation of necessary information material for the consultations;

- For the meeting organization, the consultant will be responsible for 1) preparing the meeting agenda and identify the venue, 2) identify and invite key stakeholders, 3) identifying relevant speakers, 4) preparing presentations to facilitate discussions.

- Organize the national consultation meeting in Phnom Penh. The consultant will be responsible for 1) preparing the meeting agenda and identify the venue, 2) identify and invite key stakeholders including representatives from the provincial level, 3) identifying relevant speakers, 4) preparing presentations to facilitate discussions.

- Provide recommendations on further consultations as appropriate.

Competence Requirements

The National Consultant shall meet the following criteria:

- A minimum of a Master’s or equivalent degree in natural resource management, environmental economics and policy or a related field;

- A minimum of 5 years of relevant experience in natural resource management and policy

- Good analytical, writing and communication skills both in English and Khmer, including the ability to articulate ideas in a clear and concise manner;

- Good interpersonal skills and ability to work well in a team whilst also having the capacity and initiative to work independently;

- Sound knowledge of disciplines relevant to international development work and climate change.

| Evaluation criteria | Obtainable score |
| --- | --- |
| Relevant education and number of years experiences as required by the ToR | 20 points |
| Proved relevant technical skills related to the fields of natural resource management and policy, and inclusion of local communities in benefit sharing | 40 points |
| Prior experience with REDD+ | 20 points |
| Sound knowledge of disciplines relevant to international development work and climate change | 20 points |
| Total | 100 points |