# Cambodia REDD+ Activity Cover Page

Title of Activity:

Development of preferred options for benefit sharing

Related Activities UN-REDD Workplan:

2.3.d Development of preferred options - with relevance to NFP and Protected Area planning

Objectives of Activity:

To develop, building on the assessments of existing experiences (activity 2.3b) and the consultations on this assessment, preferred options for benefit sharing mechanisms with relevance to NFP and Protected area planning.

Brief Description:

- Development of preferred options for benefits sharing models for REDD+ in Cambodia. - Building on the work conducted under activity 2.3b including the recommendations for how to develop national benefit sharing mechanism, by analyzing the possible options further including in terms of the modalities needed in order to have a transparent and effective benefit distribution mechanism. - Consider how incentives can be linked to actions or results at the local level within a national accounting and the extent of monitoring necessary to implement the different options. - Consider whether different options have different implications for the participation in REDD+ by men and women. - Consider costs implications of different options. - Consider how the options will work for the different management regimes in Cambodia. - Consider the possible implications for projects and sub-national implementation within a national benefit sharing mechanism. - Present the options and the result of the above mentioned considerations and collect feedback from key ministries, REDD+ Taskforce, Consultation Group and other stakeholders as appropriate. - Based on the above present up to four preferred options for a national benefit sharing mechanism including the relevant considerations for decision makers. - Consider whether the preferred options for a national benefit sharing mechanism can work for sub-national implementation. - Support the development of a national workshop to present the results of the above tasks - In collaboration with the REDD+ Taskforce Secretariat, the consultant team should design and organize a workshop to be held in Phnom Penh in XX 2014. - Complete a synthesis report that consolidates 1 and 2 above - A report not exceeding 40 pages plus annexes and references shall be produced.

Key Outputs:

The three project expected outputs are: - A proposal of up to four preferred options for benefits sharing for REDD+ in Cambodia. - A national workshop on the preferred options suggested with minutes from the workshop. - A synthesis report not exceeding 40 pages plus annexes and references in English and Khmer that consolidates the outcome of 1 and 2 above.

|  | Signature | Name and Function | Date |
| --- | --- | --- | --- |
| Developed by: |  | Peter Iversen, Technical Specialist | 20-05-2013 |
| Implemented by: |  | REDD+ Taskforce Secretariat |  |
| Approved by: |  | UN-REDD Programme Director |  |

CONCEPT PAPER

Development of preferred options for benefit sharing

- Objective

To develop a set of 4 preferred options for a national REDD+ benefit sharing mechanism for Cambodia.

- Expectation

That up to four options for benefit sharing mechanisms for REDD+ in Cambodia will be developed based on previous work and after extensive consultation with governmental and non-governmental stakeholders.

- Activities

- Develop suggestions for preferred options for benefit sharing mechanisms for REDD+ in Cambodia building on the work conducted under activity 2.3b and the consultations undertaken under activity 2.3c. An extensive analysis should be presented for each of the preferred options and should include the result of the following considerations and activities:

- Support to the development of a national workshop on the preferred options for benefit sharing mechanisms for REDD+ in Cambodia

- A synthesis report that consolidates the outcome of 1 and 2 above.

- Outputs:

- A proposal of up to four preferred options for benefits sharing for REDD+ in Cambodia.

- A national workshop on the preferred options suggested with minutes from the workshop.

- A synthesis report not exceeding 40 pages plus annexes and references in English and Khmer that consolidates the outcome of 1 and 2 above.

- Roles and Responsibilities

- RTS Develop ToR for the consultant team and manage the recruitment of the consultants.

- RTS Provide oversight of the work by the consultants

- RTS Develop ToR for the national workshop

- Budget

| Activity | Budget |
| --- | --- |
| - Recruitment costs | 300 |
| - International consultant 30 days (lumpsum) | 25.500 |
| - National consultant 30 days | 1.500 |
| - Organizing a one day national workshop in Phnom Penh (100 participants) | 5.190 |
| - Awareness raising material Report English and Khmer version (200 each) | 2.850 |
| - Miscellaneous | 1.500 |
| Total | 37.040 |

- Time frame

The activities will follow activity 2.3b and 2.3c and are expected to be implemented first semester of 2014.

| Activity | Time period |
| --- | --- |
| - Development of ToR and announcement of consultancy | July 2013 |
| - Recruitment of the consultants (same as for 2.3b and c) | August 2013 |
| - Development of suggestions for preferred options for benefit sharing mechanisms for REDD+ in Cambodia | First semester 2014 |
| - National workshop on the preferred options for benefit sharing mechanisms for REDD+ in Cambodia | Same |
| - A report synthesizing output 1 and 2 above | Same |