Management Group (MG) of the UN-REDD Programme

Meeting Minutes of 31 May 2017 DRAFT

15h00 Geneva/Rome

Attendance:

MG members and alternates

FAO: Tiina Vahanen, Margo BuszkoBriggs

UNDP: Josep Gari, Tim Clairs

UNEP: Gabriel Labbate

Secretariat: Mario Boccucci

- 2018 – 2020 Workplan and Budget

Decisions and Actions:

  - Secretariat will copy edit the final document tomorrow, incorporating final comments made by UNDP

  - Mario will have a call with Norway at 9:30am and discuss any red flags before the document is submitted to the quality assurance committee

  - Secretariat will share the 2018 – 2020 workplan and budget with the Executive Board tomorrow, 1 June

- Interim Committee Decisions

As a continuation and closure of the Interim Committee’s work, committee members will be requested to make two decisions – on a no objection basis – by June 13. The first regards the 2016 SNA extension; the second is to release the final 25% of funds for the 2017 programme. The Secretariat has been in communication with committee members and Nik Sekhran as Chair and we do not anticipate any complications.

Decisions and Actions:

  - FAO to send final inputs for the SNA extension documents after this call

  - UNDP/FAO to finalise the Congo Basin inception note for the supporting document to accompany the decision on releasing 25% of funds

  - UNEP to finalise the Guyana inception note

  - The Secretariat will incorporate these inputs and submit both decisions – and supporting documentation – by 5pm today

- Executive Board Meeting

  - Agenda

  - Information and Decision Documents

The Secretariat has incorporated many of the comments from the MG, and welcomed additional feedback on the agenda and timeline for the Executive Board meeting. As a result, the agenda has been streamlined into five main sections: Introduction; Progress and Visioning; Workplan and Budget; Future Strategic Opportunities for UN-REDD; and Conclusions. Simultaneous English – Spanish interpretation will be provided on all three days, organised into three-hour slots.

Decisions and Actions:

  - Secretariat will remove the discussion on no-cost extensions in Nigeria and Côte d’Ivoire and postpone for inter-sessional approval

  - Agencies (FAO – Nigeria; UNDP –  Côte d’Ivoire) to discuss with country teams before Secretariat contacts both countries to confirm requests have been received and will be dealt with inter-sessionally

  - UNEP to confirm the title of session 4 on the briefing day and prepare notes

  - FAO to check panellists’ availability for launching the reference levels paper during the lunch on Friday, 16 June

  - FAO to send the Rules of Procedure by the end of tomorrow morning for MG review. All documents to be shared with the EB by tomorrow afternoon.

  - Secretariat to share all information documents with the EB by tomorrow, 1 June

  - UNDP to send the social inclusion document by Friday

  - UNEP to lead the session on survey results