Management Group (MG) of the UN-REDD Programme

Meeting Minutes of 14 Sept 2017 DRAFT

15h00 Geneva/Rome

Attendance:

MG members and alternates

FAO: Tiina Vahanen, Margo BuszkoBriggs

UNDP: Josep Gari

UNEP: Gabriel Labbate, Dianna Kopansky

Secretariat: Mario Boccucci

- 2017 Semi-Annual Report

Decisions and Actions:

- Agencies will provide any revisions and comments by Monday, 18 September.

- Secretariat will review the inputs received on finance and advise on next steps

- Consultations for 2018 workplan and budget

This is a follow-up action from the Executive Board and will be shared in the EB update.

Decisions and Actions:

- Agencies to provide 200 word summaries on consultations and evidence by early next week

- MG members to inform each Lead Advisor 1. Keep European Commission and Norwegian embassies (and other embassies of current or prospective donors) well informed of progress and consultations in a way that is tailored to the circumstances of the country; 2. Report back on the exchange that has taken place with the embassies. Progress with this communications will be reviewed at an MG call in a month

- Results Framework

The Secretariat has submitted the final version to Norway and is waiting on Norad’s feedback.

Decisions and Actions:

- Agencies to make any minor edits by next week

- Secretariat to follow-up with Norad and share any feedback with the MG

- Secretariat to share final results framework with the Executive Board with the update if needed a few days later than planned, to allow Norad Quality Assurance department to complete the review

- Next MG Calls

Decisions and Actions:

- A call will be convened next week only if necessary (preference Wednesday or Friday) to address comments from Norad; otherwise the call will take place the following week, Tuesday 26 September