Management Group (MG) of the UN-REDD Programme

Meeting Minutes of 26 Sept 2017 DRAFT

15h00 Geneva/Rome

Attendance:

MG members and alternates

FAO: Tiina Vahanen, Margo BuszkoBriggs

UNDP: Jyoti Mathur-Filipp

UNEP: Gabriel Labbate, Dianna Kopansky

Secretariat: Mario Boccucci

Additional attendees: Florian Eisele (first two agenda items).

- COP23 Update

Florian Eisele (Communications, UN Environment) provided a quick update of both planned events during COP23 in Bonn: the UN-REDD event (possible date Monday 13 November tbc) and the Cannondale/UN-REDD bike ride (12 November).

Decisions and Actions:

- UN Environment to work on message platform for COP23 to guide not only these two events but any event with UN-REDD representation and/or participation

- UN Environment to keep MG updated and circulate updated concept notes

- This will remain as a standing agenda item for MG calls leading up to COP23

- Regional Knowledge Management

Decisions and Actions:

- UN Environment will send an overall update to the MG on the status of knowledge management activities by the end of next week (Oct 6)

- MG to ensure proactive engagement of country teams in KM activities

- Going forward, if there is anything strategic coming out of the communications working group meetings that needs MG attention, UN Environment will share as necessary

- 2017 Portfolio Management

Decisions and Actions:

- MG to provide written reactions to the portfolio management document by 11 October

- Secretariat to review and finalise by 13 October

- MG to discuss any issues at next MG call 16 October

- 2017 Semi-Annual Progress Update

Decisions and Actions:

- MG to send final edits – if any -  to Secretariat by Wednesday 27/9 COB

- Secretariat to carry out final copy edit and share with Executive Board with the forthcoming update

- Update from Norway

Decisions and Actions:

- Secretariat to share any comments from Norway with the MG (Norway has promised feedback by 27 September)

- MG to share any comments on the meta results framework with Secretariat

- Consultations on 2018 Workplan and Budget

Decisions and Actions:

- UNEP to send the evidence on consultations by end of Wednesday (27 Sept)

- FAO to send summaries and evidence of consultations by today

- UN-REDD update for FCPF Assembly in Laos

Decisions and Actions:

- Secretariat to revise based on MG comments

- Any additional feedback to be shared with the Secretariat by today

- Secretariat to send to team in Laos

- Funds Transfer Request for Chile

Decisions and Actions:

- Secretariat will send an email asking the agencies to sign off on the annual work plan budget so that funding can be transferred in tranches by the MPTF