21 September 2012

NPWG call

Participants: Maria Sanz, Julie Greenwalt, Tim Clairs, Clea Paz

AGENDA

- NP reports-Still have not received final reports.  Action points:

  - Wednesday September 26 is the ultimate deadline to receive NP reports at the Secretariat, who will compile all information on Thursday and send the consolidated report for review on Friday.

  - UNDP will share informally the revised 2011 PNG annual report with the focal points to make sure queries (if any) are addressed before the PB meeting.

- NP session at the Policy Board meeting: Action points:

- Bolivia’s NP.

- Secretariat to prepare draft decisions on the possible options, to be discussed before the PB meeting with the Government and PB members that could participate in the contact group.

- Decisions should include positive references to Bolivia’s JMA mechanism

- Secretariat to include specific guidance on how to co-chair this session in the co-chair briefing

- Once nomination of participant is received, the Secretariat should write a message to Bolivia explaining the session at the PB and sending the final version of the mission report.

b. Country Panel:

- The group was not sure if is strategic to have in the panel only countries with implementation problems and recommended:

  - Clarify the purpose of the session and what decisions are expected from it in an expanded concept note for internal use

  - Consider having an open invitations to all countries that have past inception but are not finalizing NPs, to nominate panelists and if we have more than 5 or 6, use references to regional balance to reduce the panel

  - To include at least one country that is UN-REDD and FCPF

  - Select a very good moderator for the session that can distill lessons learned and trigger a good discussion

  - Secretariat to circulate the summary of the last country panel to NPWG members

- Country presentations (DRC/Indonesia/Viet Nam):

  - Consider how to recognize countries for the finalization of NPs and indications that they have “graduated” in terms of progress

  - In the NP status presentation make references to final evaluations and a final report or assessment note by the Programme that could be produced including feedback by the Policy Board

  - Draft possible decision text: recognizing progress, but that more needs to be done

d. Means of enhancing implementation of NPs: Not discussed as document was not sent

- Signature of approved NPs (Sri Lanka and RoC)

  - Secretariat will send inter-sessional decisions this week

- Zambia and DRC Targeted support requests (Helena to join)

  - Secretariat to prepare response to Zambia, based on the latest e mail exchange

  - FAO will discuss internally on DRC’s targeted support and confirm if the support requested can be provided as TS or through the National Programme