26 January

National Programmes Working Group call-Action points

- Internal review and management response

- Tim and Clea sent  yesterday comments to the reviewer (Clea’s is only about Ecuador’s quote)

- Clea and Tim will sent written inputs to Mette on the management response by Monday and additional discussions can take place on Thursday next week

- Clea to send Mette UNDG guidelines for joint programming as this are mentioned in the review

- NPWG work-plan

- Work-plan needs to be a practical document laying out the main issues that the group needs to address, with deadlines and responsibilities mapping out when they will be addressed

- Work-plan to lead into actions and decisions

- Priority issues to be extracted from the management response to begin with, and expanded if needed later

- Clea to develop a first draft by the next call

- National Programmes for next PB:

- Status review

  - It is confirm that only RoC and Sri Lanka are presenting NPs at the next PB meeting

  - RoC: Some components received by Mette, and work-plan and budget by Tim C. ; full document expected on February 6. J Mason and Adrien Sinafasi confirmed as reviewers

  - Sri Lanka: Tim C. received the document yesterday and forwarded it today to Mette and Clea. Is 200 pages. Only one reviewer is confirmed: M. Herold, will look into other reviewers and have J. Blaster if others cannot be found.

- Pending issues

  - Discuss fund management arrangements of both NPs taking in account the recommendations from the review. Cannot have common expenses divided in three.

  - Clea to follow up with Mr. Mason and if he cannot review the document in French, will ask Steve Cobb

  - Clea to send a message asking the number of pages for each document and deadlines for reception to plan independent reviews and translations

- Visit to Rome on February 2

  - Confirm dates, preliminary agenda, participants

  - Mette confirmed that most of focal points will be in Rome (Danilo, Joel, Inge, Danae), so Tim C, Kimberly and Clea can go ahead and book tickets

  - Clea will send Mette information on arrival time and departure and list of issues and times needed, so FAO can prepare the agenda

- Defining alternative times for the call for  UNEP’s participation (Gabriel is replacing Ravi on the working group)

  - It would be very difficult to move the calls to the afternoon considering Mette’s and Tim’s schedules and the CG calls in the afternoons

  - Clea to consult with UNEP in Nairobi (February 13-15) on UNEP’s participation on the NPWG calls

- Other items

  - Signatures for NPs: It is confirmed that budget holders are signing the reports after following the internal clearance process. Clea to make sure this information is reflected on the handbook.

  - Targeted support:

    - There are a number of countries that have requested or are receiving targeted support: Ethiopia, Côte d’Ivoire, Paraguay, Costa Rica, Malasya?

    - Clea to prepare a matrix with all partner countries, to start identifying status of targeted support and fill out the matrix that Thais sent yesterday

    - Need a specific call on targeted support with Thais.