5 March

National Programmes Working Group call-Action points

AGENDA

- National Programmes for next PB:

- On Sri Lanka’s SF: Clea to correct the box marked “unclear” in the Secretariat review section and add the FAO country rep address plus the UNDP address of the UNDP representative in addition to the one UN address.

- Regarding the implementation modality, FAO to follow up internally to ensure the LoA is finalized quickly and PMU resources can be disbursed for the inception phase

- Clea to follow up with the administrative agent section for this and past submission forms

- National Programme Handbook

- Clea to circulate final draft before the PB meeting

- Joint meeting- Sharon to join

- Danilo and Kimberly to coordinate UN-REDD participation on the community-based MRV session

- Include countries with positive and success stories in the country panel

- Inception workshops in Latin America-Gabriel to inform

- Important to adhere to our principles and guidelines when planning and designing inception workshops

- If conditions are not set for a participatory inception workshop according to our guidelines, the mission to Bolivia should be renamed as “pre-inception” mission

- Important to clarify to the Government that as per their letter, the UN-REDD resources shall be used under the framework of the approved document

- Ecuador mission was delayed to April but there are no concerns about this

- National Programme Document to go along with the RPP

- Clea to circulate via mail for discussion at the next meeting

- AOB

- Gabriel to follow up with UNEP con clarifying if the support to Sudan’s efforts will be submitted as tier 2