## REDD Logframe (hidden)
REDD Planning | [6 empty] | o
Result | Implementing Partner | Related activities | Indicator | Baseline | Proposed target | Means of verification | Risks and assumptions | Status | Problems/Causes | Solutions | Targets for the 2010 | Activities and Actions | Inputs | Indicative Budget
Goal:
By the end of 2012 Viet Nam is REDD-ready and able to contribute to reducing emissions from deforestation and forest degradation nationally and regionally
Objective: To assist the Government of Viet Nam in developing an effective REDD regime in Viet Nam and to contribute to reduction of regional displacement of emissions | · Government | · Programmes of multiple donors | · Recognition of REDD-VN as a state-of-the-art national system | · No system in place | · By the time of COP-15, Viet Nam is able to demonstrate components of an effective and equitable national REDD regime | Government policy briefs for COP-15; observations by other Parties to the UNFCCC | Donor support is coordinated | The draft BDS document is complete, and executive summary will be presented at COP15 | Some misunderstanding among key officials; it seems
· Bilateral donors
· Other multilateral agencies
· NGOs
| · Civil Society |  | · Preliminary programme to reduce emissions from deforestation and forest degradation |  | · By the end of 2010, Viet Nam has in place a preliminary programme to generate independently measurable and verifiable REDD C-credits | REDD-VN reporting system | Government commitment is firm
REDD is endorsed as a component of a post-Kyoto instrument
WB FCPF provides funds to address complementary issues
· No programme
Outcome 1: Improved institutional and technical capacity for national coordination to manage REDD activities in Viet Nam | · MARD | · Programmes of multiple donors | · Components of REDD architecture in place | · Support to SFM has established partial elements, but none are REDD-ready | · By the end of 2010 key components of REDD architecture (coordinating mechanism, reference scenario, payment distribution system) are completed | Reports; interviews with key government and development partner officials | Government and partner agencies cooperate effectively
· FCPF
· Other government agencies
Funds are mobilized in a timely fashion
Outputs: | [13 empty] | 810000
1.1. National coordination mechanism | · DoF/MARD |  | · Establishment of system | · Proposal for “interim working group” exists | · By the end of April 2009 the interim working group is operational | Reports; interviews with key government and development partner officials | Commitment from all partners | Some members are there. Some meeting are organized. However the meaningfull of participation and coordination is not there yet. Lack of understanding of the among stakeholders above REDD | Information on REDD is limited, the concept is complex | Series of events to raise awareness of the | By end of June: - All network members desmontrated good knowledge on REDD and actively participated in network events and REDD activities - All departmental level officials in key state agencies related to REDD programme exposed to REDD information and demonstrated basic knowledge about REDD: | By June 2010: - 01 workshop on REDD for DOF and MARD departments - 01 workshop on REDD financing mechanism and policy implication for ministries including MARD (as a follow up) - 01 NGOs event on REDD (can be combined in the above if the number is not many) |  | 21000
[8 empty] | Member of the network is not active |  |  |  | Hold quarterly network meeting: can be combined in the first half of the year | REDD network assitant (1 year full time) | 12000
[12 empty] | Organize at least 2 study tours for the network members to REDD site in Lam Dong and other initiatives (elsewhere) | Travel and lodging cost | 30000
| · FSSP |  |  |  | · By the end of 2010 all partners have endorsed a roadmap generated by the working group |  | Institutional relationships with other initiatives, especially the FSSP are resolved | Produced a year ago, description of need to be done, who is responsible. Over logframe on the readyness. WB consultant looked on the timing issue. No update. | just need the update | Create the REDD website as an information chanell to reach broader range of audience, including international ones. | By end Q1/2010, Vietnam REDD website launched: |  | - National Subcontract for REDD website - Short-term editor | 10000
| · MONRE | [9 empty] | By the end 2010, Vietnam REDD roadmap approved by MARD: - 1st Draft Roadmap in Q1 - Roadmap endorsed by REDD Network by Q2 - MARD approved Roadmap by end 2010 |  | - International consultant (2 p.m*12,000 work in 6 months) - Hold network consultative meeting (or include in regular meeting if time allows) , 5,000 | 30000
1.2. National reference scenario for REDD | · DoF | · FCPF | · Data/analysis on deforestation and degradation using FRA RSS and other robust methodology | · Some data/ analysis exist | · By the end of 2009, preliminary analyses of available data completed | Reports | Viet Nam prioritises and resources the process adequately
| · FIPI | · FAO NFMA project | · Historical data on forest resources (volumes, carbon stock, forest classes etc.) for historical emission levels | · Not covering the whole country, existing NFI data not calculated | · By the end of June 2010, NFI data analyzed | Maps | Participating agencies in Viet Nam committed to developing the RS | BG: waiting for COP15 results. Get a consultant to review the methodology, start on what JICA is doing; Cuong has contacted with those organization; link to Network
| · FSIV | · FOMIS | · Trained staff for REDD REL development | · Some staff trained, but not specifically on REDD | · By the end of August 2010, a REDD REL/reference scenario team is fully trained | Surveys | Methodological support from Partners is available
|  | · ADB/FLITCH | · Stakeholder-endorsed interim reference scenario of forest C-stocks | · No scenario exists | · By the end of 2010 a multi-stakeholder endorsed interim REL/reference scenario has been developed | Staff records | Methodology for monitoring degradation adequate
|  | · Japan-funded project to screen REDD potential land in Viet Nam |  |  |  | Financial reports
Joint agreements and reports
1.3. Framework National REDD Program (Strategy) | · DoF | · FCPF | · Baseline analysis on governance and policy for REDD | · No integrated analysis | · By the end of September 2009, an analysis of governance and policy for REDD is completed | Reports | Coordination mechanism works effectively |  |  |  | By the end of 1st Quarter, first draft of REDD programme for Vietnam completed | Ressembe a team of international and national consultants ( 01 team leader and at least 03 member: policy analyst, institutional specialist | TORs from ??? | 200000
| · MONRE and other government agencies | · FSSP |  |  | · By the end of June 2009 a structure for the national REDD programme is endorsed by the coordinating mechanism | [5 empty] | End Q2: APP documents completed/endorsed by Network | Series of meeting to discuss the progress and consult with key agencies |  | 40000
| · NGOs |  | · Structure of national REDD programme |  | · By the end of 2010 information gaps have been identified and a workplan to fill them prepared | [5 empty] | By the end 2010: the 2 draft of REDD programme document endorsed by PM/Minister
|  |  | · Information gap analysis | · No structure exists
· Gaps only known in general terms
1.4. Performance-based, transparent benefit sharing payment system from national to local levels | · DoF/MARD | · KfW/MPI | · Stakeholder satisfaction with payment system, monetary or in-kind benefits in target communities of a magnitude that could influence on decision-making | · No REDD system, but Programme 661 system provides model | · By the end of 2010, a payment system has been developed that meets the expectations of all stakeholders and beneficiaries | Survey | Stakeholder views are not too divergent | The draft BDS document is complete, and executive summary will be presented at COP15 |  |  | End Q2; The policy options fully endorsed MARD, other ministries | Translate the documents into Vnese | Translation of documents | 2000
| · MoF | [9 empty] | End Q1: Decision for pilots | Series of meeting with key persons within selected ministries |  | 10000
| · NGOs | [9 empty] | End of Q1: Start Implement Policy recommendations (05-06) | Assemble a team of consultants (national, international) |  | 200000
[7 empty] | A mechanism can be designed that is relatively immune to corruption |  |  |  | By the end of 2010: at least 05 policy recommendations are considered by relevant by state agencies |  | sundry | 10000
1.5. Communications materials for sharing lessons internationally | · DoF | · | · Production of communications materials | · No materials | · By the end of 2009, at least 2 knowledge products have been disseminated internationally (specifically during COP-15) | Reports | Programme is able to generate internationally-relevant lessons over a short time-frame
· UNEP
· NGOs
Outcome 2: Improved Capacity to manage REDD and provide other Payment for Ecological Services at district-level through sustainable development planning and implementation | · DoF | · UNDP/MPI Mainstreaming SD and Climate into provincial planning project | · Operational district pilots in at least 2 districts | · No pilots underway | · By the end of 2010 pilots in at least 2 districts in Lam Dong have demonstrated a viable approach to planning for REDD, participatory monitoring, and a system for distribution of benefits | Reports, field survey with interviews of local stakeholders | District authorities embrace demonstration of REDD
· Provincial and district authorities
· NGOs
Funds flow in a timely fashion
Outputs:
2.1. District-level forest land-use plan mainstreaming REDD potential | · Provincial and District authorities | · Japan-funded project to screen at risk forest areas | · District socio-economic development plan with REDD priorities identified | · Local plans do not include REDD | · By the end of 2010 a multi-stakeholder endorsed socio-economic development plan has been developed that incorporates status and trends of forest cover and identifies economically-viable at risk areas | Reports/maps | Local authorities have the basic capacity for socio-economic planning | do not know the planning process at district levels |  | - Consult with RCB on the process, endorsed | · By the end of 2010 a multi-stakeholder endorsed socio-economic development plan has been developed that incorporates status and trends of forest cover and identifies economically-viable at risk areas
[11 empty] | End Q1: free prior informed consent - information on forest and carbon - economic analysis: | Draft the methodology for obtaining RPIC | Tim draft the method; translate to useable language, get independent to consult with; Awareness raising can be done before the free prior informed consent (FPIC)
[11 empty] | End of Q1: - Awareness workshop on Land Use planning with REDD for Lam Dong - Documenting the planning at district and communes, kind of information . Q1 - Document REDD specific information need for land use planning Q1 |  | - Consultant on local planning (02 m.m*2000) - Consultants for RPIC (4-10 people: 1 m.m* 2,000 - Consultant on intergraing REDD in development plan | 150000
[11 empty] | End of Q3 (or Q2): Demonstrated REDD integrated District development plans.by the end of the . |  | Travel and lodging | 25000
2.2. Participatory C-stock monitoring system | · Provincial and District governments in Lam Dong | · CIFOR (methodology developed) | · Engaged stakeholders at the district and local levels (including ethnic minorities and forest dependent communities) involved in participatory monitoring | · Local institutions have little capacity for forest monitoring | · By the end of September 2010 local institutions are able to conduct participatory monitoring | Reports, maps, data files | Capital investments and training are delivered in a timely fashion
| · FAO | · Winrock team | · Sample plot system for ground-truthing | · No sample plots exist | · By the end of June 2009, a sample plot system has been established
· NGOs
|  |  | · Preliminary C-stock estimates | · Existing processes are non-participatory | · By the end of 2010 responsible organizations have produced C-stock survey data
Institutional coordination is effective
2.3. Equitable and transparent benefit sharing payment systems | · District and provincial authorities | · RECOFTC | · Stakeholder satisfaction with payment system, monetary or in-kind benefits in target communities of a magnitude that could influence on decision-making | · No REDD payment system, but forest protection system provides a model | · By the end of 2010, a payment system has been developed that meets the expectations of all stakeholders and beneficiaries | Survey; interviews with beneficiaries | Stakeholder views are not too divergent
| · NGOs | · SNV
· WWF
· CIFOR
A mechanism can be designed that is relatively immune to corruption
2.4. Awareness raising at district and local levels | · District and provincial authorities | · Winrock | · Level of awareness among local stakeholders (including ethnic minorities and forest dependent communities) | · Stakeholders unaware of REDD | · By the end of 2010, stakeholders in pilot districts are aware of REDD and potential benefits | Stakeholder consultation minutes | Existing proposal for awareness raising on PES provide an effective vehicle for awareness raising on REDD
| · NGOs | · RECOFTC
Outcome 3: Improved knowledge of approaches to reduce regional displacement of emissions | · Regional governments | · WB | · Roadmap for reducing regional displacement of emissions | · Regional “R-PIN” drafted but not funded; no roadmap exists | · By the end of 2010, a roadmap to address regional displacement of emissions has been endorsed by the GoV and at least one other regional government | Documentation, reports | Cooperation with regional governments is feasible
· ADB
|  | · EU |  |  |  |  | Funds flow in a timely fashion
· RECOFTC
Outputs:
3.1. Quantification of regional “displacement of emissions” risk | · MARD (DoF, ICD and FPD to secure involvement of other governments) | · ADB | · Completion of analysis | · Magnitude of problem understood only in qualitative terms | · By the end of 20109 an analysis providing quantitative estimates of regional displacement of emissions risk has been produced | Report | Data on illegal and quasi-legal movement of timber and wood products can be collected or inferred
3.2. Regional dialogue on “displacement of emissions” risk | · MARD (DoF, ICD and FPD to secure involvement of other governments) | · RECOFTC | · Emerging agreements on approaches to reduce regional displacement of emissions | · Essentially no debate has taken place | · By the end of 2010 elements of a workplan to address drivers of regional displacement of emissions cooperatively are documented | Minutes of meetings, workshops, etc. | Influence of powerful entities engaged in movement of timber and wood products does not negate progress | Organize regional ws on issue, and bilateral meeting with Cambodia | X
[8 empty] | BG:DOF met Cambodia |  |  | End Q1: study tours of Cambodia to Vietnam |  |  | 70000
End Q2: Study tours of official to Cambodia
Mid Q4: Regional in Vietnam
[8 empty] | Shall enge more Laos and Thailand; not sure with T |  |  | End Q2: Study tours of official to Cambodia
3.3 Analysis of opportunities for linkage with non-REDD initiatives to reduce cross-border flow of illegal timber | · DoF, ICD and FPD | · CIFOR | · Completion of analysis | · No analysis exists | · By the end of 2010 the potential for collaboration between REDD and FLEG(T) in reducing regional displacement of emissions has been identified | Report | Differences in focus of REDD and FLEG(T) are not sufficient to negate potential for colalboration
· EU FLEGT
· WB FLEG

## Q4 2011-option A (hidden)
QUARTERLY WORK PLAN
(From 1/10/2011 - 31/12/2011) | [24 empty] | version 4.1
Programme Title: UN-REDD Viet Nam Programme
Implementing Partner: Viet Nam Administration of Forestry, Ministry of Agriculture and Rural Development | [30 empty] | July 2009 | Check | #REF!
Budget
Expected Output and Monitoring Activities | Annual Output Targets | Key Activities | Inputs | Timeframe |  |  | Responsible Party | Budget category |  |  | Total budget | By PMU | by UN Agency | Exp PMU Q1/2011 | Exp UNDP Q1/2011 | Exp UNDP Q1-2/2011 | Exp PMU Q2/11 | Total exp | Balance | Known commitments | Net budget endorsed for remaining year | Proposed adjustment |  | Total budget | By PMU | By UN Agency | Atlas code |  | Revised after 2nd PEB meeting [put figures for whole year 2010) (original chi Huyen)
|  |  |  | Oct | Nov | Dec
Atlas code
Outcome 1: Improved institutional and technical capacity for national coordination to manage REDD+ activities in Viet Nam
1.1. National coordination mechanism established (UNDP) |  | 1.1.3. Support quarterly REDD network meeting |  | x |  |  | PMU | Contracts, Commodities, transport and supplies | Workshops, meeting expenses | 75700 | 5000 | 5000 |  | 38 |  |  | 1297 | 1335 | 3665 |  | 3665 | 0 |  |  |  |  | 75700
|  | 1.1.4. Visit to REDD+ pilot sites (Lai Chau, Binh Thuan and Lao Cai, proposed pilot site of UN-REDD phase 2) | Travel and lodging cost | x | x | x | PMU/VNFOREST | Commodities, transport and supplies | Local travel, workshops | 71600 | 10000 | 10000 |  |  |  |  | 432 | 432 | 9568 |  | 9568 | 0 |  |  |  |  | 71600 |  | 3000
|  | 1.1.6. Awareness-raising on REDD+ for provincial staff in the central (awareness-raising workshops in Da Nang) |  | x |  |  | PMU/VNFOREST | Personnel, Contracts, Commodities, transport and supplies | Training courses (meeting rooms, DSA, participants travel) | 75700 | 40000 | 40000 |  | 10523 |  |  | 18024 | 28547 | 11453 |  | 18000 | 6547 |  |  |  |  | 75700 | outstanding from Q3 | 55000
|  | 1.1.7.Stakeholder consultations on the UN-REDD Phase II proposal (1 day, in Ha Noi, participants: from 6 pilot provinces) |  | x |  |  | PMU | Personnel, Contracts, Commodities, transport and supplies | Local travel, workshops, peer review | 75700 | 26000 | 26000 |  | 9139 |  |  | 1370 | 10509 | 15491 |  | 15491 | 0 |  |  |  |  | 75700 | tentatively, 1st week of Oct
1.2. Data and information for national REL/RL for REDD+ available (FAO) |  | 1.2.2. Support Vietnamese Technical Experts to attend international Trainings (and other international travel for UN-REDD) - Travel for PB7 in Berlin -Travel to Panama -Travel to COP 17 |  | x |  |  | FAO/VNFOREST | Personnel | travel |  | 25000 |  | 25000 |  |  |  |  | 0 | [5 empty] | 25000 |  |  |  | (Funds already overspent from AWP - reallocate from 1.6.10) | 25000
[8 empty] | Contract |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | ODC |  |  | 1500 |  | 1500 |  |  |  |  | 0 | [5 empty] | 1500
|  | 1.2.5. Part-time technical officer |  | x | x | x | PMU | [20 empty] | Funds outstanding from Q3
1.3. Framework National REDD+ Program (strategy) | • By March 2011 a structure for the National REDD+ Program is endorsed by MARD • By the end of June 2011 a draft document ready for presentation to the Government | 1.3.1. Drafting of the National REDD+ Program document |  | x | x |  | PMU/VNFOREST | Personnel | International consultant | 71200 | 60917 |  | 60917 |  | 3912 | 36472 |  | 40384 | 20533 |  | 0 | -20533 |  |  |  |  | 71200 | on-going contract | 92000
|  | 1.3.2. Organization of consultation workshops on NRP |  | x |  |  | PMU/VNFOREST | Contracts, Commodities, transport and supplies | Workshops, local travel | 75700 | 20000 | 20000 | [5 empty] | 0 | 20000 |  | 20000 | 0 |  |  |  |  | 75700 | tentatively, last 2 weeks of Oct
1.4. Performance-based, transparent benefit sharing payment system from national to local levels (UNDP) | • By June 2011 an assessment has been made on making the National REDD+ Fund a sub-fund of the FPDF nationally and provincially • By the end of 2011, the payment system is designed to be based upon assessment of performance and the local R-factor • By the end of 2011, a payment system has been developed that meets the expectations of all stakeholders and beneficiaries | 1.4.2. Organization of Local Consultations in Support of the Development of a REDD+ Compliant Benefit Distribution System for Viet Nam |  | x | x | x | PMU/VNFOREST | Contract | Contract with organization | 75700 | 10000 | 10000 |  |  |  |  | 956 | 956 | 9044 |  | 9044 | 0 |  |  |  |  | 72100 |  | 0
|  | 1.4.3. Review of FPDF suitability for National REDD+ Fund and design of (interim) National REDD+ Fund management (with operational rules/regulations) |  | x | x |  | PMU/UNDP | Personnel | NC 30d + travel | 71300 | 17300 | 17300 |  |  |  |  | 943 | 943 | 16357 |  | 6000 | -10357 |  |  |  |  | 71300 | on-going contract
|  | 1.4.4. Development of framework for assessment of performance and R-coefficients of the National REDD+ Fund |  | x | x |  | PMU/UNDP | Contract | Contract with organization | 72100 | 30000 |  | 30000 |  |  |  |  | 0 | 30000 |  | 36000 | 6000 |  |  |  |  | 72100 | on-going contract
1.5. Communications materials produced for sharing lessons nationally and internationally (UNEP) | • By the end of 2011, lessons learnt in programme implementation identified, documented and shared | 1.5.1 Identification and analysis of lessons likely to be of relevance nationally and internationally |  | x | x | x | UNEP/PMU | Personnel |  |  | 17500 | 10000 | 7500 |  |  |  |  | 0
|  | 1.5.2 Packaging lessons learned into information materials & activities (based on advice and support provided through the global component of UN-REDD) |  | x | x | x | UNEP/PMU | Supplies... |  |  | 18500 | 11000 | 7500 |  |  |  |  | 0
1.6 National MRV System designed (FAO) | • By the end of 2011, comprehensive framework document of the national MRV system prepared, demonstrated and presented to stakeholders • Training of Vietnamese technical staff on the MRV system (by end of 2011) • By the end of 2011 allometric equations are available for the ten most forested ecological strata | 1.6.1. Prepare framework document of the national MRV system for international reporting and national implementation of REDD+ |  | x | x | x | FAO/VNFOREST | Personnel | 1 IC (a) |  | 16000 |  | 16000 |  |  |  |  | 0 |  |  |  |  | NC(c)3M | 7500
[8 empty] | Contract |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | ODC |  |  | 960 |  | 960 |  |  |  |  | 0 | [5 empty] | 450
|  | 1.6.5. Support for the sub-Technical Working Groups |  | x | x | x | FAO/VNFOREST | Personnel |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | Contract | LoA-PMU |  | 14000 | 14000 | 0 |  |  |  |  | 0 |  |  |  |  | HACT | 3000 | 3000
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | ODC |  |  | 840 |  | 840 |  |  |  |  | 0 | [5 empty] | 180
|  | 1.6.6. Development of allometric equations |  | x | x | x | FAO/VNFOREST | Personnel | 1 IC (a) |  | 16000 |  | 16000 |  |  |  |  | 0
[8 empty] | Contract | LoA-FSIV |  | 110000 |  | 110000 |  |  |  |  | 0 | [9 empty] | Already committed. Funds outstanding from Q2
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | ODC |  |  | 7560 |  | 7560 |  |  |  |  | 0
|  | 1.6.7. Design and develop a data management system for PCM |  |  |  |  | FAO/VNFOREST | Personnel | 1 IC (a) |  | 16000 |  | 16000 |  |  |  |  | 0
[8 empty] | Contract | LoA- |  | 20000 |  | 20000 |  |  |  |  | 0
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0 | 0
[8 empty] | ODC |  |  | 2160 |  | 2160 |  |  |  |  | 0
|  | 1.6.9: Strengthening capacity of MRV-related institutions and assisting in the establishment of the VN REDD+ Office |  | x | x | x | FAO/PMU | Commodities | FAO | 30000 |  | 30000 | [11 empty] | 10000 |  |  |  | No specs yet. To be discussed.
Personnel
[8 empty] | ODC |  | 1800 |  | 1800
|  | 1.6.11 Development of the Land Monitoring System |  | x | x |  | FAO/VNFOREST | Personnel | travel |  | 80000 |  | 80000 |  |  |  |  | 0 |  |  |  |  | NC 4MM | 4000
[8 empty] | Contract |  |  |  |  | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 40000
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0 | 0
[8 empty] | ODC |  |  | 4800 |  | 4800 |  |  |  |  | 0 | [5 empty] | 2640
|  | 1.6.12 Assistance of Land Law revision to GLDA, MONRe, for land classification systems consistent between MONRE and MARD. |  | x | x | x |  | Personnel | 1 IC (a) |  | 16000 |  | 16000 |  |  |  |  | 0
[8 empty] | Contract |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 15000 |  |  |  | Proposal pending
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | ODC |  |  | 960 |  | 960 |  |  |  |  | 0 | [5 empty] | 900
Outcome 2: Improved Capacity to manage REDD+ and provide other Payment for Ecological Services at district-level through sustainable development planning and implementation | [17 empty] | 0 | 0
2.1. District-level forest land-use plan mainstreaming REDD potential (UNDP) | • By the end of 2011, methodology developed for incorporation into SEDP of status and trends of forest cover and identification of REDD+-eligible areas • By February 2011 a methodology for assessment of opportunity costs for REDD+ has been developed • By the end of 2011, methodology for REDD+ integration into FPDF is based on the provincial MRV system | 2.1.1. Consultation and training for Integration of REDD+ in forest development masterplan and land-use masterplan for period from 2010-2020 |  | x |  |  | PMU /DARD | Personnel, Contracts, Commodities, transport and supplies | Training workshops, local consultants | 72100 | 20000 | 20000 |  |  |  |  | 4650 | 4650 | 15350 |  | 15350 | 0 |  |  |  |  | 75700 | on-going, tentatively, 25 Oct | 10000
|  | 2.1.3. Support for the Provincial Working Group on REDD+ |  | x | x | x | PMU / DARD | Commodities, transport and supplies | workshops, operational expenses, travel | 71600 | 12000 | 12000 |  | 1488 |  |  | 1800 | 3288 | 8712 |  | 8712 | 0 |  |  |  |  | 71600
|  | 2.1.4. Provincial forest protection and development planning 2011-2020 for Lam Dong |  | x | x | x | DARD/Subcontractor | Contract | Contract with organization | 72100 | 55000 | 55000 | [5 empty] | 0 | 55000 | 55000 | 55000 | 0 |  |  |  |  | 72100 | on-going
|  | 2.1.6. Stakeholder consultation (forest managers and owners (continuation of FPIC) |  | x | x | x | PMU/DARD/ consultant | Personnel | Local consultants, workshops, travel | 71300 | 10000 | 10000 |  | 3440 |  |  | 8199 | 11639 | -1639 |  | 6770 | 8409 |  |  |  |  | 75700 | on-going
[8 empty] | Supplies... | Training, workshops | 75700 | 10000 | 10000 | [5 empty] | 0 | 10000 |  | 8230 | -1770 |  |  |  |  | 75700
2.3. Equitable and transparent benefit sharing payment systems defined (UNDP) |  | 2.3.2. Piloting Local Decision Making in the Development of a REDD+ Compliant Benefit Distribution System for Viet Nam |  | x | x | x | Contract | Contract | Contract with organization | 72100 | 15000 | 15000 | [5 empty] | 0 | 15000 |  | 36000 | 21000 |  |  |  |  | 72100 | on-going contract
2.4. Awareness on REDD+ created at national and local levels (UNEP) |  | 2.4.2. Preparation of awareness-raising materials Booklet on REDD+ for local govt official (2.4.2) Booklet on REDD+ for central govt official (2.4.2) Manual and flip chart training for local facilitators (2.4.3) Poster/leafleft for FPIC 2 (2.4.3) |  | x | x | x | PMU | Consultant, supplies, commodoties, equipment and travel |  |  | 37000 | 37000 | [5 empty] | 0 | [9 empty] | on-going
|  | 2.4.3 Organization of awareness raising events Photo contest News/articles on REDD/VNFOREST websites and technical magazine |  | x | x | x | PMU | Consultant, supplies, commodoties, equipment and travel |  |  | 59000 | 59000 | [5 empty] | 0 | [9 empty] | on-going |  | ?
Outcome 3: Improved knowledge of approaches to reduce regional displacement of emissions
3.1. Drivers of regional emissions displacement and inter-sectoral leakage assessed (FAO) | • By April 2011 a framework for the assessment of drivers of potential regional emissions displacement developed • By the end of 2011, a study on intra-national displacement of emissions will be completed • National REDD+ Program and FLEGT process align efforts on areas of common interest | 3.1.3. Policy dialogue between managers and businesses in province having border gate where timber imported into Vietnam |  |  | x |  | FAO / PMU | Personnel | 1 IC (b) |  | 10000 |  | 10000 |  |  |  |  | 0
[8 empty] | Contract |  |  |  |  | 0 |  |  |  |  | 0 | [9 empty] | Funds outstanding from Q2 ($20,000) and Q1 ($15,000)
[8 empty] | Contract | [14 empty] | HACT | 3000 | 3000
[8 empty] | Supplies... |  |  |  |  | 0 |  |  |  |  | 0
[8 empty] | ODC |  |  | 600 |  | 600 |  |  |  |  | 0 | [5 empty] | 180
3.2. Regional synergies and collaboration on REDD+ enhanced (UNDP) | • By the end of 2011 elements of a work plan to address drivers of regional displacement of emissions cooperatively are documented | 3.2.1. VNFOREST visit to Myanmar to discuss cooperation in REDD+ implementation |  |  | x |  | PMU/MARD ICD | Commodities, transport and supplies | Workshops, travel | 71600 | 7000 | 7000 | [5 empty] | 0 | 7000 |  | 20000 | 13000 |  |  |  |  | 75700 | Cuong to contact Myanmar colleagues
Programme management | [28 empty] | 270000
|  | Programme steering committee meeting |  | x |  | x | PMU | Commodities, transport and supplies | Local travel, workshops | 75700 | 25000 | 25000 |  | 13694 |  |  | 1095 | 14789 | 10211 |  | 3211 | -7000 |  |  |  |  | 75700
|  | Planning and Reporting |  | x |  | x | PMU | Contract |  |  | 0 | [5 empty] | 441 | 441 | -441 | [7 empty] | 74200
|  | Meeting |  |  |  |  | PMU | Supplies... | Meeting expenses | 75700 | 1000 | 1000 |  | 47 |  |  | 63 | 110 | 890 | [7 empty] | 75700
|  | Personnel Cost | [5 empty] | Personnel | [9 empty] | 0 | 0
|  | Technical Specialist |  |  |  |  | UNDP | Personnel | Project international staff | 71400 | 152651 |  | 152651 |  | 37857 | 35971 |  | 73828 | 78823 |  | 78823 | 0 |  |  |  |  | 61300
|  | Programme Manager and National REDD Team Leader, 2 technical officers |  |  |  |  | PMU | Personnel | Project local staff | 71400 | 82314 | 82314 |  | 11846 |  |  | 11446 | 23292 | 59022 |  | 32892 | -26130 |  |  |  |  | 71400
|  | Project accountant, Project Interpreter/secretary, communication officer |  |  |  |  | PMU | Personnel | Project local staff | 71400 | 37644 | 37644 |  | 6285 |  |  | 8950 | 15235 | 22409 |  | 17600 | -4809 |  |  |  |  | 71400
|  | Prog. Assistant, financial assistant, procurement assistant |  |  |  |  | PMU | Personnel | Project local staff | 71400 | 26568 | 26568 |  | 5282 |  |  | 6686 | 11968 | 14600 |  | 13300 | -1300 |  |  |  |  | 71400
|  | Lam Dong staff (3 p) |  |  |  |  | PMU | Personnel | Project local staff | 71400 | 13644 | 13644 |  | 3472 |  |  | 3691 | 7163 | 6481 |  | 7781 | 1300 |  |  |  |  | 71400
Internal Financial Controller
|  | Local travel |  |  |  |  | PMU | Transport | Local travel | 71600 | 25000 | 25000 |  | 5058 | 1028.8 | 698.43 | 6030 | 12815.23 | 12184.77 |  | 12184.77 | 0 |  |  |  |  | 71600
|  | Equipment, supplies… |  |  |  |  | PMU | Commodities and supplies | Operational expenses (communication, stationery) | 72400 | 15000 | 15000 |  | 4519 | 7.41 |  | 7916 | 12442.41 | 2557.59 |  | 8557.59 | 6000 |  |  |  |  | 72400
[11 empty] | 1201418 | 646270 | 586948 | 74831 | 42805.21 | 73141.43 | 83989 | 274766.64 | 452271.36 | 55000 | 442179.36 | -9643 |  | 113350 | 6000 | 0 |  |  | 455000
|  | Summary of Budget Q4 2011 | [5 empty] | Agencies |  |  | Total | by PMU | by Agencies | [5 empty] | Balance | [9 empty] | by PMU | by Agencies
[8 empty] | UNDP | 1.1 |  | 81000 | 81000 | 0 | 19700 | 0 | 0 | 21123 | 40823 | 40177 | 0 | 46724 | 6547 |  | 0 | 0 | 0
[9 empty] | 1.3 |  | 80917 | 20000 | 60917 | 0 | 3912 | 36472 | 0 | 40384 | 40533 | 0 | 20000 | -20533 |  | 0 | 0 | 0
[9 empty] | 1.4 |  | 57300 | 27300 | 30000 | 0 | 0 | 0 | 1899 | 1899 | 55401 | 0 | 51044 | -4357 |  | 0 | 0 | 0
[9 empty] | 2.1 |  | 107000 | 107000 | 0 | 4928 | 0 | 0 | 14649 | 19577 | 87423 | 55000 | 94062 | 6639 |  | 0 | 0 | 0
[9 empty] | 2.3 |  | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 36000 | 21000 |  | 0 | 0 | 0
[9 empty] | 3.2 |  | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 20000 | 13000 |  | 0 | 0 | 0
[9 empty] | Mgmt |  | 378821 | 226170 | 152651 | 50203 | 38893.21 | 36669.43 | 46318 | 172083.64 | 206737.36 | 0 | 174349.36 | -31939 |  | 0 | 0 | 0 |  |  | 0
[11 empty] | 727038 | 483470 | 243568 | 74831 | 42805.21 | 73141.43 | 83989 | 274766.64 | 452271.36 | 55000 | 442179.36 | -9643 |  | 0 | 0 | 0
[8 empty] | FAO | 1.1 |  | 90917 | 30000 | 60917 | 0 | 3912 | 36472 | 956 | 41340 | 49577 | 0 | 29044 | -20533 | OP 1.2 | 26500 | 0 | 0
[9 empty] | 1.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OP 1.6 | 83670 | 3000 | 0
[9 empty] | 1.4 |  | 960 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OP 2.2
[9 empty] | 2.1 |  | 111000 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 36000 | 21000 | OP 3.1 | 3180 | 3000 | 0
[9 empty] | Mgmt |  | 1581279 | 935214 | 677865 | 112508 | 47753.42 | 110311.86 | 139297 | 409870.28 | 697028.72 | 110000 | 682532.72 | -14047 |  | 113350 | 6000 | 0
[11 empty] | 1784156 | 1076214 | 739742 | 112508 | 51665.42 | 146783.86 | 140253 | 451210.28 | 761605.72 | 110000 | 747576.72 | -13580
|  | Total 3 agencies | [5 empty] | Total |  |  | 2622194 | 1670684 | 983310
SIGNATURE
Hanoi, 30 September 2011
For PMU
Pham Minh Thoa
National Programme Director
Note on M13: Huyenntt: increase 10k as outstanding payment from 2010
Note on X13: Oanh: needed for 3rd training by VNForest for central region
Note on X14: Oanh: needed for 3rd training by VNForest for central region
Note on W23: Oanh: 1,200 USD on the first draft
Note on V57: Oanh: Planning forest protection contractor (DARD Lam Dong)
Note on N58: Huyenntt: new
Note on N59: Huyenntt: new

## AWP 2012
Annex III | [42 empty] | revised 22 Feb
2012 ANNUAL WORK PLAN FOR PGA
(From 1/1/2012 - 31/12/2012)
Programme Title: UN-REDD Viet Nam Programme
Expected Output and Monitoring Activities | Annual Output Targets | Key Activities | Inputs |  | Timeframe | [15 empty] | Responsible Party | Key Actors | Budget category | Total budget | By PMU | by UN Agency | Exp PMU Q1/2011 | Exp UNDP Q1/2011 | Exp UNDP Q1-2/2011 | Exp PMU Q2/11 | Total exp | Balance | Known commitments | Net budget endorsed for remaining year | Proposed adjustment | By PMU | By UN Agency | Atlas code | Revised after 2nd PEB meeting [put figures for whole year 2010) (original chi Huyen) | PGA funding |  |  | 2012 Updated budget | 2011 Un-used budget
|  |  |  | Objectives | Jan | Feb | Mar | Mar | Apr | May | Jul | Jun | Jul | Aug | Nov | Sep | Oct | Nov | Dec | Dec
Outcome 1: Improved institutional and technical capacity for national coordination to manage REDD+ activities in Viet Nam |  | 1.7.1 National kick-off workshop |  | To get stakeholder's endorsement on the scope of the PGA and especially on the selection of the pilot province. | [18 empty] | Contract | [19 empty] | 7245 | bar: Timeframe Mar
|  | 1.7.2 Establishment of a Research Team to undertake operational aspects of the PGA, including mapping exercises | x | An national NGO will be contracted for the Research Team to drive the PGA process in the pilot province. More specifically, the NGO will: * map REDD+ stakeholders and provide a baseline for existing governance initiatives in the selected pilot province * organize and conduct a stakeholder workshop to present the PGA approach for provincial/district stakeholders in the selected pilot province, and conduct initial awareness rising on REDD+, present the findings from the mapping exerceises and get consent for a first cut on the draft indicators * consult with Advisory Group reguralry * draft the indicator set to be used for the data collection * organize and conduct a stakeholder consultation in the pilot province to get feedback on the draft indicator set | [16 empty] | PMU/VNForest/UNDP |  | Contracts, Commodities, transport and supplies | [19 empty] | 42210 | bar: Timeframe Jan to Timeframe Feb; Timeframe Mar to Timeframe May; Timeframe Jun to Timeframe Aug; Timeframe Sep to Timeframe Nov; Timeframe Dec
|  | 1.7.3 Establishment of Advisory Group |  | A larger group of REDD+ stakeholders that include GoV, CSO and Academia to advise the Research Team. | [38 empty] | 6000 | bar: Timeframe Feb; Timeframe Mar to Timeframe May; Timeframe Jun to Timeframe Aug; Timeframe Sep to Timeframe Nov; Timeframe Dec
|  | 1.7.4 South-South exchange - delegation from Indonesia to visit Viet Nam to share experiences from their REDD+ PGA | x | Exchange visit from Indonesia for inputs based on experiences with the PGA | [16 empty] | PMU/VNForest/UNDP |  | Commodities, transport and supplies | [19 empty] | 7975 | bar: Timeframe May
|  | 1.7.5 Preparation for data collection • Developing data collection instruments • Field testing of data collection instruments in pilot province • Assessments of training needs of data collectors | [40 empty] | 5000 | bar: Timeframe Jul to Timeframe Aug
|  | 1.7.6 Data collection | [40 empty] | 5000 | bar: Timeframe Sep
|  | 1.7.7 Data analysis and dissemination | [40 empty] | 5000 | bar: Timeframe Oct to Timeframe Nov; Timeframe Dec
|  | 1.7.8 Lessons Learned Exchange workshop in Indonesia |  | Focal points from the four PGA for REDD+ pilot countries will meet to discuss lessons learned and exchange expereinces | [16 empty] | UNDP | PGA Project Coordinator, GoV Focal Point, Research Team, UNDP focal points | Travel | [19 empty] | 8624
|  | Programme Management | x | [17 empty] | PMU/VNForest/UNDP |  | Personnel, Contracts, Commodities, transport and supplies | bar: Timeframe Jan to Timeframe Feb; Timeframe Apr to Timeframe May; Timeframe Jul to Timeframe Aug; Timeframe Oct to Timeframe Nov
|  | Travel costs for UNDP regional Governance expert in Bangkok |  | To give expert advice on the governance approach | [16 empty] | UNDP | [21 empty] | 9000 | bar: Timeframe Jan; Timeframe Mar; Timeframe May; Timeframe Jul; Timeframe Sep; Timeframe Nov
|  | Programme Coordinator salary |  | To facilitate the PGA process | [38 empty] | 12500 | bar: Timeframe Mar to Timeframe May; Timeframe Jun to Timeframe Aug; Timeframe Sep to Timeframe Nov; Timeframe Dec
|  | Traveling to the field for workshops | [40 empty] | 3000
|  | Miscellaneous | [40 empty] | 5000 | bar: Timeframe Feb; Timeframe Mar to Timeframe May; Timeframe Jun to Timeframe Aug; Timeframe Sep to Timeframe Nov; Timeframe Dec
Programme management | [42 empty] | 116554
SIGNATURE | [40 empty] | #REF! | Committed in WP so far
Hanoi, 12 October 2011 | [40 empty] | #REF! | PSC oustanding
For PMU | [23 empty] | For FAO | [11 empty] | For FAO
Pham Minh Thoa | [23 empty] | Akiko Inoguchi | [11 empty] | Akiko Inoguchi
National Programme Director | [23 empty] | Programme Officer | [11 empty] | Programme Officer
#REF!

## Summary (hidden)
Summary
Budget available:
According to original AWP | 0
Budget available upon deduction of USSD 64,412.4 | -64412.4 | (I)
Necessary budget for remaining 6 months | 0 | (II)
Missing budget | 64412.4 | (II)-(I)
Potential funding source | 21800
Refund PB6 from UNEP (collected) | 1500
VAT refund of 2010 (collected) | 9800 | Some from UNEP fund so will be separated to return to UNEP account
VAT refund 6 months 2011 | 7500 | Some from UNEP fund so will be separated to return to UNEP account
VAT refund last 6 months 2011 | 3000 | Some from UNEP fund so will be separated to return to UNEP account
Refund part of GMS | 11,453.76 | According to Nguyet
Note: VAT refund should be recorded in the Atlas as an additional income
so that this resource can be used as a reserve for project extension

## PMU cost (hidden)
Programme management
(FAO) | Programme steering committee meeting | x | x | PMU | Commodities, transport and supplies | Local travel, workshops | 75700 | 25000 | 25000 | 13694 |  |  | 1095 | 14789 | 10211 | 3211 | -7000 | 3000 | 75700
| Support for Provincial REDD working group |  |  | PMU | Commodities, transport and supplies | [12 empty] | 12000
| Personnel Cost |  |  |  | Personnel | [8 empty] | 0 | 0
| Programme Manager and National REDD Team Leader |  |  | PMU | Personnel | Project local staff | 71400 | 82314 | 82314 | 11846 |  |  | 11446 | 23292 | 59022 | 32892 | -26130 | 21994 | 71400
| Project accountant, Project Interpreter/secretary, communication officer |  |  | PMU | Personnel | Project local staff | 71400 | 37644 | 37644 | 6285 |  |  | 8950 | 15235 | 22409 | 17600 | -4809 | 18822 | 71400
| Prog financial assistan |  |  | PMU | Personnel | Project local staff | 71400 | 26568 | 26568 | 5282 |  |  | 6686 | 11968 | 14600 | 13300 | -1300 | 3948 | 71400
| Lam Dong staff (3 p) |  |  | PMU | Personnel | Project local staff | 71400 | 13644 | 13644 | 3472 |  |  | 3691 | 7163 | 6481 | 7781 | 1300 | 7542 | 71400
| Local travel |  |  | PMU | Transport | Local travel | 71600 | 25000 | 25000 | 5058 | 1028.8 | 698.43 | 6030 | 12815.23 | 12184.77 | 12184.77 | 0 | 15000 | 71600
| Office supplies, equipment, maintenance … |  |  | PMU | Commodities and supplies | Operational expenses (communication, stationery) | 72400 | 15000 | 15000 | 4519 | 7.41 |  | 7916 | 12442.41 | 2557.59 | 8557.59 | 6000 | 10000 | 72400
| Office rent |  |  | PMU | [13 empty] | 10800
| Total | [16 empty] | 103106

## Operational cost (hidden)
Operation cost
PEB meetings |  |  |  |  | 3000
Personnel Cost
Salary local staff
Programme Manager and National REDD Team Leader, technical officers |  |  |  | Personnel
National REDD Team Leader | month | 6 | 1003.5 | Personnel | 6021
National Technical Specialist | month | 6 | 954 | Personnel | 5724
Programme Manager | month | 6 | 1708 | Personnel | 10248
Project accountant, Project Interpreter/secretary, communication officer
Project accountant | month | 6 | 1017 | Personnel | 6102
Interpreter and secretary | month | 6 | 1017 | Personnel | 6102
Communication officer | month | 6 | 1103 | Personnel | 6618
Prog. Assistant, financial assistant, procurement assistant
Programme Assistant | month | 6 | 658 | Personnel
Financial and admin assistant | month | 6 | 658 | Personnel | 3948
Procurement assistant | month | 6 | 898 | Personnel
Lam Dong staff (3 p)
Field officers 2 persons | month | 12 | 449 | Personnel | 5388
Admin staff | month | 6 | 359 | Personnel | 2154
Local travel
DSA provincial travel 2 persons x 3 trips x 3 days on average | day | 36 | 51 | Transport | 1836
Terminal cost |  | 12 | 45 | Transport | 540
Air ticket 3 trips 2 persons |  | 12 | 250 | Transport | 3000
DSA of PMU in Lam Dong to Ha Noi 2 persons 2 trips 3 days | day | 24 | 65 | Transport | 1560
Terminal cost |  | 12 | 45 | Transport | 540
Local travel (car rental and taxi Ha Noi, Lam Dong, relevant provinces) |  | 6 | 800 | Transport | 4800
Equipment, supplies… |  |  |  | Commodities and supplies | 4531.59
Office supplies, communication maintenance
Stationeries and photocopying |  | 6 | 250 | Commodities and supplies | 1500
Telephone and mobile, internet, postal charges |  | 6 | 700 | Commodities and supplies | 4200
Electricity and water and building service |  | 6 | 200 | Commodities and supplies | 1200
Other mis costs (messenger, cleaning, consumables office supplies) |  | 2 | 300 | Commodities and supplies | 600
Lam Dong Provincial and district working group |  | 6 | 500 | Commodities and supplies | 3000
Rent |  | 6 | 1800 | Contract | 10800
Audit
Total |  |  |  |  | 90412.59

## Itemized cost
Annex III
2012 ANNUAL WORK PLAN FOR PGA
(From 1/1/2012 - 31/12/2012)
Programme Title: UN-REDD Viet Nam Programme
Expected Output and Monitoring Activities | Annual Output Targets | Key Activities | Inputs | Timeframe | [19 empty] | USD pr unit | Qty | Price | Budget for Q1+Q2 |  | Budget for Q3+Q4 | Responsible Party | Total budget | By PMU | by UN Agency | Exp PMU Q1/2011 | Exp UNDP Q1/2011 | Exp UNDP Q1-2/2011 | Exp PMU Q2/11 | Total exp | Balance | Known commitments | Net budget endorsed for remaining year | Proposed adjustment | By PMU | By UN Agency | Atlas code | Revised after 2nd PEB meeting [put figures for whole year 2010) (original chi Huyen) | PGA funding |  |  | 2012 budget in USD | 2011 Un-used budget
|  |  |  | Jan | Feb | Mar | Mar | Apr | May | Jul | Jun | Jul | Aug | Nov | Sep | Oct | Nov | Dec | Dec | Q1 | Q2 | Q3 | Q4
Outcome 1: Improved institutional and technical capacity for national coordination to manage REDD+ activities in Viet Nam |  | 1.7.1 National kick-off workshop |  |  |  |  | x | [12 empty] | x | [9 empty] | Research Team/PMU/UNDP
|  | Consultant/facilitator | [23 empty] | 1500
|  | Venue | [23 empty] | 1000
|  | Tea-break | [21 empty] | 2 | 30 | 60
|  | Lunch | [21 empty] | 15 | 30 | 450
|  | Cabin translation | [23 empty] | 225
|  | Equipment | [23 empty] | 200
|  | Translation, document, stationery and photocopying | [23 empty] | 150
|  | Air ticket provincial pax | [21 empty] | 245 | 8 | 1960
|  | DSA days | [21 empty] | 65 | 16 | 1040
|  | Terminal | [21 empty] | 45 | 8 | 360
|  | Land transport | [23 empty] | 300
|  | Subtotoal | [23 empty] | 7245 | 7245 | [22 empty] | 7245
|  | 1.7.2 Establishment of a Research Team to undertake operational aspects of the PGA, including mapping exercises | x | x | x |  | x | x | x |  | x | x | x |  | x | x | x |  | x | x | x | x | x
|  | Contract NGO to do the operational work | [17 empty] | x | x | x | x |  |  | 50000 | 25000 |  | 10000 | Research Team | [19 empty] | 35000
|  | Workshop 2 - in the Province | [18 empty] | x
|  | Venue | [23 empty] | 500 |  |  |  | Research Team/PMU/UNDP
|  | Tea-break | [21 empty] | 2 | 30 | 60
|  | Lunch | [21 empty] | 15 | 30 | 450
|  | Cabin translation | [23 empty] | 225
|  | Equipment | [23 empty] | 200
|  | Translation, document, stationery and photocopying | [23 empty] | 150 |  |  |  |  | Akiko Inoguchi | [11 empty] | Akiko Inoguchi
|  | Air ticket Nat. Stakeholders pax | [21 empty] | 245 | 4 | 980 |  |  |  |  | Programme Officer | [11 empty] | Programme Officer
|  | DSA days | [21 empty] | 28 | 20 | 560
|  | Terminal | [21 empty] | 45 | 4 | 180
|  | Land transport | [23 empty] | 300 | [16 empty] | #REF!
|  | Subtotoal | [23 empty] | 3605 | 3605 | [22 empty] | 3605
|  | Workshop 3 - in the Province | [18 empty] | x | [8 empty] | Research Team/PMU/UNDP
|  | Venue | [23 empty] | 500
|  | Tea-break | [21 empty] | 2 | 30 | 60
|  | Lunch | [21 empty] | 15 | 30 | 450
|  | Cabin translation | [23 empty] | 225
|  | Equipment | [23 empty] | 200
|  | Translation, document, stationery and photocopying | [23 empty] | 150 |  |  |  |  | Akiko Inoguchi | [11 empty] | Akiko Inoguchi
|  | Air ticket Nat. Stakeholders pax | [21 empty] | 245 | 4 | 980 |  |  |  |  | Programme Officer | [11 empty] | Programme Officer
|  | DSA days | [21 empty] | 28 | 20 | 560
|  | Terminal | [21 empty] | 45 | 4 | 180
|  | Land transport | [23 empty] | 300 | [16 empty] | #REF!
|  | Subtotoal | [23 empty] | 3605 | 3605 | [22 empty] | 3605
|  | 1.7.3 Establishment of Advisory Group |  |  | x |  | x | x | x |  | x | x | x |  | x | x | x |  | x | x | x | x | x | [6 empty] | PMU/VNForest/UNDP
|  | Logistics for meetings | [23 empty] | 2000
|  | Compensation to members | [23 empty] | 4000
|  | Subtotal | [23 empty] | 6000 | 3000 | 3 | 3000 | [20 empty] | 6000
|  | 1.7.4 South-South exchange - delegation from Indonesia to visit Viet Nam to share experiences from their REDD+ PGA | x | [5 empty] | x | [12 empty] | x | [7 empty] | UNDP/PMU
|  | Logistics for meeting | [23 empty] | 1000
|  | Travel | [21 empty] | 1500 | 3 | 4500
|  | DSA | [21 empty] | 165 | 15 | 2475
|  | subtotal | [23 empty] | 7975 | 7975 | [22 empty] | 7975
|  | 1.7.5 Preparation for data collection • Developing data collection instruments • Field testing of data collection instruments in pilot province • Assessments of training needs of data collectors | [9 empty] | x | x | [8 empty] | x | [6 empty] | 5000 | PMU/VNForest/FAO/UNDP | [19 empty] | 5000
|  | 1.7.6 Data collection | [12 empty] | x | [6 empty] | x | [6 empty] | 5000 | Research Team/PMU/UNDP/FAO | [19 empty] | 5000
|  | 1.7.7 Data analysis and dissemination | [13 empty] | x | x |  | x |  |  |  | x | [5 empty] | 5000 | Research Team/PMU/UNDP/FAO | [19 empty] | 5000
|  | 1.7.8 Lessons Learned Exchange workshop in Indonesia | [18 empty] | x
|  | Travel | [21 empty] | 1500 | 4 | 6000
|  | DSA | [21 empty] | 164 | 16 | 2624
Transfer
|  | subtotal | [23 empty] | 8624 | 8624 |  |  | UNDP | [19 empty] | 8624
|  | Programme Management | x | x | x |  |  | x | x |  |  | x | x |  |  | x | x |  |  | x | x | x | x
|  | Travel costs for UNDP regional Governance expert in Bangkok |  | x |  |  | x |  | x |  |  | x |  |  | x |  | x | [6 empty] | 1500 | 6 | 9000 | 4500 |  | 4500 | UNDP | [19 empty] | 9000
|  | Programme Coordinator salary |  |  |  |  | x | x | x |  | x | x | x |  | x | x | x |  | x |  |  |  |  | 1250 | 10 | 12500 | 6250 |  | 6250 | PMU | [19 empty] | 12500
|  | Traveling to the field for workshops for Prog Coor and UN CO | [21 empty] | 500 | 6 | 3000 | 1500 |  | 1500 | PMU/UNDP/VNForest/FAO | [19 empty] | 3000
|  | Miscellaneous |  |  | x |  | x | x | x |  | x | x | x |  | x | x | x |  | x | [6 empty] | 5000 | 2500 |  | 2500 | PMU/UNDP | [19 empty] | 5000
|  | subtotal | [24 empty] | 14750 | 0 | 14750
Programme management | [25 empty] | total | 73804 | 3 | 42750 | [20 empty] | 116554
Hanoi, 22 Feb 2012 | [47 empty] | #REF! | PSC oustanding
For PMU | [30 empty] | For FAO | [11 empty] | For FAO
Pham Minh Thoa | [30 empty] | Akiko Inoguchi | [11 empty] | Akiko Inoguchi
National Programme Director | [30 empty] | Programme Officer | [11 empty] | Programme Officer
#REF!