| Agreed next steps for the PGA in Nigeria |  |  |  |
| --- | --- | --- | --- |
| Milestones: | Specific activities: | By whom: | By when: |
| Follow-up after the Calabar workshop | - Share workshop report with agreements on key governance domains, organizational structure and next steps - Share preliminary research report | Workshop team/ PGA coordinator | 4/2/13 |
| Get baseline governance data | - Indicator training - Develop indicator set - Agree on data collection methods and process - Information/ data collected - Stakeholder validation of the findings | UN-REDD/ FAO Research team proposes, PGA/ REDD+ committee validates/ adopts Research team proposes, PGA/ REDD+ committee validates/ adopts Research team/ data collectors overseen by PGA coordinator PGA/ REDD+ Consultative Network validates, facilitated by PGA coordinator | 18/1/13 18/3/13 18/3/13 18/7/13 End of August |
| Develop a communication strategy | - Start discussing the end-users and dissemination of PGA information to ensure this reaches communities in appropriate form/ language | PGA/REDD+ Committee (to be presented to the PGA/ REDD+ Consultative Network) | Continuous work until we have the baseline data |
| Recruit a full-time PGA coordinator (as soon as possible) | - Develop ToR - Recruitment | Inputs from UN-Nigeria and UN-REDD, to be validated by the PGA/ REDD+ committee UNDP Nigeria/ UN-REDD team | ASAP |