| # UNITED NATIONS DEVELOPMENT PROGRAMME ## BDP/EEG - MISSION REPORT SUMMARY Date: 9/7/2013 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ### Name: Tim Boyle, UN-REDD |  | Tel No. +66819005402 |  |  |
| Approved Mission Itinerary: Bangkok-Thimphu-Bangkok |  | List of Annexes: |  |  |
| #### Inclusive Travel Dates: |  | Key counterpart(s) in each location: |  |  |
| 4-8 June., 2013 |  | - RGoB: Jigme Tenzin; Sigyel Delma, WMD - CO: Karma Rapten/Tashi Dorji - FAO: Joel Scriven - Consultant: Nedrup Tshering |  |  |
| Purpose/Objectives of Mission To assist in preparation of R-PP |  |  |  |  |
| Context UN-REDD support to Bhutan has been well-coordinated across agencies, and integrated with other initiatives. A request from the RGoB for targeted support was received in May, 2012, consisting of $40k from UNDP, $40k from FAO, and $25k from UNEP. The UNDP CO is also providing funding of approximately $60k over 18 months, and funding is available from PEI for work on benefit distribution. Following a mission in April, 2013, UNDP TS funds are being used for an assessment of corruption risks, benefit distribution options, and together with UNDP TRAC funds, were re-programmed to focus on developing an R-PP by July 31st, 2013. |  |  |  |  |
| Summary of Mission Activities/ Findings The national consultant has been very disappointing, and delivered only very poor and brief versions of components 1a-c and 2a-c. Joel Scriven had prepared high quality drafts of Components 3 and 4a, and I had prepared a draft of Component 4 b ahead of the mission. Therefore, much of the time was spent re-writing Components 1a-c and 2a-d. A meeting of the National Task Force on REDD+ was also attended to brief the members on the R-PP (interestingly, the meeting was held on a day declared by the government to be a no-car day (World Environment Day), so all members of the Taskforce had to walk to the meeting). Discussions were held with the UNDP CO on funding support to WMD and/or the DG of DoFPS to attend the PC15 meeting in Lombok. Discussions were also held with WMD on management arrangements for REDD+ readiness, including institutional mandates and a re-alignment of the Taskforce the become a higher-level steering committee, with three Technical Working Groups developing recommendations on specific technical issues A schedule was agreed to complete all drafting and review activities in time for submission of the R-PP so as to meet the July 31st dateline. |  |  |  |  |
| ## Follow up actions: - Finalization and submission of R-PP |  |  |  | Distribution List: - Tim Clairs, UN-REDD UNDP PTA |