Management Group (MG) of the UN-REDD Programme

Meeting Decisions of 23 October 2015

9h30 Geneva/Rome, 10h30 Nairobi

Attendance:

MG members and alternates

FAO: Maria José Sanz Sanchez, Tiina Vahanen

UNDP: Josep Gari

UNEP: Tim Christophersen

Secretariat: Mario Boccucci

Others

Secretariat: Mike Speirs, Jessica Holterhof

- Approval of decisions of previous calls, 7 and 14 October 2015

Decisions and Actions:

  - Any additional comments on the decisions are to be provided in writing by Wednesday, 28 October.

- Update on the finalization of the Fund documents (MOU, SAA and TOR)

Decisions and Actions:

- The Secretariat will provide the draft Terms of Reference for one UN representative in the EB, which will clarify the responsibilities and roles of such representative.

- The MG agreed that before each meeting of the EB, the three UN agencies will consult and agree on a common position to be presented by the UN agency that is currently a member of the EB. If any UN agency objects to the proposal for a decision at any matter, the member shall express that objection as the agreed position.

- Rather than approving of the 2016-2020 Results Framework, the EB will endorse it and propose changes/revisions to reflect lessons learnt, if deemed necessary. Additionally, a short footnote will be incorporated in the Results Framework that all outcomes are based on the Theory of Change, which has already been approved by the Policy Board.

- The UN agencies will provide a short written justification to the Secretariat on why the UN agencies have to be privy and included in the decision-making process. Based on those comments, the Secretariat will develop a rationale that will be sent to the Norwegian Government.

- The MG agreed on a timeline for the next steps:

| ACTION | WHO | WHEN |
| --- | --- | --- |
| Governance arrangements - Revision on governance arrangements based on MG comments | - Secretariat | - Latest COB Tuesday, 27 October |
| Programming cycle - Provision of updated draft Programming Cycle - UN agencies to provide written feedback | - Secretariat - UN agencies | - COB Friday, 23 October - Latest COB Monday, 26 October |
| Results Framework - UN agencies to provide written feedback - Provision of draft RF to MPTF for LPAC revision - Provision of draft RF as an information document for Session 5 to PB members | - UN agencies - Secretariat - Secretariat | - Latest COB Tuesday, 27 October (with potential follow-up discussion during next MG call) - Latest COB Tuesday, 27 October - Latest COB Monday, 2 November |
| Other sections of TOR - Provision of updated draft TOR - UN agencies to provide written feedback | - Secretariat - UN agencies | - COB Friday, 23 October - Latest COB Monday, 26 October |

- Update on the request to Norway for the 2016 Budget and the extension of the current SNA by 12 months

Decisions and Actions:

  - The UN agencies will provide their inputs for the 2016 fund request to Norway with a cost breakdown by UNDG budget categories as well as any written comments on the narrative by Monday, 26 October.

  - The no-cost extension will be signed in the following order: UNEP, FAO and UNDP.

- Update on PB15 agenda/Knowledge Management day

Decisions and Actions:

  - The draft agenda has been circulated to the MG for comment. Any additional comments are to be provided by Monday, 26 October.

  - No internal MG meeting will take place on Wednesday, 11 November.

- AOB

Next MG call

Decisions and Actions:

  - The next MG call will be on Friday, 30 October at 9.30h (Geneva time).