FiA Contract

Six outputs and 9 indicators are identified:

| Output | Indicator | Observations/Current status |
| --- | --- | --- |
| 1. Relevant fisheries officials trained on carbon stock assessment | At least 20 fisheries officials from the Great Lake and Coastal Areas improved knowledge on carbon stock assessment by Q3 of 2013 | USAID training cannot be counted! |
| 2. Local communities and local authorities aware of role of flooded forest and mangrove in carbon emissions and absorption | At least 4 public awareness [events] organized for at least 200 people by Q4 of 2013 | How many events held? How many people attended? Training reports available? |
| 3. 5-year implementation plan developed | Plan on REDD+ activities in flooded forest and mangrove management produced by Q1 of 2014 | Draft available? |
| 4. Law enforcement strengthened | At least two patrol teams formed and functioning well from Q4 of 2013; At least 20 demarcation poles and sign boards installed by Q2 of 2014 Two blockhouses constructed at conservation sites by Q1 of 2014 A set of equipment for preventing flooded forest procured by Q1 of 2014 | 4 indicators … current status? “Equipment for preventing flooded forest …” – presumably some words missing here |
| 5. Flooded forest and mangroves reforested where previously cleared | At least 20 ha replanted by Q2 of 2014 | Completed? Maps/reports? |
| 6. Effective management system evaluated | Effective management system evaluated by Q4 of 2014 |  |