# Work Plan

# UN-REDD Indonesia National Joint Programme Activities [June to October 2012]

| No. | Outcomes | Deliverables | Activities |  | Budget (US$) |  | Source of fund | Related ProdocOutputs | Collaborative Party | Time schedule |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Jun | Jul | Aug | Sep |  | Oct |
| 1 | Project operation | Good performance of project management in compliance with existing standard | - Project support (operations, especially administration, Human Resources and financial activities). |  | Salary | 40,000 (FAO), 75,000* (UNDP), 49,000*(UNEP) | FAO, UNDP, UNEP | 1.1 |  |  |  |  |  |  |  |
|  |  |  |  |  | Office Rental (July – Dec 2012) | 10,000 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Travel | 25,000 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Office supplies and misc. | 25,000 |  |  |  |  |  |  |  |  |  |
| 2 | MRV methods & capacities, specifically those on NFI and REL, are available in Indonesia & are endorsed by government agencies. | Indonesia’s National Forest Inventory (NFI) has improved data collection, data management and reporting | - Field data collection + meetings (a set of field data in inventory reports for 35 sample plots) |  | Staff for field teams, travel, field gear, meetings | 260,000 | FAO | 2.1 | Tadulako University and BPKH |  |  |  |  |  |  |
|  |  |  | - Quality Control (QC) of field data collection through re-measurement |  | Staff for field teams, travel, field gear, meetings | 18,000 |  |  | BPKH, Dinas Kehutanan |  |  |  |  |  |  |
|  |  |  | - Quality Assurance (QA) workshop |  | Workshop | 11,000 |  |  | IPSDH (IH) |  |  |  |  |  |  |
|  |  |  | - Entry of field data |  | Consultants + procurement of server | 23,000 |  |  | IPSDH (IH) |  |  |  |  |  |  |
|  |  |  | - NFI data analysis (timber and carbon stock data per NFI plot) |  | Consultant + meetings | 9,000 |  |  | IPSDH, FORDA |  |  |  |  |  |  |
|  |  |  | - NFI reporting (GHG inventory of Central Sulawesi forest) |  | Consultation methodology, printing and presentation of report | 12,500 |  |  | IPSDH, POKJA REDD+ CS |  |  |  |  |  |  |
|  |  |  | - Data validation |  | Desk review by consultant and meetings | 10,000 |  |  | University, FORDA |  |  |  |  |  |  |
|  |  |  | - Recommendation to refine the new NFI design |  | Workshop | 12,497 |  |  | IPSDH |  |  |  |  |  |  |
|  |  |  | - Development of policy recommendation for NFI |  | Consultant, Travel, Meeting | 6,000 |  |  | DKN (Agus Setyarso), Ministry of Forestry |  |  |  |  |  |  |
|  |  | Allometric equations in Indonesia are representative of all forest types and carbon groups | - Allometric equation training (Viet Nam) to identify existing allometric equations and remaining gaps |  | Travel of 14 participants | 28,000 |  | 2.2 |  |  |  |  |  |  |  |
|  |  |  | - Workshop on allometric equation (Indonesia) to develop a proposal on destructive sampling sites |  | Workshop | 11,000 |  |  |  |  |  |  |  |  |  |
|  |  | REDD+ related spatial data is available to the public | - Forest monitoring WebGIS |  | Consultants + software and hardware procurement + presentation meeting | 24,000 |  | 2.1 | IPSDH, FAO |  |  |  |  |  |  |
|  |  | Methodology and capacity for REL is available in each province in Indonesia | - REL training in 33 provinces |  | Two trainings for 33 persons, one from each province | 28,000 |  | 2.2 | Pusdiklat, Bappenas SatGas |  |  |  |  |  |  |
|  |  |  |  |  | Travel of participants (optional) | 30,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Workshop on REL development at province |  | Workshop in Palu, 25 Participants | 11,000 |  |  | POKJA REDD+ CS, IPSDH |  |  |  |  |  |  |
|  |  |  | - Peer review process for provincial REL |  | Selected experts to review the REL | 11,000 |  |  | IPSDH |  |  |  |  |  |  |
|  |  |  | - Development of policy recommendation of REL calculation at province |  | Consultant, travel, meeting | 5,000 |  |  | IPSDH |  |  |  |  |  |  |
|  |  | MRV readiness continues in Indonesia building also on lessons learned in UN-REDD | - Workshop on gap analysis for MRV |  | Workshop, Travel | 20,345 |  | 2.1 | IPSDH, SatGas, Forda, UN-REDD, AusAID, FCPF, JICA, GIZ |  |  |  |  |  |  |
|  | Optional activities (to be partnered with the Task Force and other agencies and depends on the need and the results of coordination efforts) |  | - Training on GHG inventory for forestry sector |  | Training for 30 participants, | 14,000 |  |  | SatGas, IPSDH |  |  |  |  |  |  |
|  |  |  | - Development of database on forest carbon information |  | Meetings, consultant, software | 15,000 |  |  | FORDA, IPSDH |  |  |  |  |  |  |
| 3 | Integration of the UN-REDD’s Provincial REDD+ Implementation Plan into the national programmes - SRAP and RAD-GRK | Finalization and consultation of the Provincial REDD+ Implementation Plan | - Final draft of the Provincial REDD+ Implementation Plan |  | Consultant | 9,000 | UNDP | 3.1, 3.3, and 1.2 | REDD+ Working Group |  |  |  |  |  |  |
|  |  |  | - FGD/Seminar and consultations on the Provincial REDD+ Implementation Plan in Central Sulawesi |  | (approx. 100 participants for consultations) | 15,000 |  |  | REDD+ Task Force, REDD+ Working Group, and RAD-GRK Working Group |  |  |  |  |  |  |
|  |  | Inputs to the Forestry Sector of RAD-GRK by transferring the results from the Implementation Plan and other relevant UN-REDD activities | - Joint workplan with the Task Force and the Working Groups |  |  | 15,000 |  |  | REDD+ Task Force, REDD+ Working Group, and RAD-GRK Working Group |  |  |  |  |  |  |
|  |  |  | - Workshops on related UN-REDD results for the first draft of RAD-GRK for the forestry sector in Central Sulawesi |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - FGDs and consultations on the first draft |  |  | 20,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Support for the final draft of RAD-GRK for the forestry sector in Central Sulawesi |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Dissemination of information on the process to develop RAD-GRK | - Documentation of RAD-GRK development process/lessons learned |  | Consultant | 15,000 |  |  |  |  |  |  |  |  |  |
|  |  | Inputs to SRAP by transferring the results from the Implementation Plan and other relevant UN-REDD activities | - Consultations on the Provincial REDD+ Strategy, led by the REDD+ Working Group (sub-technical group on Provincial Strategy) |  | (Provincial and district government) | 25,000 |  |  | REDD+ Task Force, REDD+ Working Group, and RAD-GRK Working Group |  |  |  |  |  |  |
|  |  |  | - Joint workplan with the Task Force and the Working Groups |  |  | 15,000 |  |  | REDD+ Task Force, REDD+ Working Group |  |  |  |  |  |  |
|  |  |  | - Implementation of the workplan and coordination with the Task Force |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | FPIC methodology development and advocacy for legalization | Finalization of FPIC methodology | - FPIC practice | - National Park | Survey, ToT, Event | 40,000 | UNDP | 3.2 | REDD+ Working Group |  |  |  |  |  |  |
|  |  |  |  | - Optional: other communities |  | 60,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Evaluation of FPIC practice | - National Park | Consultants | 10,000 |  |  | Independent evaluators |  |  |  |  |  |  |
|  |  |  |  | - Optional: other communities |  | 15,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Development of the final draft of FPIC methodology |  | Consultant | 8,000 |  |  | REDD+ Working Group |  |  |  |  |  |  |
|  |  | Dissemination of information, comments and inputs from stakeholders as well as the process to develop the methodology | - Consultations on the FPIC methodology |  | (Palu and Jakarta) | 20,000 |  | 3.2 and 1.2 | REDD+ Working Group, REDD+ Taks Force, PokjaPantau |  |  |  |  |  |  |
|  |  |  | - FPIC process documentation/lessons learned |  | Consultant | 15,000 |  |  | REDD+ Working Group |  |  |  |  |  |  |
|  |  | Advocacy for legalization of FPIC methodology | - FGDs on legal work for FPIC mechanism in Central Sulawesi |  |  | 10,000 |  | 3.2 | REDD+ Working Group, Biro Hukum Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - Development of policy recommendations for FPIC implementation and methodology in Central Sulawesi |  | Consultant | 8,000 |  |  |  |  |  |  |  |  |  |
|  |  | Dissemination of information on the activities related to safeguards | - National workshop on social safeguards for REDD+ (Launching event with FAO and UNEP) |  | (Jakarta) | 8,000 |  |  | REDD+ Working Group, REDD+ Task Force, FCPF |  |  |  |  |  |  |
| 5 | BDS options development, socialization and support for legal framework | Finalization of BDS options for Central Sulawesi | - FGDs on the BDS study draft |  |  | 10,000 | UNDP | 2.3 | REDD+ Working Group |  |  |  |  |  |  |
|  |  |  | - Development of the final BDS options for Central Sulawesi |  | Consultant | 8,000 |  |  |  |  |  |  |  |  |  |
|  |  | Dissemination of the results from the BDS study | - Seminars/workshops on the results of the BDS study |  |  | 20,000 |  | 2.3 and 1.2 | REDD+ Working Group, academia |  |  |  |  |  |  |
|  |  | Advocacy for REDD+ compliant BDS legal framework in Central Sulawesi | - FGDs on legal work for BDS |  |  | 8,000 |  | 2.3 | REDD+ Working Group |  |  |  |  |  |  |
|  |  |  | - Development of policy recommendations on BDS legal framework |  | Consultant | 8,000 |  |  |  |  |  |  |  |  |  |
| 6 | Capacity Assessment and Development for REDD+ Knowledge and Learning Facility/Network in Central Sulawesi | Capacity Assessment on knowledge, learning, and general awareness of REDD+ at district level in Central Sulawesi | - Identifying stakeholders at the district |  | Consultant | 10,000 | UNDP | 3.2 and 1.2 | Asia-Pacific Regional Centre (APRC), REDD+ Working Group |  |  |  |  |  |  |
|  |  |  | - Design and conduct the assessments |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Develop recommendations (and costing) and knowledge packages to be delivered through various modalities and network |  | Consultant | 8,000 |  |  |  |  |  |  |  |  |  |
|  |  | Dissemination of the results of the assessment | - Consultations on the recommendations and knowledge packages |  |  | 12,000 |  |  | REDD+ Task Force |  |  |  |  |  |  |
|  |  |  | - Optional: CA process documentation/lessons learned |  | Consultant | 15,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Optional: International event on needs assessments |  |  | 30,000 |  |  |  |  |  |  |  |  |  |
|  | Optional activities (to be partnered with the Task Force and other agencies and depends on the need and the results of coordination efforts) | Capacity development through implementation of knowledge packages | - Implement/Deliver Knowledge Packages through Facility/Network |  | Consultant | 35,000 |  |  | REDD+ Working Group, REDD+ Task Force KM Team, Pustanling |  |  |  |  |  |  |
|  |  |  | - Evaluation of results of Knowledge Delivery and Network Facilitation |  | Independent evaluators | 12,000 |  |  |  |  |  |  |  |  |  |
|  |  | Dissemination of the CA process | - CD process documentation lessons learned |  | Consultants | 20,000 |  |  |  |  |  |  |  |  |  |
|  |  | Policy recommendations on KM framework for REDD+ | - Joint Workshop and FGDs on developing framework for REDD+ knowledge management in Indonesia |  |  | 25,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Developing a policy recommendation on participatory KMframework of REDD+ Indonesia |  | Consultant | 20,000 |  |  |  |  |  |  |  |  |  |
| 7 | Impact of the awareness-raising activities on REDD+ issues in national level and Central Sulawesi | Impact assessment of the UN-REDD National Programme awareness-raising activities | - Development of tools for assessing impact of awareness-raising activity |  | Consultant | 11,000 | UNEP | 1.3. |  |  |  |  |  |  |  |
|  |  |  | - FGD on the impact assessment of the Programme awareness-raising activities |  | Field visit of consultant, FGD expenses and printing | 10,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Final report summarizing the result of impact assessment |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Awareness impact monitoring system for Central Sulawesi | - Development of awareness impact monitoring system for Central Sulawesi |  | Consultant | 11,000 |  |  | REDD+ Task Force, REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - FGD on the awareness impact monitoring system for Central Sulawesi |  | Field visit of consultant , FGD expenses and printing | 10,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Final report summarizing the system |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Strengthening common understanding on REDD+ issues among key stakeholders in national level and Central Sulawesi | Policy recommendation of REDD+ communication strategy | - Finalization of draft of policy recommendation of REDD+ communication strategy |  | FGD expenses and remaining consultant fee | 9,000 | UNEP | 1.3 | REDD+ Task Force |  |  |  |  |  |  |
|  |  |  | - FGD on the policy recommendation of REDD+ communication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | REDD+ information, education and communication materials | - Brochures, leaflets, posters, short clip on REDD+ and FPIC |  | Consultant’s fee, design, layout and printing distribution | 11,500 |  |  | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - Editing of documentary film of FPIC process in LembahMukti Village |  | Consultant | 3,000 |  |  | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - On-Air Radio socialization regarding REDD+ issues in national level and Central Sulawesi Province |  | Air-time fee | 6,000 |  |  | National Council on Climate Change (DNPI), REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - Newsletters |  | Consultant | 8,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Website maintenance |  | Consultant | 3,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Final revision of popular version of UN-REDD Indonesia Annual Report |  | Consultant fee and printing | 6,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Translating, proofreading and editing materials of UN-REDD Indonesia for international audiences |  | Consultant for translation | 2,500 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Consultant for proofreading and editing | 6,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Launching of UN-REDD products (including publication of outputs under programme of work of FAO UNDP, and UNEP); co-funding events financed by UNDP and FAO |  | Including printing and reproduction the products, Inviting 33 representatives from 33 provinces, and dissemination of the prducts to the concerned parties | 25,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Documentation of FPIC process and other UN-REDD’s activities in the pilot village (e.g. LembahMukti Village) |  | Consultant fee, field visit, FGD of 15-pax, and printing | 11,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Lessons learned report focusing on the Programme |  | Consultant | 11,000 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Printing | 2,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - “UN-REDD Indonesia in pictures”, a book consists of captioning picture stories related to UN-REDD Indonesia’s activities |  | Consultant fee including travel and local transport | 11,000 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Reproduction cost (hard covered) | 5,000 |  |  |  |  |  |  |  |  |  |
| 9 | International and national campaign on REDD+ | Participation of key stakeholder representatives in the international conference on REDD+ | - Sending 5 Indonesian representatives to attend the 3th ASFN Conference in Cambodia (11-16 June 2012) |  | Travel cost and DSAs for 5 pax to Cambodia (@ 6 days/pax) | 8,600 | UNEP | 1.3 |  |  |  |  |  |  |  |
|  |  | Policy recommendation on gender safeguard | - Polishing zero draft gender safeguard document produced on 7 February 2012 |  | Consultant | 1,500 |  |  | REDD+ Task Force |  |  |  |  |  |  |
|  |  | Gender and REDD+ Study in Central Sulawesi | - Development of study on gender and REDD+ in Central Sulawesi |  | Consultant | 11,000 |  |  | REDD+ Task Force |  |  |  |  |  |  |
|  |  |  | - FGD on the gender and REDD+ in Central Sulawesi |  | Field visit of consultant, FGD expenses and printing | 10,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Study report on gender and REDD+ in Central Sulawesi |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Enhancing knowledge and capacity of key stakeholders at national level and Central Sulawesi on updated REDD+ information | REDD+ trainings – with emphasis on local level actors | - Trainings on REDD+ for local woman leaders in Central Sulawesi |  | Consultant fee, training expenses, and printing | 8,750 | UNEP | 1.3 | REDD+ Task Force |  |  |  |  |  |  |
|  |  |  | - Trainings on REDD+ for religious leaders in Central |  | Consultant fee, training expenses, and printing | 8,750 |  |  |  |  |  |  |  |  |  |
|  |  | Capacity building for REDD+ negotiators | - Trainings on REDD+ negotiation for existing and future Indonesian Delegates who are specialized in REDD+ negotiation |  | Trainings and FGD expenses, consultant fee, and printing | 12,000 |  |  | International cooperation Bureau (KLN) of Mofor, DNPI, Ministry of Foreign Affairs |  |  |  |  |  |  |
|  |  |  | - Guideline for REDD+ negotiators |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Study on the geopolitical map of REDD+ |  | Consultant and FGD expenses | 17,000 |  |  |  |  |  |  |  |  |  |
| 11 | Maximizing potential carbon-benefits and incorporating multiple benefits in Central Sulawesi | Finalization of the priority setting toolkit for multiple benefits development | - Improving map, soil and biomass carbon maps inputs for the development of multiply benefit maps |  | Travel | 4,000 | UNEP | 2.4 | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  |  |  | Consultant | 15,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Two-day workshop to launch the final product of the priority setting toolkit |  | Workshop expenses | 15,000 |  |  | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - Training GIS related to the use of priority setting toolkit for provincial staffs |  | Training expenses | 15,000 |  |  | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - Trainings GIS related to the use of priority setting toolkit for district staffs (covering basic GIS and the GIS related to the use of toolkit) |  | Training expenses | 19,000 |  |  | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  |  |  | Consultant | 15,000 |  |  |  |  |  |  |  |  |  |
|  |  |  | - Policy recommendation on the adoption of the toolkit for REDD+ planning (for the drafting of related Central Sulawesi Governor letter/decree) |  | Consultant | 10,000 |  |  | REDD+ Working Group in Central Sulawesi, Provincial Government of Central Sulawesi |  |  |  |  |  |  |
|  |  | Multiple benefits Valuation | - Two-day workshop on multiple benefit valuation in Palu, Central Sulawesi |  | Workshop expenses | 10,000 |  |  | REDD+ Working Group in Central Sulawesi |  |  |  |  |  |  |
|  |  |  | - Advisory notes on the implementation of multiple benefits for a forest area |  | Consultant | 5,000 |  |  | REDD+ Working Group in Central Sulawesi, Provincial Government of Central Sulawesi |  |  |  |  |  |  |

# Plan of Consultations Conducted by PMUfor the UN-REDDNational Joint Programme Activities DuringExtension

| No. | Date& Time | Consulted Institution | Location | Issue | Note |
| --- | --- | --- | --- | --- | --- |
| 1. | 28-29 May | Pak Rauf, Pokja II Sulteng | Pajajaran Suites | FAO and UNEP Plan | Proposal from Pokja incorporated into Workplan |
| 2. | 1 June 14.00 – 17.00 | Satgas REDD+, Policy Working Group | Satgas REDD+ working group meeting room, BNPB Build, Jl. Juanda | Follow-up on the letter from Satgas to Governor | Tri-partiet meeting - Joint Workplan for SRAP (July 2012) - Share and Invite Satgas REDD on UN-REDD activities |
| 3. | 4 June 10.30 – 17.00 | PokjaPantau REDD+ Sulteng | Hotel Jazz, Palu | Progress UN-REDD, extension plan and exit strategy | Governor – Pokja REDD+ Sulteng – PokjaPantau consultation meeting. |
| 4. | 6 June 09.00 – 16.30 | Stakeholder engagement working group Satgas REDD+ | Satgas REDD+ working group meeting room, BNPB Build, Jl. Juanda | FPIC | FPIC guideline and materials to be sent to Satgas for Kalteng FPIC inputs. |
| 5. | 6 June 16.00 – 19.00 | UKP4/Satgas, FAO, Pustanling, KLH, Mofor. | UKP4 meeting room, jln. Veteran | REL training, MRV synchronization program | Satgas REDD+ will use a training module to be implemented in Central Kalimantan |
| 6. | 8 June 10-12.00 | KM working group, Satgas REDD+ | Satgas REDD+ working group meeting room, BNPB Build, Jl. Juanda | KM FGD preparation | TOR for facilitator consultant will be developed by pak John and share to others next week |
| 7. | 8 June | Bappenas, Pusdikat | Santika Hotel | REL for RAD | FGD is requested (add to FAO workplan) |
| 8. | 8 June | Univ Tadulako, Pak Rauf Cs | Santika Hotel, Bogor | FAO work on NFI | MoU FAO-UNTAD |
| 9. | 9 June 10-12.00 | Tripartietmeering (PMU UNREDD, Satgas REDD+, SultengGov) | Hotel Borobudur | Plan for Sulteng | Joint Workplan on SRAP With Satgas REDD |
| 10. | May-June | Bu Rukmini / Pokja IV Sulteng | Email | FPIC plan and gender mainstreaming | FPIC second testing and legal work at province level |

# PMU STRUCTURE DURING EXTENSION PERIOD

*) May-Oct 2012

Stated in the prodoc of UN-REDD

Dates: 21-31

Provincial Strategy and Action Plan

Regional Action Plan on GHG

Free, Prior, Informed Consent

Benefit Distribution System

The knowledge packages will be developed based on the results of the capacity assessment.

Knowledge management