## Slide 1: REDD+ Readiness Roadmap, Bangladesh
Mr. Md. Yunus Ali, Chief Conservator of Forests,
Bangladesh Forest Department
Mr. Haradhan Banik, Deputy Chief Conservator of Forests, National REDD+ Focal Point,
Bangladesh Forest Department
Venue: CBCB Centre,24/C Asad Avenue,
Mohammadpur, Dhaka-1207.
Date: 23-24 October 2013.

## Slide 2: What is REDD+? Definition:
Reducing Emissions from Deforestation and Forest Degradation; and the role of conservation, sustainable management of forests and enhancement of forest carbon stocks
+ = Forest Conservation, Sustainable Management of Forest and Enhancement of Forest Carbon Stocks

## Slide 3: Why REDD+ in Bangladesh?
High Rural Population Density: Opportunity to test REDD+ Strategies which will be relevant for other countries with fast-growing populations

## Slide 4: Why REDD+ in Bangladesh?
Vibrant Microfinance Sector: Using existing large-scale microfinance networks to develop lessons on benefit distribution for REDD+

## Slide 5: Why REDD+ in Bangladesh?
Mangrove ecosystems: Appropriate REDD+ strategies in the world’s largest mangrove ecosystem, for potential replication elsewhere

## Slide 6: Why REDD+ in Bangladesh?
REDD+ as a link between Adaptation and Mitigation strategies: As a leader in climate change adaptation negotiations, Bangladesh can demonstrate how REDD+ can complement, rather than conflict with, a National Adaptation Plan of Action (NAPA)

## Slide 7: Why REDD+ in Bangladesh?
Forest Governance and the Chittagong Hill Tracts: Bottom-up approaches to inducing changes in behavior among forest-dependent peoples and local authorities, building mutual respect and confidence

## Slide 8
Forest area by forest types
The total area divided into tree Cover
Forest types area by tree cover classes (%)
Source: National Forest and Tree Resources Assessment 2005-2007 Bangladesh, MoEF, FAO

## Slide 9
National/International Policy and Institutional Framework
Benefit distribution
MRV/FIS
Policies and Measures
National REDD+ Strategy
Environmental Safeguards, including:
Stakeholder participation
Respect for rights of IPs (including FPIC)
Transparent governance (including anti-corruption)
No conversion of natural forests
Capture of multiple benefits
Avoidance of displacement and reversals
Social Safeguards, including:
CO2
CO2
CO2

## Slide 10
Prepare “REDD+ Readiness Roadmap”
Implement Roadmap (Phase 1 of REDD+: Initial Readiness)
Scale-up and initiate results- based payments (Phase 2 of REDD+)
Full National Implementation (Phase 3)
PROCESS
PRODUCTS
Readiness Roadmap
Implementation Framework
MRV System
Nat’l REDD+ Strategy
Lessons & revisions
Performance

## Slide 11
REDD+ Steering Committee
FAO
UNDP
National Expert
REDD+ Focal Point
Roadmap Preparation Process
Establishment of Technical Advisory Team

## Slide 12
MRV Working Group
Reference Emission Levels
Forest Monitoring
Strategy Working Group
Drivers of Deforestation and Degradation
Policies and Measures
Safeguards Working Group
Consultation and Participation
Social and Environmental Standards
Forest and Non-forest Land
Roadmap Technical Advisory Team
Establishment of Technical Working Groups
Roadmap Preparation Process

## Slide 13: Stake holder Consultation
During REDD+ Readiness Roadmap preparation 5 Regional Workshop Were conducted -
Rangamati- All participant were indigenous people
Cox's Bazar- Local & indigenous people
Madhupur- Local & indigenous people
Sreemongol- Local & indigenous people
Thakurgaon- Local & indigenous people

## Slide 14
Roadmap Preparation Process
Stakeholder Consultations
National Workshop

## Slide 15
Roadmap Preparation Process
Stakeholder Consultations
Regional Workshop

## Slide 16
Roadmap Preparation Process
Stakeholder Consultations
Regional Workshop

## Slide 17
National Consultations
IP,
Govt,
NGO,
CMC,
DP
At Dhaka

## Slide 18
REDD Team
Talked with
Raja Devasish Roy- Chakma King
Local IP Leaders in Longadu
&
Bilai Chari,

## Slide 19
 | Roadmap Outcomes
Roadmap Outcome 1 | REDD+ Management Structure agreed and established
Roadmap Outcome 2 | Establish conditions for inclusive and equitable consultation and communication on REDD+ Output 1: Awareness raising strategy Output 2: Create framework for stakeholder engagement Output 3: Continuous consultation process
Roadmap Outcome 3 | National REDD+ Strategy Options Identified Output 1: Consensus on drivers of deforestation and forest degradation Output 2: Preliminary options for REDD+ strategies defined
Roadmap Outcome 4 | Frame Conditions for REDD+ Implementation in place Output 1: Institutional and stakeholder capacities for REDD+ developed Output 2: Legal rights regarding land tenure and resource use clarified
Roadmap Outcome 5 | Information for developing national Reference Levels or Reference Emission Levels acquired Output 1: Capacity need assessment on REL/RLs Output 2: Assess Bangladesh’s National Circumstances Output 3: Combining and harmonize historical forest area changes Output 4: Develop a methodology to assess past forest land area changes Output 5: Testing different RELs/RLs and possibilities of sub-national RELs/RLs
Roadmap Outcome 6 | Monitoring and MRV procedures for REDD+ developed Output 1: Build capacity for GHG inventory in the forest sector Output 2: Develop a satellite forest monitoring system Output 3: Design a national forest inventory Output 4: Support scientific research on key issues for MRV

## Slide 20: Roadmap Outcome 1
REDD+ Management Structure agreed and established
Inter-ministerial meeting on REDD+
Review of existing REDD+ management arrangements
REDD+ Steering Committee and REDD Cell ToRs revised and agreed
Regular meetings of REDD+ Steering Committee
REDD+ Stakeholder Forum (RSF) established and functioning, with agreed membership, roles and ToR
Three Technical Working Groups (TWGs) established and functioning, with agreed membership, roles and ToR
Review of technical advisory framework for REDD+, comparing role of current REDD+ Technical Committee with those of RSF and TWGs
National REDD+ management structure formalised and mandated by MoEF

## Slide 21: Roadmap Outcome 2
Establish conditions for inclusive and equitable consultation and communication on REDD+
Output 1: Awareness raising strategy
  Review and develop materials for REDD+ in Bangladesh context
  Adapt and initiate extension network for REDD+
  Assess opportunity for radio/TV broadcasts
  Establish national REDD+ website
Output 2: Create framework for stakeholder engagement
  Detailed, objective stakeholder analysis and validation through REDD+ Stakeholder Forum
  Engage existing civil society networks as channels for two-way communication on REDD+
  Develop strategy for mainstreaming gender issues in forest sector
  Continuously review and revise REDD+ SC and TWG membership to reflect changing stakeholder views

## Slide 22: Roadmap Outcome 2
Establish conditions for inclusive and equitable consultation and communication on REDD+
Output 3: Continuous consultation process
  National and regional workshops on REDD+ management structure, drivers and candidate strategies
  Develop guidelines on methods for ensuring FPIC, designed around traditional decision-making systems
  Train extension workers as intermediaries in FPIC process
  Assess options for independent grievance mechanism for forestry and environmental issues
  Establish ombudsman for climate change issues and new cell for climate change under human rights commission

## Slide 23: Roadmap Outcome 3
National REDD+ Strategy Options Identified
Output 1: Consensus on drivers of deforestation and forest degradation
  Analyse results of national/regional consultation workshops on drivers
  Assess national forest governance systems for effectiveness against drivers
  Identify conflicts, and need for alignment, within existing land use policies
  Output 2: Preliminary options for REDD+ strategies defined
  Analyse results of national/regional consultation workshops on strategies
  Develop options for policy-based approaches to addressing drivers
  Develop locally-specific activity packages for addressing drivers in CHT and other regions
  Feasibility of strategic options assessed against human and financial capacity and infrastructure needs
  Methodology developed for cost analysis of candidate strategies and activity packages

## Slide 24: Roadmap Outcome 4
Frame Conditions for REDD+ Implementation in place
Output 1: Institutional and stakeholder capacities for REDD+ developed
  Analyse institutional strengthening requirements of key bodies in REDD+ management structure, including internal governance, communication and administration
  Develop a national competency framework for REDD+
  Undertake a full Capacity Building Needs Assessment for REDD+
  Design a national REDD+ Capacity Building Action Plan
  Develop a national REDD+ information management system
Output 2: Legal rights regarding land tenure and resource use clarified
  Assess clarity of land and forest tenure systems, analyse gaps in legislation
  Study on the meaning and application of ‘carbon rights’ in national context
  Incorporate forest and land rights issues into new Right to Information Act and Anti-corruption law
  Form independent commission for customary land rights in CHT and at national level

## Slide 25: Roadmap Outcome 4
Frame Conditions for REDD+ Implementation in place
Output 3: Transparent system for management of REDD+ finances in place
  Conduct study on the design of a body for management of international transactions in carbon credits
  Analyse past ‘best practice’ in Bangladesh for implementing national-scale development projects
  Analyse existing microfinance schemes for potential roles in resource distribution within REDD+
  Investigate options for lowering transaction costs for local forest managers
  Develop options for a performance-based payment mechanism for forest sector activities, accessible to private and non-government actors
Output 4: Nationally-appropriate and internationally-compliant standards for social and environmental safeguards developed
  Review globally-available REDD+ safeguards tools
  Develop nationally-specific indicators to comply with international social and environmental principles and criteria
  Comprehensive multi-stakeholder validation process for social and environmental indicators
  Develop and test monitoring methodology against indicators

## Slide 26: Roadmap Outcome 5
Information for developing national Reference Levels or Reference Emission Levels acquired
      Output 1: Capacity need assessment on REL/RLs
The stakeholders for REL/RL development are identified;
A workshop will be held representing the various stakeholders involved in REL/RLs;
REL/RLs human, technical and financial capacities will be assessed;
Training on REL/RL will be provided;
The necessary institutional arrangements will be identified.
      Output 2: Assess Bangladesh’s National Circumstances
Further assessment of land-use policy, forest policy and governance;
Assessments undertaken as part of the REDD+ Strategy analysis;
Collection of historic data will provide the contribute to conservation goals, sustainable development priorities, objectives and projects, and circumstances that will have a significant impact on the successful implementation of REDD+.
      Output 3: Combining and harmonize historical forest area changes
Comparison of existing historical data for deforestation, afforestation/reforestation, forest degradation, forest management, national park;
Harmonization of existing data when possible;
Recommendations on the use of historical data to develop REL/RL at national and sub-national levels.

## Slide 27: Roadmap Outcome 5
Information for developing national Reference Levels or Reference Emission Levels acquired
      Output 4: Develop a methodology to assess past forest land area changes
Assess the quality of past satellite imageries in comparison with currently available satellite imageries for the forest monitoring system;
Assess past forest land area change in one demonstration sites;
Analysis of the compatibility of the past forest land area assessment with the results; obtained from the forest monitoring system;
Test the method in one demonstration site;
Propose methodology and recommendations.
      Output 5: Testing different RELs/RLs and possibilities of sub-national RELs/RLs
Identifying and learning from REL/RL(s) methodologies from other countries;
Identification of existing sub-national REL/RL(s) in Bangladesh;
Developing and testing REL/RL(s) at sub-national scale with the objective of scaling up to national scale in the future;
Workshop to discuss the development of RELs/RLs;
Propose recommendations and methodology to integrate sub-national actions into the national REDD+ strategy.

## Slide 28: Roadmap Outcome 6
Monitoring and MRV procedures for REDD+ developed
Output 1: Build capacity for GHG inventory in the forest sector
  Conduct specific capacity building needs assessment for forest sector GHG inventory, including geospatial data processing
  Rationalise forest definitions and classification systems for land and forest types
  Identify and procure equipment and software for forest sector GHG inventory
  Establish central database and data collection methods
Output 2: Develop a satellite forest monitoring system
  Establish national satellite image characterisation for forest monitoring
  Establish national forest management information system
  Align forest boundaries in the field with GIS-based boundaries
  Develop nationally-appropriate indicators and methods for forest monitoring system

## Slide 29: Roadmap Outcome 6
Monitoring and MRV procedures for REDD+ developed
Output 3: Design a national forest inventory
  Harmonise and record all existing inventory data
  Review existing national forest inventory design and recommend improvements
  Explore options for multi-stakeholder participation in forest inventory activities and capacity development needs for these options
Output 4: Support scientific research on key issues for MRV
  Develop allometric equations for major existing tree species and forest types
  Explore development of participatory tools for forest monitoring and MRV

## Slide 30: The National REDD+ Roadmap
National REDD+ Readiness Roadmap
Implementation of the roadmap
REDD+ projects
National and international support to REDD+ mechanism

## Slide 31: A) UN-REDD Global Programme
Implementation of the roadmap
Targeted Support Programme on -
Social Impact &Corruption Risk Assessment
Social Impact Assessment
Modhupur
Sreemongol
Kaptai
(Cox’Bazar
Dinazpur)
b) Corruption Risk Assessment
Modhupur
Sreemongol
(Next consultation will be held at -
Khulna,
Rangamati,
Cox’sBazar,
Dinazpur )
2. Measurement, Reporting & verification (MRV)
IP,
Local People, Sawmill owners,
Furniture makers,
Forest dwellers,
Brick field owners
Etc.

## Slide 32: B) UN-REDD National Programme
Implementation of the roadmap
Readiness Preparation Proposal (R-PP)
-Submission of R-PP
UN-REDD 9th policy Board Meeting
– BD is invited to submit the R-PP
Validation Meeting - Govt. NGO, IP, DP etc.
UN-REDD 11th policy Board Meeting
- will be held in December,2013

## Slide 33: Thank You