## Slide 1: Identifying UN-REDD Priorities in Indonesia

## Slide 2: Step 1: Scoping Mission
Meetings with all stakeholder groups
Discussions on harmonization with WB
Scoping Mission - Nov. 2008

## Slide 3: Step 2: Post-Scoping Mission
Gaps analysis
Support services to MoF
Development of “Draft 0”

## Slide 4: Step 3: Formulation Mission
Formulation Mission - Feb. 2009
Discussions with MoF and other stakeholder groups
Harmonization with R-PLAN
Development of JPD for submission to UN-REDD Policy Board

## Slide 5: Draft project structure
Objective of UN-REDD Programme in Indonesia:
To assist the GoI in attaining REDD-readiness

## Slide 6: Outcomes
Outcome 1: Strengthened multi-stakeholder participation at national level
Outcome 2: Successful provincial demonstration of establishing MARV and fair payment systems based on the national REDD architecture
Outcome 3: Capacity established to implement REDD at decentralized levels

## Slide 7: 1: Strengthened multi-stakeholder participation at national level
Output 1.1 Consensus on key-issues for REDD policy development
Organize national and sub-national consultations on key-issues, including inter-ministerial round table discussions
Analyze key issues identified by stakeholders to streamline the REDD value chain
Prepare policy recommendations
Develop roadmap for issuing policies to address these issues

## Slide 8: 1: Strengthened multi-stakeholder participation at national level
Output 1.1 Consensus on key-issues for REDD policy development
Output 1.2 Communications and knowledge exchange programme
Conducting awareness baseline assessment;
Design of social marketing campaign, specifically focusing on high level government decision makers;
Engage with existing REDD projects to analyze lessons (particularly related to issues of poverty)
Develop REDD Information, Education and Communication materials
National knowledge & learning platform established
Conduct training on REDD

## Slide 9: 2: Successful provincial demonstration of MARV and fair payment systems
Output 2.1 Improved Capacity to capture REDD elements within MARV
Organization of a seminar at provincial level
Identification and assessment of capacity building needs and feasibility for MARV at the provincial level
Training of staff of provincial institutions in implementation of MARV system
Mobilization of technical support for designing scalable NFI sampling scheme and standards.
Demonstration and formulation of standards for the estimation of carbon storage and temporal change

## Slide 10: 2: Successful provincial demonstration of MARV and fair payment systems
Output 2.2 Reference emissions level (REL) established
Review of methodologies for establishing scenario/baseline at a provincial level
Awareness raising of purpose of REL and calculation methodology
Compilation of data to support establishment of the REL
Establishment of a provisional Baseline and Reference emissions level (REL)
Stakeholder consultations on provisional REL
Scientific peer review of provisional REL
Establishment of revised REL
Dissemination of REL information
Output 2.1 Improved Capacity to capture REDD elements within MARV

## Slide 11: 2: Successful provincial demonstration of MARV and fair payment systems
Output 2.1 Improved Capacity to capture REDD elements within MARV
Output 2.3 Harmonized fair and equitable payment mechanism at provincial level
Output 2.2 Reference emissions level (REL) established
Compilation of information on existing payment systems
Analysis and review of benefits and constraints of existing payment systems
Formulation of options for modifications required to meet requirements of a REDD payment system
Stakeholder consultations on proposed modifications
Integration of modifications to create a REDD payment system
Pilot payment system with seed money
Training of staff of local institutions on application of modifications to the payment system

## Slide 12: 2: Successful provincial demonstration of MARV and fair payment systems
Output 2.1 Improved Capacity to capture REDD elements within MARV
Output 2.3 Harmonized fair and equitable payment mechanism at provincial level
Output 2.2 Reference emissions level (REL) established
Development and testing of the Priority Setting Toolkit
Training of provincial staff of BAPLA, BAPPEDA and others in its use;
Mapping of above- and below-ground carbon stocks inside and outside the Forest Estate at provincial level;
Overlay mapping to incorporate co-benefits into the planning products and produce GIS maps
Output 2.4 Toolkit for priority setting

## Slide 13: 3: Capacity established to implement REDD at decentralized levels
Output 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level
Identify areas of REDD-eligible forest
Analyse opportunity costs of alternative land uses
Mainstream REDD into existing spatial planning and forest utilization planning
Develop district based consensus on land – and forest use allocation
Approve the REDD mainstreamed spatial plan.

## Slide 14: 3: Capacity established to implement REDD at decentralized levels
Output 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level
Output 3.2 Empowered local stakeholders are able to benefit from REDD
Capacity needs assessment
Design of capacity building processes, including training programmes
Training of trainers
Conduct of training and other capacity building activities
Assessment of follow-up activities required to improve and sustain capacity

## Slide 15: 3: Capacity established to implement REDD at decentralized levels
Output 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level
Output 3.2 Empowered local stakeholders are able to benefit from REDD
Output 3.3 Multi-stakeholder-endorsed District plans for REDD implementation
Develop REDD implementation plans
Socialize REDD to stakeholders in districts