Agenda

- Non-cost extension requests

Action Points

- The NPWG cautioned regarding weather the Policy Board is fitted to define non-cost extensions

- The Secretariat will send the messages from the RC, Norway, Ibrahim to the National Programme working group members for background information (done)

- The Secretariat will circulate a background document  and proposed options by the next call

- The Secretariat should consult with Norway, MPTF, Ibrahim on the likelihood of approval of a potential inter-sessional decision if we decide to send one

- Tracking tool for NPs (Onye to join)

Action Points

- The NPWG welcomed the tracing tool and provided the following suggestions: Add a column for lead agency, implementation arrangement modality, column to put a tick for Secretariat received copy of the HACT micro-assessment from National Counterpart/s, Annual delivery rates??, correct the “T” missing in the column outcomes.  In addition it asked that the Secretariat looks into ways to automatise how to connect with data from the agencies

- The Secretariat will circulate a revised version by next call

- Inter-sessional decision on inviting Colombia to submit an NP

Action Points

- The Group agreed that the Secretariat will send the inter-sessional decision document to the Policy Board working group and they will decide if the table rating the countries should be attached or not.

- Targeted support requests

Action Points

- Regarding previous multi-agency targeted support requests, a letter was sent to Argentina as agreed by the NPWG

- The NPWG has asked the status of the letters on Mongolia and Bhutan. The Secretariat would report back after the call on the status of this letters

- South Sudan sent a very detailed proposal on MRV to FAO. Secretariat should expect a letter soon in addition to Cote d’Ivoire, and the Pacific Islands (FAO supported only)

- Reports from the mission to Bolivia and Viet Nam (Gabriel and Clea).

Action Points

- Gabriel provided a brief report on the mission to Bolivia, indicating that a draft report was produced. The mission was very complex but was well managed by the UN-REDD team leader. Substantive discussions were held, that were maintained in good terms. Several options were discussed. Regarding the conditions to implement, these have changed from when the Programme was approved and are now very difficult.  Bolivia would like to present their new mechanism to the PB. The NPWG concluded that the feasibility of the options that Bolivia proposed shall be weighted by the Mission team in accordance to the mission ToRs, as the decision on inviting Bolivia to submit or not a revised proposal to the Policy Board is a PB decision.

- Clea provided a brief report to the mission to Viet Nam (summarized in http://www.unredd.net/index.php?option=com_docman&task=doc_download&gid=7771&Itemid=53). UNEP indicated the need to receive information on the results and lessons learnt from Viet nam’s Phase 1. The Secretariat indicated that Viet Nam will submit a final report in September with that information.