Management Group (MG) of the UN-REDD Programme

Meeting Minutes of 12 April 2018

15h30 Geneva/Rome

Attendance:

MG members and alternates

FAO: Margo BuszkoBriggs

UNDP: Elspeth Halverson, Josep Garí

UNEP: Gabriel Labbate (and Florian Eisele for KM/Comms agenda item)

Secretariat: Mario Boccucci, Mihaela Secrieru

- KM/Comms Strategy & Workplan review

Decisions and Actions:

- The MG empowers the global KM/Comms Working Group to take decisions on strategic KM/comms issues (e.g. the focus of South-South exchanges, choice of impact stories, social media campaigns, etc.). Should the WG be unable to reach consensus, issues will be elevated to MG’s attention.

Additional elements of the discussion

The MG welcomed the revised documents shared by UN Environment on behalf of the KM/comms Working Group (see minutes of 13 March MG call) and all agreed to accelerate action towards the operationalisation of the 2018 work plan.

- TA/2019 Programming review

Decisions and Actions:

- MG members to provide pending debriefs on progress on and updates of the 2019 workplan and budget for countries and KM components by 16 April.

Done and shared with the Secretariat.

- Secretariat to prepare a consolidated narrative to present to the EB and share with the MG by 20 April.

Done and shared with the MG

- On potential small adjustments to TA/2019 workplan and budget, agencies will continue assessing demand from countries and will provide an update at the MG call on 15 May.

- Lower Mekong potential opportunity

Decisions and Actions:

- FAO to share the revised concept note prior to 24 April MG call.

- AOB: Update on Executive Board Informal Meeting

Decisions and Actions:

- Secretariat to confirm details of the meeting (tentatively 3rd May from 5:30pm for up to two hours plus voluntary dinner, outside the UNFCCC official area) and share updated concept note as soon as confirmation is received from last two pending countries.

Done and shared with MG.