Management Group (MG) of the UN-REDD Programme

Meeting Minutes of 9 October 2018 FINAL

15h30 Geneva/Rome

Attendance:

MG members and alternates

FAO: Margo BuszkoBriggs, Tiina Vahanen

UNDP: Elspeth Halverson, Josep Garí

UNEP: Gabriel Labbate

Secretariat: Mario Boccucci, Mihaela Secrieru

- EB2 Preparations

Decisions and Actions:

- Agencies to provide inputs to questions raised by Norway in their feedback to the 2019 workplan and budget. Secretariat to consolidate and respond to Norad – by 10 October

- Agencies and Secretariat to share draft PPTs for EB sessions – by 12 Oct

- FAO to share the pending Info Notes for their two KM sessions ASAP

- Pre-EB MG meeting in Rome on 17 October – PM, time to be defined

Additional elements of the discussion

The Secretariat reported back on main issues highlighted by Norad during the pre-EB check-in call (9 Oct, with Lars Andreas and Vania), for which MG members should be prepared to speak to during the EB, as follows:

- Remaining concern about financing overlapping/already-financed activities, pointing at activities carried-over from 2017/TA and asking to be reassured these are not overlapping with what is budgeted for 2019;

- Request for information and practical examples on how the Programme cooperates with other entities and/or initiatives to maximise synergies at country level (e.g. Colombia, Congo, Indonesia, Myanmar, Viet Nam), as well as on how we work together within UN-REDD at country level (e.g. Viet Nam: synergies being developed between TA, NP and potentially with the Lower Mekong initiative in the future.

- Request for updating the narrative accompanying the 2019/TA budget, in particular Colombia.

Agencies also agreed to build on momentum created by the joint article by Heads of Agencies with regards to the future of UN-REDD post-2020 by inserting references to the article and to the Programme’s 10 year anniversary in the Chairperson’s speaking notes, the Secretariat’s report of progress, minutes of the meeting, etc.