## Countries with NPs
| Partner countries with National Programmes | Expression of interest | Validation Meeting | NP approved | NP signed | NP in implementation | Member of FCPF | Co-financing (total amount US$) | Co-financing sources |  |  |  | Financial Implementation | [5 empty] | Programme Duration |  |  |  | Targeted support | Achievement of OUTCOMES (%) | Comments
# | [9 empty] | Lead Agency | Implementation modality | HACT microassessement on workspace | UN Agency | Approved Budget | Funds transfered | Expenditures | Delivery of approved budget % | Delivery of funds transfered % | Transfer of funds (from MPTF to Agencies) |  | End | % of duration covered to date
1 | Bolivia | 2008-09-25 | 2010-01-18 | 2010-03-18 | 2010-11-01 | ü | ü |  |  | UNDP |  |  | FAO | 1819000 | 515205 | 30909 | 1.699% | 5.999% | 2010-12-03 | 2012-10-22 | 2013-04-03 | 63.8%
[13 empty] | UNDP | 2889000 | 700850 | 51335.4 | 1.777% | 7.325%
[13 empty] | UNEP | *
[14 empty] | 4708000 | 1216055 | 82244.4 | 1.747% | 6.763%
2 | Cambodia | 2009-08-10 | 2010-09-30 | 2010-11-05 | 2011-05-01 | ü | ü | 930000 | FAO, UNDP | UNDP |  |  | FAO | 1300050 | 1300050 | 7736 | 0.5951% | 0.5951% | 2011-08-11 | 2012-10-22 | 2013-05-31 | 52.14%
[13 empty] | UNDP | 1551500 | 1551500 | 84843.26 | 5.468% | 5.468%
[13 empty] | UNEP | 149800 | 149800 | 0 | 0% | 0%
[14 empty] | 3001350 | 3001350 | 92579.26 | 3.085% | 3.085%
3 | DRC | 2008-09-18 | Initial: 30 Jan 2009 | Initial: 10-Mar-2009 | Initial: July 2009 | ü | ü | 90750000 | FIP/Banque Mondiale, CBF/BAD, FCPF/Banque Mondiale, WWF/CI/Forest Trends | UNDP
|  |  | Full: 19 Jan 2010 | Full: 18-Mar-2010 | Full: Oct 2010 | [7 empty] | FAO | 2926450 | 2926450 | 1107215 | 37.83% | 37.83% | 2010-11-01 | 2012-10-22 | 2013-05-30 | 82.87%
[13 empty] | UNDP | 3110690 | 3110690 | 3000826 | 96.47% | 96.47%
[13 empty] | UNEP | 1346060 | 1346060 | 1207427 | 89.7% | 89.7%
[14 empty] | 7383200 | 7383200 | 5315468 | 71.99% | 71.99%
4 | Ecuador | 2009-06-15 | 2011-02-15 | 2011-03-22 | 2011-10-28 | ü |  |  |  | FAO |  |  | FAO | 1576058 | 1576058 | 123687.41 | 7.848% | 7.848% | 2011-11-04 | 2012-10-22 | 2013-12-31 | 45.26%
[13 empty] | UNDP | 1575538 | 1575538 | 51310.78 | 3.257% | 3.257%
[13 empty] | UNEP | 848404 | 848404 | 104253.94 | 12.29% | 12.29%
[14 empty] | 4000000 | 4000000 | 279252.13 | 0.069813 | 6.981%
5 | Indonesia | 2008-07-01 | 2009-02-10 | 2009-03-10 | 2009-11-01 | ü | ü | 240000 | UNDP | UNDP |  |  | FAO | 1498000 | 1498000 | 1088680 | 72.68% | 72.68% | 2010-01-20 | 2012-10-22 | 2012-10-31 | 99.51%
[13 empty] | UNDP | 2996000 | 2996000 | 2379701 | 79.43% | 79.43%
[13 empty] | UNEP | 1150250 | 1150250 | 967315 | 84.1% | 84.1%
[14 empty] | 5644250 | 5644250 | 4435696 | 78.59% | 78.59%
6 | Nigeria | 2009-11-03 | 2011-02-21 | 2011-10-14 |  | √ |  |  |  | UNDP |  |  | FAO | 1130990 | 1130990 | 0 | 0% | 0% | 2012-09-06 | 2012-10-22 | 2015-02-28 | 5.111%
[13 empty] | UNDP | 2400350 | 2400350 | 0 | 0% | 0%
[13 empty] | UNEP | 468660 | 468660 | 0 | 0% | 0%
[14 empty] | 4000000 | 4000000 | 0 | 0% | 0%
7 | Panama | 2008-09-08 | 2009-10-13 | 2009-10-30 | 2010-10-01 | ü | ü |  |  | UNEP |  |  | FAO | 2189000 | 1679900 | 447218 | 20.43% | 26.62% | 2010-11-18 | 2012-10-22 | 2014-01-31 | 63.42%
[13 empty] | UNDP | 2067350 | 906290 | 225573 | 10.91% | 24.89%
[13 empty] | UNEP | 1043650 | 833530 | 481136 | 46.1% | 57.72%
[14 empty] | 5300000 | 3419720 | 1153927 | 21.77% | 33.74%
8 | Papua New Guinea | 2008-09-09 | 2010-09-22 | Initial : 10-Mar-2009 | 2011-05-01 | ü | ü | 261614 | UNDP CO PNG | FAO | [8 empty] | 2011-06-23 | 2012-10-22 | 2013-12-31 | 54.11%
|  |  |  | Full: 5-Nov-2010 | [8 empty] | FAO | 4520750 | 1666889 | 0 | 0% | 0%
[13 empty] | UNDP | 1707634 | 817501 | 141969.48 | 8.314% | 17.37%
[13 empty] | UNEP | 160500 | 107000 | 0 | 0% | 0%
[14 empty] | 6388884 | 2591390 | 141969.48 | 2.222% | 5.479%
9 | Paraguay | 2008-08-11 | 2010-06-25 | 5 Nov 2010 | 2011-07-01 | ü | ü |  |  | UNDP |  |  | FAO | 2190000 | 2190000 | 73746 | 3.367% | 3.367% | 2011-08-09 | 2012-10-22 | 2014-07-31 | 40.74%
[13 empty] | UNDP | 1490001 | 1490001 | 51342 | 3.446% | 3.446%
[13 empty] | UNEP | 1040000 | 1040000 | 98390 | 9.461% | 9.461%
[14 empty] | 4720001 | 4720001 | 223478 | 4.735% | 4.735%
10 | Philippines | 2010-01-22 | N/A | Initial: 5-Nov-2010 | 2011-07-01 | ü |  | 15000 | UNDP | FAO |  |  | FAO | 315650 | 315650 | 170051 | 53.87% | 53.87% | 2011-08-05 | 2012-10-22 | 2012-12-31 | 87.06%
[13 empty] | UNDP | 162950 | 162950 | 2067 | 1.268% | 1.268%
[13 empty] | UNEP | 21400 | 21400 | 0 | 0% | 0%
[14 empty] | 500000 | 500000 | 172118 | 34.42% | 34.42%
11 | Republic of Congo | 2009-02-11 |  | 25 –Mar-2012 |  |  | ü |  |  | UNDP |  |  | FAO | 1368262 | 0 | 0 | 0% | 0%
[13 empty] | UNDP | 1813188 | 0 | 0 | 0% | 0%
[13 empty] | UNEP | 818550 | 0 | 0 | 0% | 0%
[14 empty] | 4000000 | 0 | 0 | 0% | 0%
12 | Solomon Islands | 2009-11-13 | N/A | Initial: 5-Nov-2010 | 2011-05-01 | ü |  | 647700 | Solomon Islands Ministry of Environment Climate Change, Disaster Management and Teorplogy, Ministry of Forestry and Research, FAO, UNDP, SPC, GTZ, JICA | UNDP |  |  | FAO | [5 empty] | 2011-06-03 | 2012-10-22 | 2013-06-16 | 70.42%
[13 empty] | UNDP | 550000 | 550000 | 17333.36 | 0.031515 | 3.152%
UNEP
[14 empty] | 550000 | 550000 | 17333.36 | 0.031515 | 3.152%
13 | Tanzania | 2008-09-22 | 2009-02-24 | 2009-03-10 | 2009-12-01 | ü | ü | 244350 | UNDP CO Tanzania, FCPF/WBI | UNDP |  |  | FAO | 1498000 | 1498000 | 301132 | 20.1% | 20.1% | 2010-01-25 | 2012-10-22 | 2013-06-30 | 81.38%
[13 empty] | UNDP | 2568000 | 2568000 | 1193877 | 46.49% | 46.49%
[13 empty] | UNEP | 214000 | 214000 | 178425 | 83.38% | 83.38%
[14 empty] | 4280000 | 4280000 | 1673434 | 39.1% | 39.1%
14 | Sri Lanka | 2009-09-07 |  | 25 –Mar-2012 |  |  |  | 63000 | GTZ, SENSA, UNDP | FAO |  |  | FAO | 2578700 | 0 | 0 | 0% | 0%
[13 empty] | UNDP | 979050 | 0 | 0 | 0% | 0%
[13 empty] | UNEP | 442250 | 0 | 0 | 0% | 0%
[14 empty] | 4000000 | 0 | 0 | 0% | 0%
15 | Viet Nam | 2008-11-17 | 2009-01-22 | 2009-03-10 | 2009-08-01 | ü | ü |  |  | UNDP |  |  | FAO | 1690814 | 1690814 | 1667350 | 98.61% | 98.61% | 5.oct 2009 | 2012-10-22 | 2012-06-30 | 100.9%
[13 empty] | UNDP | 2501128 | 2501128 | 2463383 | 98.49% | 98.49%
[13 empty] | UNEP | 192814 | 192814 | 192376 | 99.77% | 99.77%
[14 empty] | 4384756 | 4384756 | 4323109 | 98.59% | 98.59%
16 | Zambia | 2008-08-05 | 2010-02-03 | 2010-03-18 | 9-Oct-10 | ü |  |  |  | UNDP |  |  | FAO | 2180000 | 1988247 | 772259 | 35.42% | 38.84% | 28.oct 2010 | 2012-10-22 | 2013-08-31 | 71.08%
[13 empty] | UNDP | 1995000 | 1353269 | 450671 | 22.59% | 33.3%
[13 empty] | UNEP | 315000 | 120005 | 0 | 0% | 0%
[14 empty] | 4490000 | 3461521 | 1222930 | 27.24% | 35.33%
Note on X1: Prydz: What information should be included? Agency? And which country? Amount?
Note on Y1: ikwu: suggestion to color code acheivements towards outcomes, green for acheived, yellow for on track, Red for off track)

## NP delivery vs duration
NATIONAL PROGRAMME DELIVERY
| BOLIVIA | CAMBODIA | DRC | ECUADOR | INDONESIA | NIGERIA | PANAMA | PNG | PARAGUAY | PHILIPPINES | REP.CONGO | S.ISLAND | TANZANIA | S. LANKA | VIETNAM | ZAMBIA
% Project duration covered | 63.8% | 52.14% | 82.87% | 45.26% | 99.51% | 5.111% | 63.42% | 54.11% | 40.74% | 87.06% | 0% | 70.42% | 81.38% | 0% | 100.9% | 71.08%
Delivery of approved budget (%) | 1.747% | 3.085% | 71.99% | 0.069813 | 78.59% | 0% | 21.77% | 2.222% | 4.735% | 34.42% | 0% | 3.152% | 39.1% | 0% | 98.59% | 27.24%
Delivery of funds transferred | 6.763% | 3.085% | 71.99% | 6.981% | 78.59% | 0% | 33.74% | 5.479% | 4.735% | 34.42% | 0% | 3.152% | 39.1% | 0% | 98.59% | 35.33%

## Overall NP delivery
NATIONAL PROGRAMME DELIVERY
| BOLIVIA | CAMBODIA | DRC | ECUADOR | INDONESIA | NIGERIA | PANAMA | PNG | PARAGUAY | PHILIPPINES | REP.CONGO | S.ISLAND | TANZANIA | S. LANKA | VIETNAM | ZAMBIA | TOTAL | Overall % Delivery
Approved budget | 4708000 | 3001350 | 7383200 | 4000000 | 5644250 | 4000000 | 5300000 | 6388884 | 4720001 | 500000 | 4000000 | 550000 | 4280000 | 4000000 | 4384756 | 4490000 | 67350441 | 28.41% | Expenditures divide by approved budget
Expenditure s | 82244.4 | 92579.26 | 5315468 | 279252.13 | 4435696 | 0 | 1153927 | 141969.48 | 223478 | 172118 | 0 | 17333.36 | 1673434 | 0 | 4323109 | 1222930 | 19133538.63
Funds transferred | 1216055 | 3001350 | 7383200 | 4000000 | 5644250 | 4000000 | 3419720 | 2591390 | 4720001 | 500000 | 0 | 550000 | 4280000 | 0 | 4384756 | 3461521 | 49152243 | 38.93% | Expenditures divide by funds transferred
Expenditure s | 82244.4 | 92579.26 | 5315468 | 279252.13 | 4435696 | 0 | 1153927 | 141969.48 | 223478 | 172118 | 0 | 17333.36 | 1673434 | 0 | 4323109 | 1222930 | 19133538.63
NATIONAL PROGRAMME DELIVERY
Amount
Approved budget | 67350441
Expenditures | 19133538.63
Funds transferred | 49152243
Expenditures | 19133538.63

## Expenditure by Country
NATIONAL PROGRAMME DELIVERY
DRC | 5315468
INDONESIA | 4435696
VIETNAM | 4323109
TANZANIA | 1673434
ZAMBIA | 1222930
PANAMA | 1153927
ECUADOR | 279252.13
PARAGUAY | 223478
PHILIPPINES | 172118
PNG | 141969.48
CAMBODIA | 92579.26
BOLIVIA | 82244.4
SOLOMON ISLAND | 17333.36
NIGERIA | 0
REP. CONGO | 0

## Other partner countries
# | Other partner Countries | Expression of interest | Missions | Member of FCPF | UN agencies co-financing | More info
1 | Argentina | 2009-09-08 |  | ü |  | Argentina Workspace page
2 | Bangladesh | 2010-03-24 | Aug 2010 : Programming |  | ü | Bangladesh Workspace page
July 2011: Scoping
January 2012: REDD+ roadmap consultation
3 | Benin | 2011-09-07 |  |  |  | Benin workspace page
4 | Bhutan | 2010-04-09 | Jun 2010: Programming |  | ü | Bhutan Workspace page
5 | Cameroon | 2011-07-05 |  | ü |  | Cameroon workspace page
6 | Central African Republic | 2010-04-29 |  | ü |  | CAR workspace page
7 | Chile | 2011-06-16 |  | ü |  | Chile workspace page
8 | Côte d’Ivoire | 2010-10-19 | March 2012: UNDP RTA support mission |  |  | CI Workspace page
9 | Costa Rica | 2009-12-03 |  | ü |  | Costa Rica Workspace page
10 | Colombia | 2010-04-09 |  | ü |  | Colombia Workspace page
11 | Ethiopia | 2011-04-15 |  | ü |  | Ethiopia Workspace page
12 | Gabon | 2010-07-09 | Oct 2010 : MRV | ü |  | Gabon workspace page
13 | Ghana | 2011-07-04 |  | ü |  | Ghana workspace page
14 | Honduras | 2011-05-05 |  | ü |  | Honduras Workspace page
15 | Guatemala | 2010-03-12 |  | ü |  | Guatemala workspace page
16 | Guyana | 2010-09-06 |  | ü |  | Guyana Workspace page
17 | Kenya | 2010-01-12 |  | ü |  | Kenya Workspace page
18 | Malaysia | 2012-01-20 |  |  |  | Malaysia country page
19 | Myanmar | 2011-09-23 | May 2011: REDD+ workshop |  |  | Myanmar workspace page
20 | Mexico | 2009-12-15 | Oct 2010: MRV | ü | ü | Mexico Workspace page
21 | Mongolia | 2011-04-15 | Mar 2011: Scoping mission |  | ü | Mongolia workspace page
Sept 2011: Tier 2 proposal
22 | Nepal | 2009-10-14 |  | ü |  | Nepal Workspace page
23 | Pakistan | 2011-04-18 |  |  |  | Pakistan Workspace page
24 | Peru | 2011-05-18 |  | ü |  | Peru Workspace page
25 | Sudan | 2009-12-23 | March 2012: support for REDD+ Strategy |  | ü | Sudan workspace page
26 | South Sudan | 2011-09-19 |  |  |  | South Sudan workspace page
27 | Suriname | 2011-09-30 |  | ü |  | Suriname workspace page
28 | Uganda | 2012-03-12 |  | ü |  | Uganda country page