## Countries with NPs
| Partner countries with National Programmes | Expression of interest | Validation Meeting | NP approved | NP signed | NP in implementation | Member of FCPF | Co-financing (total amount US$) | Co-financing sources |  |  |  | Financial Implementation | [5 empty] | Programme Duration |  |  |  | Targeted support | Achievement of OUTCOMES (%) | Comments
# | [9 empty] | Lead Agency | Implementation modality | HACT microassessement on workspace | UN Agency | Approved Budget | Funds transfered | Expenditures | Delivery of approved budget % | Delivery of funds transfered % | Transfer of funds (from MPTF to Agencies) | Up to Dec 2012 | End | % of duration covered to date/programme end date
1 | Bolivia | 2008-09-25 | 2010-01-18 | 2010-03-18 | 2010-11-01 | ü | ü |  |  | UNDP |  |  | FAO | 1819000 | 515205 | 42094 | 2.314% | 8.17% | 2010-12-03 | 2012-12-31 | 2013-11-09 | 72.29%
[13 empty] | UNDP | 2889000 | 700850 | 59500 | 2.06% | 8.49%
[13 empty] | UNEP | *
[14 empty] | 4708000 | 1216055 | 101594 | 2.158% | 8.354%
2 | Cambodia | 2009-08-10 | 2010-09-30 | 2010-11-05 | 2011-05-01 | ü | ü | 930000 | FAO, UNDP | UNDP |  |  | FAO | 1300050 | 1300050 | 111635.52 | 8.587% | 8.587% | 2011-08-11 | 2012-12-31 | 2014-12-31 | 41.66%
[13 empty] | UNDP | 1551500 | 1551500 | 373944 | 24.1% | 24.1%
[13 empty] | UNEP | 149800 | 149800 | 19628 | 13.1% | 13.1%
[14 empty] | 3001350 | 3001350 | 505207.52 | 16.83% | 16.83%
3 | DRC | 2008-09-18 | Initial: 30 Jan 2009 | Initial: 10-Mar-2009 | Initial: July 2009 | ü | ü | 90750000 | FIP/Banque Mondiale, CBF/BAD, FCPF/Banque Mondiale, WWF/CI/Forest Trends | UNDP
|  |  | Full: 19 Jan 2010 | Full: 18-Mar-2010 | Full: Oct 2010 | [7 empty] | FAO | 2926450 | 2926450 | 1650279 | 56.39% | 56.39% | 2009-06-23 | 2012-12-31 | 2013-12-31 | 79.1%
[13 empty] | UNDP | 3110690 | 3110690 | 3101125 | 99.69% | 99.69%
[13 empty] | UNEP | 1346060 | 1346060 | 1178921 | 87.58% | 87.58%
[14 empty] | 7383200 | 7383200 | 5930325 | 80.32% | 80.32%
4 | Ecuador | 2009-06-15 | 2011-02-15 | 2011-03-22 | 2011-10-28 | ü |  |  |  | FAO |  |  | FAO | 1576058 | 1576058 | 293468 | 18.62% | 18.62% | 2011-11-04 | 2012-12-31 | 2013-12-31 | 54.23%
[13 empty] | UNDP | 1575538 | 1575538 | 146424 | 9.294% | 9.294%
[13 empty] | UNEP | 848404 | 848404 | 341034 | 40.2% | 40.2%
[14 empty] | 4000000 | 4000000 | 780926 | 0.19523 | 19.52%
5 | Indonesia | 2008-07-01 | 2009-02-10 | 2009-03-10 | 2009-11-01 | ü | ü | 240000 | UNDP | UNDP |  |  | FAO | 1498000 | 1498000 | 1407878 | 93.98% | 93.98% | 2010-01-20 | 2012-12-31 | 2012-10-31 | 99.51% |  | completed
[13 empty] | UNDP | 2996000 | 2996000 | 2931787 | 97.86% | 97.86%
[13 empty] | UNEP | 1150250 | 1150250 | 1072285 | 93.22% | 93.22%
[14 empty] | 5644250 | 5644250 | 5411950 | 95.88% | 95.88%
6 | Nigeria | 2009-11-03 | 2011-02-21 | 2011-10-14 |  | √ |  |  |  | UNDP |  |  | FAO | 1130990 | 1130990 | 0 | 0% | 0% | 2012-09-06 | 2012-12-31 | 2015-02-28 | 12.89%
[13 empty] | UNDP | 2400350 | 2400350 | 45369 | 1.89% | 1.89%
[13 empty] | UNEP | 468660 | 468660 | 0 | 0% | 0%
[14 empty] | 4000000 | 4000000 | 45369 | 1.134% | 1.134%
7 | Panama | 2008-09-08 | 2009-10-13 | 2009-10-30 | 2010-10-01 | ü | ü |  |  | UNEP |  |  | FAO | 2189000 | 1679900 | 645630 | 29.49% | 38.43% | 2010-11-18 | 2012-12-31 | 2014-01-31 | 67.19%
[13 empty] | UNDP | 2067350 | 906290 | 442082 | 21.38% | 48.78%
[13 empty] | UNEP | 1043650 | 833530 | 785555 | 75.27% | 94.24%
[14 empty] | 5300000 | 3419720 | 1873267 | 35.34% | 54.78%
8 | Papua New Guinea | 2008-09-09 | 2010-09-22 | Initial : 10-Mar-2009 | 2011-05-01 | ü | ü | 261614 | UNDP CO PNG | FAO | [8 empty] | 2011-06-23 | 2012-12-31 | 2013-12-31 | 61.42%
|  |  |  | Full: 5-Nov-2010 | [8 empty] | FAO | 4520750 | 1666889 | 131312 | 2.905% | 7.878%
[13 empty] | UNDP | 1707634 | 817501 | 195510 | 11.45% | 23.92%
[13 empty] | UNEP | 160500 | 107000 | 0 | 0% | 0%
[14 empty] | 6388884 | 2591390 | 326822 | 5.115% | 12.61%
9 | Paraguay | 2008-08-11 | 2010-06-25 | 5 Nov 2010 | 2011-07-01 | ü | ü |  |  | UNDP |  |  | FAO | 2190000 | 2190000 | 140150 | 6.4% | 6.4% | 2011-08-09 | 2012-12-31 | 2014-07-31 | 48.95%
[13 empty] | UNDP | 1490001 | 1490001 | 132756 | 8.91% | 8.91%
[13 empty] | UNEP | 1040000 | 1040000 | 275012 | 26.44% | 26.44%
[14 empty] | 4720001 | 4720001 | 547918 | 11.61% | 11.61%
10 | Philippines | 2010-01-22 | N/A | Initial: 5-Nov-2010 | 2011-07-01 | ü |  | 15000 | UNDP | FAO |  |  | FAO | 315650 | 315650 | 139872 | 44.31% | 44.31% | 2011-08-05 | 2012-12-31 | 2013-04-30 | 81.59%
[13 empty] | UNDP | 162950 | 162950 | 102071 | 62.64% | 62.64%
[13 empty] | UNEP | 21400 | 21400 | 0 | 0% | 0%
[14 empty] | 500000 | 500000 | 241943 | 48.39% | 48.39%
11 | Republic of Congo | 2009-02-11 |  | 25 –Mar-2012 |  |  | ü |  |  | UNDP |  |  | FAO | 1368262 | 1368262 | 0 | 0% | 0% | 2012-11-23 | 2012-12-31 | 2015-10-30 | 3.595%
[13 empty] | UNDP | 1813188 | 1813188 | 0 | 0% | 0%
[13 empty] | UNEP | 818550 | 818550 | 0 | 0% | 0%
[14 empty] | 4000000 | 4000000 | 0 | 0% | 0%
12 | Solomon Islands | 2009-11-13 | N/A | Initial: 5-Nov-2010 | 2011-05-01 | ü |  | 647700 | Solomon Islands Ministry of Environment Climate Change, Disaster Management and Teorplogy, Ministry of Forestry and Research, FAO, UNDP, SPC, GTZ, JICA | UNDP |  |  | FAO | [5 empty] | 2011-06-03 | 2012-12-31 | 2014-03-31 | 56.74%
[13 empty] | UNDP | 550000 | 550000 | 121502 | 0.22091 | 22.09%
UNEP
[14 empty] | 550000 | 550000 | 121502 | 0.22091 | 22.09%
13 | Tanzania | 2008-09-22 | 2009-02-24 | 2009-03-10 | 2009-12-01 | ü | ü | 244350 | UNDP CO Tanzania, FCPF/WBI | UNDP |  |  | FAO | 1498000 | 1498000 | 493422 | 32.94% | 32.94% | 2010-01-25 | 2012-12-31 | 2013-06-30 | 86.67%
[13 empty] | UNDP | 2568000 | 2568000 | 1905126 | 74.19% | 74.19%
[13 empty] | UNEP | 214000 | 214000 | 193841 | 90.58% | 90.58%
[14 empty] | 4280000 | 4280000 | 2592389 | 60.57% | 60.57%
14 | Sri Lanka | 2009-09-07 |  | 25 –Mar-2012 |  |  |  | 63000 | GTZ, SENSA, UNDP | FAO |  |  | FAO | 2578700 | 2578700 | 0 | 0% | 0% | 2013-04-04 | 2012-12-31 | 2016-01-30 | 0%
[13 empty] | UNDP | 979050 | 979050 | 0 | 0% | 0%
[13 empty] | UNEP | 442250 | 442250 | 0 | 0% | 0%
[14 empty] | 4000000 | 4000000 | 0 | 0% | 0%
15 | Viet Nam | 2008-11-17 | 2009-01-22 | 2009-03-10 | 2009-08-01 | ü | ü |  |  | UNDP |  |  | FAO | 1690814 | 1690814 | 1622552 | 95.96% | 95.96% | 5.oct 2009 | 2012-12-31 | 2012-06-30 | 100.5% |  | Completed
[13 empty] | UNDP | 2501128 | 2501128 | 2435952 | 97.39% | 97.39%
[13 empty] | UNEP | 192814 | 192814 | 189183 | 98.12% | 98.12%
[14 empty] | 4384756 | 4384756 | 4247687 | 96.87% | 96.87%
16 | Zambia | 2008-08-05 | 2010-02-03 | 2010-03-18 | 9-Oct-10 | ü |  |  |  | UNDP |  |  | FAO | 2180000 | 1988247 | 1211486 | 55.57% | 60.93% | 28.oct 2010 | 2012-12-31 | 2013-08-31 | 77.94%
[13 empty] | UNDP | 1995000 | 1353269 | 668689 | 33.52% | 49.41%
[13 empty] | UNEP | 315000 | 120005 | 39055 | 12.4% | 32.54%
[14 empty] | 4490000 | 3461521 | 1919230 | 42.74% | 55.44%
Note on X1: Prydz: What information should be included? Agency? And which country? Amount?
Note on Y1: ikwu: suggestion to color code acheivements towards outcomes, green for acheived, yellow for on track, Red for off track)

## NP delivery vs duration
NATIONAL PROGRAMME DELIVERY
| BOLIVIA | CAMBODIA | DRC | ECUADOR | INDONESIA | NIGERIA | PANAMA | PNG | PARAGUAY | PHILIPPINES | REP.CONGO | S.ISLAND | TANZANIA | S. LANKA | VIETNAM | ZAMBIA
Project Lifespan | 72.29% | 41.66% | 79.1% | 54.23% | 99.51% | 12.89% | 67.19% | 61.42% | 48.95% | 81.59% | 3.595% | 56.74% | 86.67% | 0% | 100.5% | 77.94%
Budget spent/committed | 2.158% | 16.83% | 80.32% | 19.52% | 95.88% | 1.134% | 35.34% | 5.115% | 11.61% | 48.39% | 0% | 22.09% | 60.57% | 0% | 96.87% | 42.74%
Delivery of funds transferred | 8.354% | 16.83% | 80.32% | 19.52% | 95.88% | 1.134% | 54.78% | 12.61% | 11.61% | 48.39% | 0% | 22.09% | 60.57% | 0% | 96.87% | 55.44%

## Overall NP delivery
NATIONAL PROGRAMME DELIVERY
| BOLIVIA | CAMBODIA | DRC | ECUADOR | INDONESIA | NIGERIA | PANAMA | PNG | PARAGUAY | PHILIPPINES | REP.CONGO | S.ISLAND | TANZANIA | S. LANKA | VIETNAM | ZAMBIA | TOTAL | Overall % Delivery
Approved budget | 4708000 | 3001350 | 7383200 | 4000000 | 5644250 | 4000000 | 5300000 | 6388884 | 4720001 | 500000 | 4000000 | 550000 | 4280000 | 4000000 | 4384756 | 4490000 | 67350441 | 36.59% | Expenditures divide by approved budget
Expenditure s | 101594 | 505207.52 | 5930325 | 780926 | 5411950 | 45369 | 1873267 | 326822 | 547918 | 241943 | 0 | 121502 | 2592389 | 0 | 4247687 | 1919230 | 24646129.52
Funds transferred | 1216055 | 3001350 | 7383200 | 4000000 | 5644250 | 4000000 | 3419720 | 2591390 | 4720001 | 500000 | 4000000 | 550000 | 4280000 | 4000000 | 4384756 | 3461521 | 57152243 | 43.12% | Expenditures divide by funds transferred
Expenditure s | 101594 | 505207.52 | 5930325 | 780926 | 5411950 | 45369 | 1873267 | 326822 | 547918 | 241943 | 0 | 121502 | 2592389 | 0 | 4247687 | 1919230 | 24646129.52
NATIONAL PROGRAMME DELIVERY
Amount
Approved budget | 67350441
Expenditures | 24646129.52
Funds transferred | 57152243
Expenditures | 24646129.52

## Expenditure by Country
NATIONAL PROGRAMME DELIVERY
DRC | 5930325
INDONESIA | 5411950
VIETNAM | 4247687
TANZANIA | 2592389
ZAMBIA | 1919230
PANAMA | 1873267
ECUADOR | 780926
PARAGUAY | 547918
PHILIPPINES | 241943
PNG | 326822
CAMBODIA | 505207.52
BOLIVIA | 101594
SOLOMON ISLAND | 121502
NIGERIA | 45369
REP. CONGO | 0
SRI LANKA | 0

## Other partner countries
# | Other partner Countries | Expression of interest | Missions | Member of FCPF | UN agencies co-financing | More info
1 | Argentina | 2009-09-08 |  | ü |  | Argentina Workspace page
2 | Bangladesh | 2010-03-24 | Aug 2010 : Programming July 2011: Scoping January 2012: REDD+ roadmap consultation |  | ü | Bangladesh Workspace page
3 | Benin | 2011-09-07 |  |  |  | Benin workspace page
4 | Bhutan | 2010-04-09 | Jun 2010: Programming |  | ü | Bhutan Workspace page
5 | Cameroon | 2011-07-05 |  | ü |  | Cameroon workspace page
6 | Central African Republic | 2010-04-29 |  | ü |  | CAR workspace page
7 | Chile | 2011-06-16 |  | ü |  | Chile workspace page
8 | Colombia | 2010-04-09 |  | ü |  | Colombia Workspace page
9 | Costa Rica | 2009-12-03 |  | ü |  | Costa Rica Workspace page
10 | Côte d’Ivoire | 2010-10-19 | March 2012: UNDP RTA support mission |  |  | CI Workspace page
11 | Ethiopia | 2011-04-15 |  | ü |  | Ethiopia Workspace page
12 | Gabon | 2010-07-09 | Oct 2010 : MRV | ü |  | Gabon workspace page
13 | Ghana | 2011-07-04 |  | ü |  | Ghana workspace page
14 | Guatemala | 2010-03-12 |  | ü |  | Guatemala workspace page
15 | Guyana | 2010-09-06 |  | ü |  | Guyana Workspace page
16 | Honduras | 2011-05-05 |  | ü |  | Honduras Workspace page
17 | Kenya | 2010-01-12 |  | ü |  | Kenya Workspace page
18 | Lao PDR | 22.June 2012 |  |  |  | Lao PDR workspace page
19 | Malaysia | 2012-01-20 |  |  |  | Malaysia country page
20 | Mexico | 2009-12-15 | Oct 2010: MRV | ü | ü | Mexico Workspace page
21 | Mongolia | 2011-04-15 | Mar 2011: Scoping mission Sept 2011: Tier 2 proposal |  | ü | Mongolia workspace page
22 | Morrocco | 2012-05-29 |  |  |  | Morrocco workspace page
23 | Myanmar | 2011-09-23 | May 2011: REDD+ workshop |  |  | Myanmar workspace page
24 | Nepal | 2009-10-14 |  | ü |  | Nepal Workspace page
25 | Pakistan | 2011-04-18 |  |  |  | Pakistan Workspace page
26 | Peru | 2011-05-18 |  | ü |  | Peru Workspace page
27 | South Sudan | 2011-09-19 |  |  |  | South Sudan workspace page
28 | Sudan | 2009-12-23 | March 2012: support for REDD+ Strategy |  | ü | Sudan workspace page
29 | Suriname | 2011-09-30 |  | ü |  | Suriname workspace page
30 | Uganda | 2012-03-12 |  | ü |  | Uganda country page