## Slide 1: Suggestion for next steps for PGA for REDD+ in Vietnam

## Slide 2: A possible roll-out of the PGA
Identify and convene relevant stakeholders
Identify the priority areas to be assessed
Agree on indicators, data identification and methods of collection
Data collection and analysis
Data presentation and dissemination
Capacity building on how to act upon the findings of the PGA

## Slide 3: This is where we are now
Identify and convene relevant stakeholders
  Informal consultation with the STWG on Governance 21 November 2011
  National kick-off workshop 6 March 2012

## Slide 4: Next steps
Identify the priority areas to be assessed
Challenges
Criteria for selection of pilot province

## Slide 5: Some challenges to address:
Insufficient access to information, esp for local forest dependent communities on issues such as:
  On REDD generally
  Willingness of local authorities to make information available
  Technical knowledge on forest protection
Insufficient participation of relevant stakeholders at local level
  Lack of consultations in the allocation of forest land
  Gender perspective often missing
Not taking into account traditional knowledge
Decision-making is not consultative

## Slide 6: Possible Criteria for Pilot Province
Commitment and interest from local stakeholders
Province with REDD+ activities
Large forest coverage
Provinces with forest loss
Large presence of marginalised and vulnerable groups
Easily accessible

## Slide 7: Next steps
  2. Identify the priority areas to be assessed
  Establish Research Group and Advisory Groups guided by the inputs from today’s workshop by April 2012
  Do local stakeholder consultations in the selected pilot province to validate the exercise May 2012
Notes: We will contract a non-state actor to implement the PGA, use of existing expertise in the country.

## Slide 8: To be done in Q2-Q3 2012
Agree indicators, data identification and methods of collection
  Research Team & Advisory Team finalize a draft version of indicators by July 2012
  Local stakeholder consultation in the pilot province on the draft indicators by August 2012
  National stakeholder consultation on progress with the STWG on Governance by August 2012

## Slide 9
Data collection and analysis
Data collection in the pilot province conducted by Research Team by September 2012
Analyze data by October 2012

## Slide 10
5. Data presentation and dissemination
Share findings from the data analysis by December 2012

## Slide 11
6. Utilization of findings of the PGA
Training of both state and non-state actors on how to act upon the findings end of 2012 and forward
Use of findings to inform the National REDD+ Programme end of 2012 and forward

## Slide 12: Expand the PGA ??
Inclusion of other provinces ?
Refine methodology based on lessons learned from the pilot province ?
Expand indicators ?