NIGERIA PGA:

TRAINING ON GOVERNANCE INDICATORS AND INFORMATION SOURCES

Preparatory Note

I. BACKGROUND INFORMATION

What is a PGA?

Participatory Governance Assessment for REDD+ (PGA) is an inclusive and multi-stakeholder approach that a country can use to obtain robust, credible and actionable information on governance in areas relevant to REDD+. Its participatory process, owned by REDD+ stakeholders in the country, aims to ensure the relevance, credibility and legitimacy of the governance information obtained, and to serve as a mechanism for increased dialogue and accountability among stakeholders. The PGA is conceived as a first step in addressing governance challenges, by identifying and assessing them first, and producing recommendations, and eventually as a basis for policy reform.

PGA pilot countries

Nigeria is one of four pilot countries currently implementing a PGA process with support from the UN-REDD Programme. The other pilot countries are Ecuador, Vietnam and Indonesia, which are at various stages of implementation - Indonesia having finalized an entire PGA cycle, including the development of governance indicators, the collection and analysis of data, the launch of a major report on governance for REDD+, and national dialogue on follow-up on PGA recommendations.

Status of the Nigerian PGA process

In Nigeria, the decision to implement a PGA was based on the expressed need and political will to address governance issues for REDD+, governance being considered a high priority within the country's REDD preparedness process. The PGA process was engaged in late 2012, to be piloted within the Cross River State (CRS) before being extended to the rest of the country.

So far, the following steps have been taken:

1. In late 2012, a PGA research team was commissioned to undertake preliminary research in three pilot sites in CRS, on four aspects of governance: (1) Stakeholder analysis, (2) The private sector, (3) Traditional means of communication with local communities and (4) A mapping of governance issues relevant for the REDD+ process in CRS and at the national level.

2. In January 2013, a 3-day workshop in Calabar provided the opportunity for REDD+ stakeholders to reflect on the findings of the preliminary PGA research work and consider the next steps in the PGA process in Nigeria. The workshop also included a 1-day training on indicators. At this initial workshop, the following outcomes were achieved:

- The PGA Committee was constituted with 8 members representing different stakeholder categories (National State, CRS, organized civil society, academia and local communities).

- A management structure for the PGA was discussed and established.

- Key governance domains were identified for the PGA to deal with, and the following 4 domains were prioritized: (1) Broad and Informed Participation of REDD+ Stakeholders, (2) Harmonization of Policy and Legal Framework for REDD+, (3) Transparency & Accountability of the REDD+ Process and Finance, (4) Inter-governmental relations in REDD+ implementation.

- A draft set of indicators was developed for the 4 above-mentioned governance domains.

- A roadmap was drafted, outlining the agreed next steps for the PGA process in Nigeria.

3. After January 2013, the Nigerian PGA process experienced a period of delay due to a number of reasons, including certain capacity and administrative issues, which were eventually resolved through the recruitment of a Nigerian UN-REDD team by the end of 2013. In November 2013, a mission from the PGA global support team allowed to re-engage discussions on the PGA and its integration with the rest of the REDD+ work in Nigeria (in particular in relation with safeguards and the newly constituted Safeguards Taskforce), and to prepare for restarting PGA activities. In January 2014 the new PGA Coordinator took office, thus promising faster progress in the implementation of the remaining steps of the PGA process in 2014.

4. In February 2014, a 2-day working meeting of the PGA Committee allowed to re-activate the PGA process, take stock of achievements to date and plan the way forward. Participants included the PGA Committee members themselves as well as some members of the Safeguards Taskforce and some additional representatives from the Federal Ministry of Environment and the CRS Forestry Commission. At this meeting the following results were reached:

- The PGA roadmap was updated, reflecting a new timeframe and adjusted activities.

- A detailed PGA workplan for 2014 was elaborated.

- The PGA management structure was revised and agreed.

- The PGA Committee was effectively re-activated and agreed on further working processes.

- The draft set of governance indicators was reviewed, gaps were identified and suggestions for improvement were made.

- Stakeholder participation was discussed against the roadmap, and substantive inputs were provided on specific stakeholders to be involved at the different steps of the PGA process.

- The integration of the PGA process within the broader REDD+ work in Nigeria, including the safeguards work area, was discussed and established.

- Specific technical support needs from the UN-REDD agencies were identified - including further training on governance indicators and data collection methods. among other.

Demand for training on indicators and data collection methods

During the PGA planning meeting of February 2014, several participants expressed a clear demand for an additional training on indicators, to complement the 1-day training provided in January 2013, and build stronger and more specific capacity on governance indicators for the team that will lead and conduct the PGA work - namely essentially the PGA Committee and the PGA Research team. This request followed the review and analysis of the current draft indicator set during the workshop, through which participants realized that they required further knowledge and capacity in order to refine this draft indicator set and present it to local communities - so as to eventually get local communities' input and make the indicators more relevant to them. It was requested that this training is provided before any further PGA activities would be conducted, in particular before conducting the 3 local workshops scheduled in the workplan. Consequently, to avoid delaying the activities planned for 2014, it was recommended that this training should be provided as soon as possible and no later than the end of March 2014.

II. TRAINING OBJECTIVES

Based on the demand from the PGA Committee and other stakeholders present at the February 2014 PGA meeting, this training workshop has the following objectives:

- to further develop the specific knowledge and capacity of the PGA Committee members and the PGA research team on governance indicators and their sources of information (or data collection methods), so as to enable them to work on the PGA indicators and conduct the PGA process with adequate technical knowledge;

- to practically help the PGA Committee members and PGA research team revise and improve the draft indicator set currently available for the 4 priority governance domains identified, and start to identify data collection methods;

- to prepare the research team and other relevant PGA team members for the conduction of the local participatory workshops planned for April 2014 in the 3 pilot sites where local communities' inputs  on the indicators and data collection methods will be sought.

III. PARTICIPANTS

The participants in this training will be all the members of the PGA Committee and the PGA research team, as defined through previous agreements. The possibility of including additional participants, possibly from the Safeguards Task force or other REDD+ working areas as relevant, remains open.

IV. TRAINING STRATEGY AND ACTIVITIES

The training will take place over 3 to 4 days in a local area in Cross River State and consist of interactive technical presentations on governance indicators and their sources of information, practice-oriented training exercises and immediate application of the knowledge and skills acquired through working sessions on the real Nigerian PGA indicator set.

The training is proposed to be conducted by 2 specialists of the global UN-REDD/UNDP team, namely Danae Issa, specialist on participatory governance assessments, and Estelle Fach, specialist on anti-corruption (including anti-corruption assessments) for REDD+, with substantive technical contribution from Kristin Devalue from UN-REDD/FAO.

In order to meet the above-mentioned objectives, the following specific activities are suggested - which are further developed and organized in the detailed training agenda attached:

1. Introduction of training objectives and participants;

2. Putting the training in context: recap on the PGA approach, current status of PGA process in Nigeria, 2014 PGA workplan and next steps;

3. Technical presentations and practical sessions on governance indicators, including but not limited to the following:

- the specificities of governance indicators in comparison with other types of indicators;

- de jure vs. de facto indicators;

- quantitative vs. qualitative indicators;

- perception vs. experience-based indicators;

- disaggregated indicators/data vs. indices;

- gender-sensitive and pro-poor indicators;

- transparency, integrity and (anti-)corruption indicators;

- indicators on participation;

- the formulation of SMART indicators;

- examples of existing governance indicator sets from other countries;

-...

4. Technical presentations and practical sessions on sources of governance information and governance data collection methods, including:

- primary and secondary governance data;

- objective data, perception data and experience-based data;

- surveys, interviews, focus group discussions and other first-hand data collection methods;

- examples from other countries;

-...

Note: This training will include elements on data collection in order to start thinking about the methods that will be used to inform the 4 governance domains for which indicators are being elaborated. However, it will not go into detail about specific data collection methods nor data collection instruments development, as these will be the object of further training and technical support at a later stage of the PGA process, in the phase of preparation for data collection.

5. Working sessions to apply acquired knowledge and develop and improve the current draft governance indicator set, including:

- revising, reformulating, re-categorizing, removing or adding certain indicators;

- proposing and recommending data collection methods for each of the indicators.

6. Discussion on the possible actors of the operation and institutionalization of data collection, including the PGA research team members, national statistical institutes or other research institutes or academic organizations, civil society organizations etc.

7. Practical training sessions on information and participatory consultation workshop methodologies, practically applied to the PGA indicator set in order to prepare for the local workshops to be conducted.

EXPECTED OUTCOMES:

By the end of the workshop it is expected that:

- Participants are familiar with different types of governance indicators and data collection methods.

- Participants are able to formulate appropriate and relevant governance indicators as needed.

- The PGA indicator set is revised and a new, improved draft version is established.

- Data collection methods are identified for the indicators of the revised indicator set.

- Participants are prepared for conducting local participatory workshops to consult local communities on the PGA indicators and data collection methods.

- Participants are fully aware of the current status and steps of the PGA process in Nigeria, and of their specific responsibilities for implementing it.

V. PRACTICAL INFORMATION

Dates: 3 to 4 days between 24 and 28 March 2014

Location: Boje, Boki local governmennt area, Cross River State, Nigeria

VI. BUDGET:

See attached

Note: All travel and other costs for the 2 UN-REDD/UNDP specialists coming from abroad are to be covered by UN-REDD/UNDP HQ directly, and thus do not need to be included in this training budget.