## Slide 1
PGA MILESTONES 2014
1. Activate PGA Committee, review previous agreements, strategic planning of PGA process
2. Refine indicator set and select data collection methods
3. Finalize and validate indicator set and data collection methods
4. Prepare and train for data collection
5. Collect and analyze governance data
6. Validate findings
7. Draft, validate and publish PGA report
8. Communicate and promote the use of PGA information and recommendations
WHEN
HOW AND WITH WHOM
9. Institutionalize the PGA process to ensure its continuation and cylcic repetition over time
Feb
Mar
Apr
Jun
Jul-Aug
Oct
PGA Committee meeting in Calabar
Local workshops in 3 pilot sites
Broad participatory validation meeting in Calabar
Data collection training – State and local level
Local validation workshops in 3 pilot sites
Official public PGA report launch at international, national, State and local levels
Nov
Sep
Training on indicators in Calabar
May
Data collection in the 3 pilot sites
State-level validation workshop with broad participation in Calabar
Ongoing coordination with safeguards work / collaboration with Statistical Institute / other...