## PGA WP2014
PGA WORKPLAN 2014
MILESTONES | Activities | Responsibility | When | Deliverables
1. Activate PGA Committee, review previous agreements, strategic planning of PGA process | PGA Committee meeting in Calabar | PGA Coordinator | 19-20 Feb | Meeting conducted / meeting report
| Circulate meeting report and ouputs agreed at the meeting to all participants | PGA Coordinator | by 6 Mar | Meeting report circulated by email communications with attachments and hard copy
| Validation from PGA Committee members (electronic validation) | PGA Committee | by 13 Mar | Responses (comments or no objection) via email communication
2. Refine indicator set and select data collection methods | Training on indicators and data collection methods, followed by training on conduction of local workshops with local stakeholders | PGA Coordinator / UNDP | 3-4 days in the 3rd week of Mar | training conducted / training report
| (with possible participation from Indonesia) | UNDP
| local workshops in 3 pilot sites: | PGA Coordinator and SE specialist
| Workshop 1 in Mangrove site | support from local site coordinator | 4th week of Mar | workshop report 1 with inputs on indicators and data collection methods
| Workshop 2 in Ekuri site | support from local site coordinator | 1st week of Apr | workshop report 2 with inputs on indicators and data collection methods
| Workshop 3 in Mbe Mountain | support from local site coordinator | 2nd week of Apr | workshop report 3 with inputs on indicators and data collection methods
| Refine indicator set and data collection methods with inputs from the local workshops | PGA Research team | by last week of Apr | refined indicator set with data collection methods
3. Finalize and validate indicator set and data collection methods | Stakeholder validation meeting in Calabar | PGA Coordinator and SE specialist | 2nd week of May | meeting report
| Finalization of indicator set and data collection methods including inputs from validation workshop | Research team | 3rd week of May | final indicator set with data collection methods
| Validation of final indicator set and data collection methods (electronic validation) | PGA Committee | by end of May | final, validated indicator set with data collection methods
4. Prepare and train for data collection | Development of data collection instruments (questionnaires etc.) | Research team | end of May/1st week of June
| Validation of data collection instruments | PGA Committee | mid-June
| training trainers for data collection | supported by FAO | 3rd week of June
| (with possible participation by expert from Vietnam) | FAO
| Assemble data collection team | Research team leader | end of June
| Training local data collectors on site | Research team | 1st-2nd week of July
5. Collect and analyse governance data | Collect data on the field | Research team (possible outsourcing, to be decided) | mid-July to mid-August
| Analyze data and draft preliminary report | Research team | early September | preliminary report
6. Validate findings | organize local validation workshop in the 3 pilot sites | PGA Coordinator, SE specialist and Research team | 2nd and 3rd week of September
| Local validation workshop 1 in Mangrove site | support from local site coordinator
| Local validation workshop 2 in Ekuri site | support from local site coordinator
| Local validation workshop 3 in Mbe Mountain site | support from local site coordinator
| Integrate inputs from local workshop into the draft report | Research team | by end of September
7. Draft, validate and publish PGA report | State-level validation workshop in Calabar with broad stakeholder participation | PGA Coordinator and SE specialist | early October
| Integrate inputs from State-level validation workshop | Research team | by mid-October | report ready for publication by end of October
| Final validation of report (electronic validation) | PGA Committee | by 3rd week of October | report finalized
| Copy-editing and publication of report | PGA Coordinator | by end of October | report published
8. Communicate and promote the use of PGA information and recommendations | Official launch of PGA report: | PGA Coordinator and SE specialist | November | report launched officially
| National Report Launch |  | November | report launched officially at the State and national level
| International Report Launch |  | November | report launched and shared internationally
| State/local level report launch and sharing with local communities |  | tbd
| Development of communication strategy | SE specialist | starting in February
Other communication actions to be determined as the communication strategy is being developed
9. Institutionalize the PGA process to ensure its continuation and cylcic repetition over time | Coordination with Safeguards work to ensure integration of PGA results and indicator system in the future Safeguards Information System | PGA Coordinator | ongoing throughout the process
Other institutionalization actions to be further discussed and determined