## Slide 1
Session 5c:
An Update on Support to
Community-Based REDD+ (CBR+)
UN-REDD Policy Board
Lima, 8-9 July 2014

## Slide 2: Contents
Overview of CBR+
Progress since PB11
CBR+ Launch
Pilot Country Updates
  Cambodia
  DR Congo
  Nigeria
  Panama
  Paraguay
  Sri Lanka
Country Progress Summary
Notes: Welcome everyone to this first session of the day on CBR+.
The aim of this presentation is to give you an update on how CBR+ is progressing. As most of you know, CBR+ was approved at PB10 in Lombok, Indonesia a year ago, and was allocated $4 million from the generous contribution of Norway. I’m very pleased to update you on the great progress that has been happening to get this pioneering initiative off the ground over the last year, and the steps we and our regional and country colleagues have been taking since I last updated you at PB11 in Geneva last year.

## Slide 3: 1. Overview of CBR+
USD $4 million was allocated to CBR+ at PB 10
Grants up to $50,000 to support CBOs, NGOs, and indigenous peoples to participate in the design, implementation and monitoring of REDD+ readiness activities, while ensuring linkages to national REDD+ processes.
The vast majority of CBR+ funds (over 87%) are going directly to the country level to fund grants as well as support activities e.g. capacity building, outreach, knowledge management, M&E.
Co-financed by and implemented in partnership with the GEF Small Grants Programme.
Funded activities will align with national REDD+ strategies and priorities (e.g. UN-REDD National Programmes).
Notes: I’m eager to focus mainly on updates, but I’ll run through some key points about how CBR+ will work to refresh your memories. I also refer you to the Guidance Note on CBR+ that is available online in English, French and Spanish if you’d like more details.
USD $4 million was allocated to CBR+ at PB 10.
CBR+ will provide grant of up to $50,000 to communities, NGOs and indigenous peoples, to empower them to participate in the design, implementation and monitoring of REDD+ readiness activities, while ensuring linkages to national REDD+ processes.
It’s important to note that the vast majority of that four million (over 87 %) will go directly to the countries. That will fund direct grants to communities, as well as country level support activities e.g. capacity building, outreach, knowledge management, M&E etc.
CBR+ is being implemented in partnership with the GEF Small Grant Programme, who have decades of experience in delivering grants directly to communities in developing countries.
A crucial aspect of CBR+ is that community-level grants will complement ongoing national REDD+ processes and UN-REDD National Programmes.

## Slide 4: 1. Overview of CBR+ (cont’d)
CBR+ is being delivered by UNDP, using SGP’s existing country-based grants delivery mechanism
SGP National Coordinators
CBR+ National Steering Committees: Representatives from national REDD+ bodies/UN-REDD National Programmes/IP and CSO REDD+ platforms join the existing SGP National Steering Committees to form “CBR+ National Steering Committees”
CBR+ Country Plans: Being developed in each country to guide project selection and ensure link with national level work on REDD+ readiness
Notes: As a component is the Stakeholder Engagement work area, CBR+ is being delivered by UNDP. I am overseeing it on behalf of the UN-REDD Management Group, and we have two members of the UNDP UN-REDD team (Dearbhla Keegan and Nina Kantcheva) overseeing the day-to-day management of CBR+ at the global level.
At the country level, CBR+ is being managed by SGP’s National Coordinators (UNDP staff experienced in managing small grant processes at the country level), working closely with UN-REDD staff who are providing technical guidance and ensuring robust links to UN-REDD processes.
SGP National Steering Committees are already in place in SGP countries. For CBR+, these have been supplemented with REDD+ expertise from the National Programme steering committees and IP/CSO platforms to form CBR+ National Steering Committees. CBR+ NSCs will approve CBR+ Country Plans and will select grantees. The precise composition of each CBR+ NSC varies from country to country but they all have government, IP and CSO representation.
CBR+ Country Plans are currently being developed in each pilot country. These will outline the approach for selecting grant recipients in each country, and ensure that the CBR+ grants complement ongoing REDD+ processes.

## Slide 5: 2. Progress since PB11
6 pilot countries confirmed – implemented PB11 recommendation to review feasibility of Panama as a CBR+ pilot country
Coordination and co-financing arrangement with SGP developed
Discussion & consultation with national stakeholders (government, IP and CSO platforms, UNDP Country Office, UN-REDD colleagues)
CBR+ National Steering Committees formed
Work plans and budgets for each of the six pilot countries developed
Focus has been on building a strong programmatic and operational base for CBR+’s success
Notes: As per the recommendation of PB11, we assessed the feasibility of Panama being a pilot country and concluded that Panama would indeed be a suitable pilot country
At the global level we have been driving forward crucial preparatory activities that must be in place before CBR+ grants can be disbursed, including:
  Confirmation of the six pilot countries;
  Development of coordination and financial arrangements with GEF-SGP to deliver both grants and vital support activities such as monitoring and evaluation, knowledge management and outreach to community-level stakeholders. The working relationship with SGP has proved very productive so far – we are benefitting greatly from their decades of expertise in community grant-making and their on-the ground presence
  Discussion of CBR+ with national counterparts in government, IP and CSO REDD+ platforms, UNDP country offices, and regional UN-REDD colleagues in each of the pilot countries to ensure stakeholders are engaged in and supportive of CBR+
  Initiating processes to identify government, indigenous peoples and civil society stakeholders with REDD+ expertise to serve on the CBR+ National Steering Committees
Although these activities are not reflected in the expenditure of CBR+ funds (which you will note in the 2013 annual report are not yet spent), they are nonetheless absolutely crucial to the long term sustainability of CBR+ and the success of this new partnership with the GEF-SGP. It’s important to recognize that low expenditure on CBR+ during 2013 does not reflect a lack of progress: in fact the opposite is the case. A great deal of non-financial resources have been invested during the latter half of 2013 and the first half of 2014 to drive forward inception activities that will be critical to ensuring a defined programmatic support structure, and, at the country level, the engagement and ownership of stakeholders.
Because of this thorough preparation phase, we are now very well-placed to disburse grants before the end of 2014, with the support of stakeholders and strong coordination between UN-REDD and SGP personnel

## Slide 6: 3. CBR+ Launch
Global CBR+ Launch at United National Headquarters in New York, 14 May 2014, during the UN Permanent Forum on Indigenous Issues
Notes: We formally launched CBR+ at a reception during the UNPFII in New York in May. We were honoured to have some distinguishes colleagues and friend of the UN-REDD Programme join us – Kanyinke Sena – former UNPFII Chair and UN-REDD PB member; also Joan Carling, Secretary-General of the Asia Indigenous Peoples Pact.

## Slide 7: 4. Pilot Country Updates
Cambodia
DR Congo
Nigeria
Panama
Paraguay
Sri Lanka
Notes: These are the six pilot countries for CBR+: 2 per region, all with National Programmes.
Real variety among the 6 pilot countries:
  Each country faces different context, different challenges, so CBR+ is being implemented slightly differently in each country to take account of that
  For example, in some of these countries there was already a very strong connection and relationships between SGP and UN-REDD (e.g. in Paraguay where the SGP NSC and UN-REDD NSC overlapped almost entirely). In other countries this relationship is being established from scratch
  Some countries face specific challenges e.g. Panama where a change in government is in currently taking place – this is delaying the formation of the CBR+ NSC, as they wait for the government representative to be identified
Just to remind you how these pilot countries were selected:
  First narrowed down to only countries with both National Programmes, and SGP country programmes
  Determination of each country’s suitability for piloting CBR+ was made based on extensive discussion with SGP’s Country Programme Management Team, who consulted with SGP Country Teams. SGP advised on the capacity and resources of each SGP Country Programme. Selection was also based on extensive consultation with UN-REDD Regional Technical Advisors and Stakeholder Engagement Specialists, who also consulted their FAO and UNEP counterparts at regional and country levels. National Programme delivery rates were also taken into account.

## Slide 8: Cambodia
Stage | Status
Formation of CBR+ NSC | Complete (includes members from Ministry of Environment, Ministry of Forestry, IP and NGO reps from the REDD+ consultation group)
First meeting of CBR+ NSC | TBD – expected to take place the same week as PB12
CBR+ Country Plan | Expected September/October 2014 “Zero draft” CBR+ Country Plan is currently being developed
Consultations and validation of CBR+ Country Plan | Planned for October/November 2014 3 workshops will be held to receive inputs from stakeholders
Expected disbursal of grants | Call for proposals to be issued by December 2014
Notes: Four new members have been added to form the CBR+ NSC:
  H.E Chuop Paris, deputy Secretary-General of National Council for Green Growth (MoE);
  H.E Hout Bunnary, deputy General of MAFF;
  Mr. Chheurt Chhorn, IP representative to the REDD+ consultation group;
  Ms. Teng Rithiny, NGO representative to the REDD+ consultation group.
Agenda of the first CBR+ NSC meeting included:
  Introduction of the NSC CBR+ members;
  Introduction of the ToR of the NSC CBR+ (which have already been drafted);
  Discussion of CBR+ Country Plan development guidelines and reconfirmation of who will develop this Plan (grant v procurement);
  CBR+ activity plan for July-December 2014;
  Sharing of the CBR+ guidance note, which has been translated into Khmer.
A Zero draft of the CBR+ Country Plan has been developed by CO and UN-REDD staff, and is expected to be finalised in September/early October 2014, followed by consultations which will be carried out by an NGO;
Hope to issue a call for proposals before the end of 2014.

## Slide 9: Sri Lanka
Stage | Status
Formation of CBR+ NSC | Complete
First meeting of CBR+ NSC | Expected 10 July 2014
CBR+ Country Plan | An NGO or consultant will be recruited to develop the CBR+ Country Plan The approach will be confirmed at the first CBR+ NSC meeting
Consultations and validation of CBR+ Country Plan | Date TBD Will be carried out by the NGO or consultant developing the CBR+ Country Plan
Expected disbursal of grants | November/December 2014
Notes: The SGP NSC was briefed on CBR+ on 6 May. UN-REDD staff briefed the NSC on national level REDD+ work and on opportunities to link CBR+ to ongoing work.
On 22 May, Shireen briefed the national UN-REDD body on CBR+ and SGP.
Members for the CBR+ NSC have been nominated but there is currently some issues with the NGO representative having second thoughts about accepting the position as it would preclude his organization from receiving SGP funds. It is hoped that this will be cleared up and the first CBR+ NSC meeting will be held before 10 July.
A grant will be issued to an NGO or consultant to carry out the development of the CBR+ Country Plan, as well as outreach, KM and M&E. CBR+ NSC members need to OK this at the upcoming meeting. This NGO will be supported by a university that has expertise in REDD+.
Grants are expected to begin disbursing by November

## Slide 10: DR Congo
Stage | Status
Formation of CBR+ NSC | Expected by 15 July 2014 Nominations received – currently checking to ensure transparent process was followed
First meeting of CBR+ NSC | Date TBD
CBR+ Country Plan | Expected by September 2014 “Zero draft” is currently being developed. An NGO will be recruited to carry out stakeholder consultations and validation workshop. NGO recruitment is in process and will be completed by 28 July
Consultations and validation of CBR+ Country Plan | August/September 2014
Expected disbursal of grants | Before end of 2014
Notes: CBR+ NSC composition is in process - should be formed by 15 July
CSO representatives for the CBR+ NSC have been nominated. Ellen (REDD+ focal point in CO) of the UN- REDD CO team is checking if selection procedures were respected. She is also working with the government to select its representatives.
The Country Plan is being developed by a UN-REDD staff. The first draft is being examined for additional inputs.
An NGO will be recruited to carry out stakeholders’ consultations on the Plan and to carry out a stakeholder validation workshop.
It is hoped the NGO will be selected by July 28.

## Slide 11: Nigeria
Stage | Status
Formation of CBR+ NSC | Complete Includes CSO reps and government REDD+ experts
First meeting of CBR+ NSC | Planned for last week of July
CBR+ Country Plan | In process Key elements identified already, such as a focus on Cross River State area (to optimize synergies with the national REDD+ process' architecture) “Zero draft” is being developed by Nigeria REDD+ team with UN-REDD support
Consultations and validation of CBR+ Country Plan | Date TBD (likely in September)
Expected disbursal of grants | Before end of 2014
Notes: NSC is composed already – includes Edwin Usang and another CSO representatives; also Odigha Odigha – government representative from Cross River State
First CBR+ NSC meeting was planned for end of June but wanted to have a zero draft Plan first for the CBR+ NSC to review. First meeting now planned by first week of July - Expect substantial progress on CBR+ Country Plan after the first CBR+ NSC meeting
CBR+ will focus on Cross River State - currently many NGOs active with SGP in Cross River State, so we don’t envision any problem getting strong proposals
Should be able to disburse grants before December

## Slide 12: Panama CBR+ : Bosques de Vida
Stage | Status
Formation of CBR+ NSC | Expected within weeks - delayed due to change in government A multi-stakeholder CBR+ Technical Advisory Group has been formed and is moving forward with technical discussions
First meeting of CBR+ NSC | Expected within weeks As soon as government representative is confirmed
CBR+ Country Plan | Early September 2014
Consultations and validation of CBR+ Country Plan | October 2014 Consultation and validation will happen by October Outreach and capacity building for communities is also planned for November 2014
Expected disbursal of grants | December 2014
Notes: After discussion among various stakeholders in Panama, it was agreed to add the byline “Bosques de Vida” to CBR+’s name in Panama, in order to make the name more memorable and to give it more positive and locally-relevant associations
Panama has had a few unique challenges to deal with that are affecting CBR+’s progress:
  Sensitivities around the NP associated with last year’s complaint from IPs has resulted in the need to advance very carefully with CBR+
  A new President and government as of July 1
In response to these challenges, a slightly different approach has been taken:
  A Technical Advisory Group has been formed including government, IP, Afro-descendent, campesino and UNDP representatives. The TAG has already met and is pushing ahead with technical discussions and will present technical recommendations to the CBR+ NSC once it is formed.
CBR+ NSC should be formed in a few weeks after the change in government. First meeting will hopefully take place the week of 21 July.
It is hoped that the Plan will be validated in October, outreach and training for CBOs could happen in November.
It may be possible to issue a call for proposals, and possibly even select and approve some grants, by December 2014.

## Slide 13: Paraguay
Stage | Status
Formation of CBR+ NSC | Complete
First meeting of CBR+ NSC | Complete
CBR+ Country Plan | Expected September 2014 Will be drafted by the same consultant who is drafting the national REDD+ strategy
Consultations and validation of CBR+ Country Plan | September/October 2014 Local workshops will be held to consult on the CBR+ Country Plan and train communities to develop proposals
Expected disbursal of grants | Call for proposals in October/November 2014 Grants disbursed by December 2014
Notes: The CBR+ NSC has been formed and the first meeting has already taken place.
The CBR+ NSC consists of the 7 existing SGP NSC members with one additional member (INFONA). All existing SGP NSC members were already members of the UN-REDD Steering Committee and so it was only necessary to add this one more representative. Representatives of other organizations can be invited to join at a later date if needed. Current members include government, NGO, IPs and academia.
The Country Plan is being developed by a consultant who is also developing the national REDD+ strategy, and is expected to be ready by September. The consultant’s contract is being extended to allow for additional time to prepare the CP as well.
Local-level workshops will be held in strategic areas to consult on the Plan and also to build the capacity of communities.
Call for proposals expected in October/November (with capacity building workshops taking place concurrently). Will be ready to disburse grants by end of 2014.

## Slide 14: 5. Country Progress Summary
CBR+ NSCs formed in 3 out of 6 countries; rest to be formed before end of July
CBR+ Country Plans: zero drafts developed in 3 out of 6 countries; rest to be developed by August
Consultation and validation of Plans to be complete by September
All 6 pilots expect to deliver grants before end of 2014
Remaining grants funding from the pilot phase of CBR+ will be spent in early 2015
Notes: 3 countries have their CBR+ NSCs fully formed, and the remaining 3 are well on their way to having these committees formed by end of July
3 countries have “zero draft” of their CBR+ Country Plans in progress – Cambodia, DRC and Paraguay (these still need to be reviewed, consulted, validated and finalized)
Consultations and validation of CBR+ Country Plans should be complete by September/October
All 6 SGP National Coordinators are confident that they will disburse CBR+ grants before the end of 2014.
Remaining grants funding from the pilot phase of CBR+ will be spent in early 2015
We are hopeful that we can build on this progress and find ways to continue to support CBR+ into the future.

## Slide 15
Country | Start Date | Number of community projects funded | Total grant amount disbursed (US$)
Cambodia | 2004 | 177 | 6,721,646
Sri Lanka | 1994 | 371 | 7,695,888
DR Congo | 2009 | 73 | 2,473,399
Nigeria | 2009 | 110 | 3,394,869
Panama | 2005 | 121 | 2,719,704
Paraguay | 2009 | 22 | 583,840
Delivery by SGP Country Programmes
in the CBR+ pilot countries
Notes: The 6 CBR+ pilot countries were selected in part, based on the strength of their SGP Country Programmes, to ensure that CBR+ grants would be delivered quickly and effectively.
Between the 6 CBR+ pilot countries, their National Coordinators and country teams have delivered over 23.5 million dollars in grants to date, to support 874 community-level projects
Based on their past performance, as well as our very positive interactions with the SGP team at global level as well as in the 6 pilot countries, we share their confidence that the majority of CBR+ grants will be disbursed before the end of 2014, with the remainder to be disbursed in early 2015.

## Slide 16
Thank you.
For more information contact:
Charles McNeill charles.mcneill@undp.org