Priority Activities for the rest of 2013

| Outputs | Priority Activities |
| --- | --- |
| Outcome 1: Effective National Management of the REDD+ Readiness process and stakeholder engagement in accordance with the Roadmap principles |  |
| Output 1.1 National REDD+ Readiness Coordination Mechanism established | - Building Capacity of the REDD+ Taskforce (Visit to Vietnam in October) - Regular meetings of the Cambodia REDD+ Taskforce - Develop and Approved TOR of the REDD+ Taskforce |
| Output 1.2 Support to National REDD+ Readiness process | - Coordinate different REDD+ Readiness support project/programme in Cambodia (UN-REDD, Cam-REDD, FCPF REDD+ Readiness project) - Development of consolidated UNREDD – JICA TA team work plan on MRV |
| Output 1.3 Stakeholders are engaged in the REDD+ Readiness process | - IP selection process in the remain 8 provinces - Building Capacity of Consultation Group - Form Consultation Group - Building Capacity of Consultation Group - Develop consultation plan and implement |
| Output 1.4 Stakeholders provided with information on REDD+ and the National REDD+ Readiness process | - Assess and review the existing REDD+ Communication material - Provide training on REDD+ to different stakeholders at national and subnational |
| Outcome 2: Development of the National REDD+ Strategy and Implementation Framework. |  |
| Output 2.1 Development of individual REDD+ strategies and implementation modalities | - Monitor and Document: - FA project (Building the Awareness and Support of REDD+ Among the Forest-Dependent Communities in Siem Reap province) - FiA project (Conservation and reforestation of Flooded Forest and Mangrove to involve in Carbon emission prevention and Carbon stock) - GDANCP project (Support to the development of the National Protected Areas Strategic Management Plan) |
| Output 2.2 Evaluation of co-benefits | - Recruit International and National consultants - Field study and document - Meeting workshop to share and validate the findings |
| Output 2.3 Establishing REDD+ Fund mechanisms and Revenue sharing | - Establishment of Benefit-Sharing Technical Team - Recruit International and National consultants - Field study and document - Meeting/workshop to share and validate the findings |
| Output 2.4: Establishing REDD+ Fund mechanisms | - Concept note and TOR are developed but implementation considered through the FCPF program in 2014. |
| Output 2.5 Policy and legal development for the National REDD+ implementation framework | - Not priority and implementation considered through the FCPF program in 2014. |
| Output 2.6 Safeguards and monitoring of co-benefits | - Establishment of Safeguards Technical Team - National consultants - Field study and document - Meeting/workshop to share and validate safeguards |
| Outcome 3: Improved capacity to manage REDD+ at subnational levels |  |
| Output 3.1 Development of National REDD+ project guidelines and approval of funding for demonstration sites | - Establishment of Demonstration Technical Team - Development of guidelines - Ongoing monitoring of implementation by the Technical Team |
| Output 3.2 Pilot project activities | - Release grant - Collect pilot project reports |
| Outcome 4: Design of a Monitoring System and REL framework and capacity for implementation. |  |
| Output 4.1 Establishment National MRV/REL Technical Team and build appropriate national capacity | - Establishment of MRV/REL Technical Team - Assessment of the capacities for GDNACP, FiA and FA on MRV - Identification of adequate roles and functions for each entity or institution in the MRV system; - Identification of institutional arrangements to support MRV activities and data sharing |
| Output 4.2 Develop Cambodia Monitoring system plan | - Review of National Forest definition scenarios - Determine National Forest definition - Determine forest cover classification (workshop land classification) - Preparation of draft zero-forest map - Technical session to discuss carbon pools and reference period discussed with leading government institutions |
| Output 4.3 Review of the forest cover assessments to provide REDD+ activity data and design the satellite forest monitoring system | - Establishment of achieve containing index maps, satellite and aerial imageries for Cambodia; plan developed for integration into Cambodian REDD+ website. - Development of forest monitoring system processing chain scenario - Test monitoring system web platform development - One national consultation workshop on forest monitoring systems - Preparation of maps of forest cover change for discussion |
| Output 4.4 Design of a National Forest Inventory to develop emission and removal factors for REDD+ related activities | - Design of Multi-purpose National Forest Inventory design - Creation of archive of existing forest inventory data accessible to MRV team - Assessment of carbon stock and emission factors based existing data; list of identified missing emission factors; - Creation of database for GHG inventory with existing assessment data - Preparation of recommendations and costing for establishing new emission factors |
| Output 4.5 Support the development of a REDD+ related GHG Reporting System | - Not a priority for implementation, will be implemented in 2014 |
| Output 4.6 Support the development of Cambodia RL/REL framework | - Assessing the sources of and contribution of wood fuel use to current and projected future emissions - Quantitative assessment of drivers of forest degradation - Collate data on drivers of deforestation - Revision and finalization of REDD+ Roadmap land-use, forest policy and governance report - Assessment of national circumstances (preferably government institution contracted to prepare assessment of national circumstances ) |