Corruption risks in “MRV”

In the last session of the workshop, on 16 October, participants were split into groups and asked to reflect upon corruption risks using the different components of the PNRPS, using a set template and reflecting on who has the power/mandate, what is the abuse, and who benefits from it. Below is the unedited table submitted for the MRV components and activities of the PNRPS.

| Component and Key Activities | Corruption Risks – Means and Players | Likelihood | Effect | Conditions /factors enabling the potential corrupt practice | Interventions Needed |
| --- | --- | --- | --- | --- | --- |
| 5 – Measurable, Reportable and Verifiable (MRV) Conditions Key Activities: • Utilize appropriate MRV tools • Assess capacities and technologies to remotely measure changes in forest cover • Improve capacity to monitor emissions factors • Calculate emissions reference levels • Create business-as-usual and REDD-plus projections • Assume a phased approach to carbon MRV - Establish socioeconomic and environmental impact assessments - Establish financial review procedures | Government, LGU, tenure holders, CSO and academe may commit fraud in reporting data and information (misdeclaration or underestimation of baseline ) | 3 | Increase in carbon stock |  | - Third party verification and quality control even at the baselining stage - Strengthen the multisectoral MRV working group both at the national and field levels - Vigilance in application of MRV tools and protocols - Application of incentives and safeguards systems |
|  | over reporting of accomplishment | 2 | Increase in carbon stock |  |  |
|  | LGU/DENR may use abuse of discretion/favouritism by organizing of POs with members not eligible for tenure issuance which may later on receive the benefits from REDD plus | 2 | Actual PO beneficiaries will be deprived of the benefits from REDD plus |  | - Update inventory of forest occupants/communities - Review and strict enforcement of criteria and guidelines for PO formation, land tenure issuance and contracting |