UN-REDD Social & Environmental Principles & Criteria: Internal Work Plan

Aug 2011 – Mar 2012

| Actions | 2011 |  |  |  |  |  |  | 2012 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | LEAD | Aug | Sep | Oct | Nov | Dec | Jan |  | Feb | Mar |
| Tracking progress |  |  |  |  |  |  |  |  |  |  |
| 1. Review of work plan | All | 12 |  |  |  |  |  |  |  |  |
| Responding to comments and further development of P&C |  |  |  |  |  |  |  |  |  |  |
| 2a. Prepare new version of P&C in light of comments : - input 3 sets of responses & discuss differences - Redraft P&C themselves - Revise purpose statement; - Annex(es) on process to date and relationship with other documents/standards - Discuss b. sign off by UN-REDD agencies | a. (i) WCMC (LM/VK), UNDP (EH), (ii) UNEP (VK, LJM, JCG, WPS), UNDP (EH) (iii) WCMC (LJM), - UNDP (EH) - All; b. WPS, TC | 19 Drafts ii-iv 24 v. 26 | a. 4, b. 2 |  |  |  |  |  |  |  |
| 3. Submit next draft of P&C to PB 7 (including translation by Sect) | JCG (to check possibility of reviewing translations) |  | 5, docs posted 26 |  |  |  |  |  |  |  |
| 4. Consideration of P&C by PB 7 : request approval for further piloting by countries preparing NPs for submission at PB8 | RP, TC |  |  | 13-14 |  |  |  |  |  |  |
| 5. Public consultation period : both tool and P&C Using available events | JG to track Durban opportunities |  | (CBD consultation 21) Part’shp safeguard event 30? |  |  | Durban Forest day 18 |  |  |  |  |
| 6. Simultaneous circulation to PB members and observers, IAG and other independent reviewers b. Coordinate agreement on list of independent reviewers (between UNDP/UNEP/FAO) | a. TC via Secretariat, b. LM/ED |  |  |  |  |  |  |  |  |  |
| 7. Facilitated consultation & testing round 2, with specific countries (preparing new NPs) | Likely to be Sri Lanka, Rep Congo, Guatemala + others? |  |  |  |  |  |  |  |  |  |
| 8. Revision following testing & consultations, including Cambridge? Meeting in Jan |  |  |  |  |  |  | ?17-18 |  | ?5 |  |
| 9. Present to PB 8 for approval (alongside tool) |  |  |  |  |  |  |  |  |  |  |
| Tool development and piloting |  |  |  |  |  |  |  |  |  |  |
| 1. Agreement on common format inc guidance | LM, UNDP |  | 5 |  |  |  |  |  |  |  |
| 2. a. Develop content with input from regional and national teams | LM, UNDP (AK) |  |  |  |  |  |  |  |  |  |
| 3. Prepare introduction and supporting material | LM, EH |  |  |  |  |  |  |  |  |  |
| 4. Consolidate and check for consistency | JCG |  |  |  |  |  |  |  |  |  |
| 5. Version 1 to review & testing (along with P&C) |  |  |  |  |  | 18 |  |  |  |  |
| 6. Revision (as for P&C) |  |  |  |  |  |  |  |  | ?5 |  |
| 7. Present to PB 8 (alongside P&C) |  |  |  |  |  |  |  |  |  |  |