Activities and Workplan

| Result | Activity | Output and timeframe | UN Agency | Responsible party | Indicator(s) of success/impact | Funds – from UN-REDD) | Co- financing (amount and source) | Budget breakdown |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Category | Amount |
| Stakeholders provided with information, and awareness raised on REDD+ through various means of communications (including videos, posters, brochures, TV/radio programmes, etc.) | Design and delivery of awareness raising events at national and sub-national level | By March, 2015, a series of sub-national concert events held By September 2014, at least two additional awareness raising events for the general public designed and delivered | UNDP | RTS | By the end of 2016, average awareness raised by specified amounts over baseline values, especially for the stakeholder groups having the lowest awareness in 2013. Baseline (average score of respondents to awareness survey; lowest 5 groups): Community Forests: 59% Community PAs: 65% Indigenous Peoples: 72% Community Fisheries: 76% Targets: Community Forests: 70% Community PAs: 73% Indigenous Peoples: 80% Community Fisheries: 83% | 40,000 | N/A | Personnel | 15,000 |
|  |  |  |  |  |  |  |  | Supplies etc. | 8,000 |
|  |  |  |  |  |  |  |  | Contracts | 17,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 0 |
| Women are effectively included into management of the REDD+ readiness process | Support to the newly established “Gender Team” | From June 2014 onwards, a functioning Gender Team is able to review and endorse all documents being prepared for presentation to the Taskforce | UNDP | RTS | By March 2015, the draft National REDD+ strategy adequately reflects gender perspectives Baseline: There is no process to ensure the incorporation of gender perspectives Target: From June 2014 onwards, all documents submitted to the Taskforce for policy decisions have been endorsed by the Gender Team | 25,000 | N/A | Personnel | 15,000 |
|  |  |  |  |  |  |  |  | Supplies etc. | 5,000 |
|  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 0 |
|  | Total |  |  |  |  | 65,000 | - |  |  |