Minutes of the meeting of the SEPC working group - 27 Jun. 12

Present:

UN-REDD secretariat: Clea Paz (CP)
UNDP: Leo Peskett (LP)
UNEP: Julie Greenwalt (JG)
UNEP-WCMC: Lera Miles (LM), Lucy Goodman (LG), Blaise Bodin (BB)

FAO: Emelyne Chemey (EC)

Action points:

- SEPC working group to review the National Programmes Reporting Templates. Changes could be proposed, noting they would not be incorporated prior to PB 9

- SEPC working group to get agreement on the summary information note here prior to COB 4 July, it could be reduced to one page.  It should state the aims and programme of work of the SEPC working group, and be circulated to

  - The Monitoring and Information Working group (to be circulated prior to coordination call)

  - The National Programme Working Group

  - The Management Group

- For the SEPC/Cancun alignment document, EC and LG to summarise the relationship between the SEPC and the Cancun safeguards, and reduce the international provisions to only those that are directly linked. SEPC working group to comment on the draft here by COB 4 July (noting Leo and Lera have already commented)

- How to publish the SEPC/Cancun document, and how to recognise the UN-REDD decision on taking into account the UNFCCC, to be discussed on a future call

Agenda

- Briefing from Clea on the National Programme Cycle.

- Discuss draft 1 pager on proposed SEPC support to the UN-REDD Programme for the National Programme Working Group

- Send summary document to Co-ordination Group? (action 6 of Rome meeting)

- Inputs from and linkages to other UN-REDD work

- SEPC/Cancun alignment document drafted by UNEP-WCMC and FAO (action 10 of Rome meeting)

- How to publish SEPC/Cancun alignment document

- AOB

Minutes:

Briefing from Clea on the National Programme Cycle.

CP emphasized the different stages at which countries are in their National Programmes, highlighting that it is unlikely new countries will added next year.  SEPC support to the implementation phase is therefore more pertinent than SEPC support to the scoping phase.

CP then summarised the current references to safeguards in National Programme documentation.  The group spent some time discussing the semi-annual, annual and final reporting templates, the relevant content of which had not been recently reviewed by many on the call.

Proposed SEPC support to the UN-REDD Programme for the National Programme Working Group (action 6 of Rome meeting)

It was decided this document will update the following on the SEPC Working Group’s planned activities:

- the Management Group

- the Management and Information Working Group

- the National Programme Working Group

Comments on the draft are invited by COB 4 July, noting that the SEPC working group will aim to submit this before the Monitoring and Information Working group’s videoconference call on the 6 July.

SEPC/Cancun alignment document drafted by UNEP-WCMC and FAO (action 10 of Rome meeting)

LP & LM were both concerned that the length of the current table obscured the message of alignment with the SEPC and suggested a summary, either in narrative or tabular form, at the beginning of the document.  It was noted that every criteria was covered by relevant international agreements, and that this point could be concisely made in the introduction.

There was further discussion on what the UN-REDD decision on going beyond the UNFCCC might be.

AOB

The working group was established as a collaboration between UNDP and UNEP, and that FAO was subsequently invited to join.