## Slide 1
INTEGRATED LAND-USE ASSESSMENT (ILUA) PHASE II
AN OVERVIEW
Bwalya Chendauka
National Coordinator
2011
REPUBLIC OF ZAMBIA

## Slide 2: Outline of 2011 ILUA II work plan presentation ===============================
Brief Background
Expected outcome of ILUA II
Outputs of ILUA II
Project Coordination (Implementation structure)
Multi-sectoral Technical Committee
Budget for year one of ILUA II
Work plan activities and timeline/output
Linkages of ILUA II and UN-REDD

## Slide 3: Brief Background of ILUA I ===============================
Between 2005 to 2008, Zambia implemented ILUA through the MTENR-Forestry Department
ILUA was the first of its kind, included both biophysical and livelihood aspects
The ILUA approach offered the possibilities of analysing land management as whole
Also marked the beginning of a collaborative effort

## Slide 4: Brief background cont../ ==============================
The 2005 to 2008 ILUA is now referred to as ILUA I which generated largely base line data
ILUA II (2010- 2013) is a continuation and aims at enhancing the use and development of data towards Sustainable Forest Management
ILUA II is also expected to address data collection needs for more REDD pertinent parameters including carbon pools

## Slide 5: Expected Outcome of ILUA II ==============================
‘strengthened capacity in planning and implementation of Sustainable Forest Management (SFM) and REDD through better information capacity building, dissemination of information and improved multi-sectoral dialogue’.

## Slide 6: Outputs of ILUA II ==============================
Output 1: Effective means of dissemination and utilization of the information for multi-sector dialogue
Output 2: improved methodological and human capacity in collecting and analyzing forest resource information for SFM, REDD monitoring and carbon inventory
Output 3: Implementation of ILUA II Mapping and Field Survey.

## Slide 7: Project Coordination ===========================

## Slide 8: Multi- Sectoral Technical Committee ==============================
MTENR will use the Technical Committee (TC) composed of experts from different sectors with linkage to information provided by ILUA.
Technical Committee is divided into three thematic areas(working groups):
Dissemination of information,
Forest and carbon assessment, and
Remote sensing and mapping.
The responsibility of TC will be to oversee and provide necessary requested technical input in the implementation of the project activities.
TC is be composed of representatives from all main stakeholder organizations.

## Slide 9: Budget for year one of ILUA II ===============================

## Slide 10: 2011 work plan activities ===============================
The Project Document covers the first two years of 11/2010-10/2012.
Activities for 11/2012-10/2014 will be planned during the first 18 months of the project.
The Work Plan for the first year is presented next.

## Slide 11: Activities - mobilization ==============================

## Slide 12: Activities - Output 1 =============================

## Slide 13: Activities -Output 2 ===========================

## Slide 14: Complimentarity of ILUA II and UN-REDD ===============================

## Slide 15: Complimentarity of ILUA II UN-REDD - Output 1 ==============================

## Slide 16: Linkages between ILUA II and UN-REDD, Output 2 ==============================

## Slide 17
THANK YOU !