### Nigeria REDD+ Participatory Governance Assessment (PGA) Research Teach

### Terms of reference

Background

The Federal Government of Nigeria joined the UNREDD Programme in 2010, and submitted a national REDD+ readiness programme in March 2011. The Nigeria REDD+ Readiness Programme envisions a two-track approach to achieve REDD+ readiness in Nigeria, with the development of institutional and technical capacities at Federal level and, simultaneously, carrying out intense institutional, strategy-building and demonstration activities in Cross River State.  It is envisioned that state-level progress will in turn inform the national process and guide pragmatically other states interested in REDD+.

Cross River State has been retained as the pioneer state to serve as a ‘demonstration model’ because of its political leadership and manifest engagement in forest conservation and in exploring the REDD+ mechanism, as well as for its major potential for emissions reduction from the forest sector given that it hosts over 50% of the country’s high tropical forests.

For the REDD+ community, assessing and enhancing the governance of the forest sector and of the REDD+ mechanism itself is now considered equally important as the system designed to monitor carbon. Broadly speaking, governance data for REDD+ is needed to identify the drivers of deforestation and forest degradation, to help design appropriate interventions to tackle these drivers, and to assess and review the effects of these interventions. More specifically, a national governance information system for REDD+ could disseminate data on REDD+ funding received as well as revenue distribution, cases tried in court, level of perceived corruption, etc. Such information-sharing systems can provide a critical accountability mechanism if the data generated is deemed robust and credible, if indicators are chosen so as to truly reflect and address citizens’ concerns and interests, and if this information is acted upon.

For governments to be able to provide credible information on the national REDD+ process, and more specifically on how governance and social safeguards are promoted, addressed and respected, mutual trust in how this information is prepared and mutual appreciation of the relevance of this information is crucial. A Participatory Governance Assessment (PGA) is a valuable tool to build such information systems and to prepare the grounds for effective safeguards. PGAs for REDD+ emphasize the inclusion of various stakeholders (government officials, civil society actors, forest-dependent communities, oversight institutions and the media, among others) from the very beginning of the process to ensure that there is a broad-based agreement on the governance indicator framework developed and on the methodology used to collect data.

As a diagnostic tool, the PGA in Nigeria will help achieve the following objectives:

- To assess the existence and implementation of adequate policies and legislations necessary for the effective implementation of REDD+ and more generally, for the sustainable management of forests;

- To assess the institutional capacity of government agencies at federal, state and local levels to implement the REDD+ Programme and sustainable forest management (SFM) policies;

- To assess the existence and effectiveness of an anti-corruption strategy specifically designed for REDD+;

- To assess the existence and effectiveness of mechanisms established for meaningful participation by forest-dependent communities in the implementation of REDD+;

- To assess the existence and implementation of the benefit distribution system for REDD+ in terms of its transparency and fairness in distribution of benefits to the concerned stakeholders.

Overall mandate & constitution of the PGA Research Team

A national-level “PGA Research Team” will be responsible for designing the PGA methodology, in close consultation with the two Governance Working Groups at both Federal and CRS levels.

This Research Team will be constituted by 3 to 4 experts from universities, independent research institutions as well as from representatives from CSOs with relevant research skills (see recruitment qualifications below).

Specific functions & deliverables of the PGA Research Team

- Developing the PGA methodology & the data collection strategy for the first pilot in Cross River State:

- Assist with the organization of the first PGA workshop on indicators and data collection methods planned for mid-October 2012, as necessary;

- As a technical input to the first PGA workshop, map existing data sources relevant to the set of priority REDD+ governance issues;

- Participate in the training workshop as resource persons and facilitators, as necessary;

- Based on the priority REDD+ governance issues agreed upon at the first PGA workshop, and based on the initial recommendations made to the Research Team during this workshop (with regards to the PGA framework, indicator types, possible data sources, data collection methodologies, etc.),  develop a first draft of a PGA methodology (to  be piloted in Cross River State), including a PGA indicator framework and a data collection strategy (by end of October 2012);

- Facilitate consultations at both Federal and CRS levels to seek feedback on the draft indicator framework and the proposed data collection strategy; consultations will be held with both Federal-level and CRS-level Governance Working Groups, as well as with local communities and key stakeholders in Cross River State (first week of November);

- Finalize the PGA indicator framework and the data collection methodology as per the feedback received from the stakeholder consultations held at both Federal and CRS levels, as well as from UNDP and FAO (second week of November);

- Develop data collection instruments (survey questionnaires, guides for focus group discussions, administrative data collection forms, etc.) in line with the revised methodology (second week of November).

- Coordinate the test-run of the PGA methodology in Cross River State (mid-November until end of November):

- Coordinate the test-run of the PGA methodology in selected sites of CRS;

- Identify suitable data collectors and provide them with necessary training prior to the test-run.

- Process data from the test-run and present recommendations for fine-tuning the methodology before rolling it out across CRS (first two weeks of December):

- Make some recommendations (both operational and methodological) based on the test-run to improve the PGA methodology and the data collection process before its roll-out across CRS;

- Consult with the two GWG (at Federal & CRS levels), as well as with UNDP & FAO, to seek their feedback on the recommendations;

- Finalize the PGA methodology based on the feedback received.

- Coordinate overall data collection activities across Cross River State during PGA roll-out (January 2013)

- Identify suitable data collectors and provide them with necessary training;

- Coordinate overall data collection activities across CRS.

- Draft PGA report and formulate recommendations on the replicability of the PGA methodology in other REDD+ candidate states (February 2013):

- Prepare a first draft of the PGA report that includes a description of the methodology & data collection strategy, data analysis and recommendations based on the findings;

- Seek comments and feedback on this first draft from the two GWG (at both Federal and CRS levels), as well as from UNDP & FAO, and revise the report accordingly;

- Organize a workshop in CRS to present the findings to CRS stakeholders and to seek their feedback;

- Finalize the report as per the feedback received from the stakeholder workshop held in CRS

- Integrate in the report a section providing recommendations on the replicability of the PGA methodology in other REDD+ candidate states.

Recruitment qualifications:

This Research Team will be constituted by 3 to 4 experts from universities, independent research institutions as well as from representatives from CSOs with relevant research skills.

The following recruitment qualifications can be used to guide the selection process:

- Master in Law, Political Sciences, Social sciences or other relevant disciplines.

- Demonstrated expertise, work experience or research specialization in the areas of governance, forest policy, forest governance, public policy, community empowerment, REDD+, climate change, corruption, etc.