## Secretariat Workplan
UN-REDD SECRETARIAT 2010 ANNUAL WORKPLAN
Key Results | Activities | Timeframe |  |  |  | Main Responsible Staff | Indicators
|  | Q1 | Q2 | Q3 | Q4
1.Programme strategy developed | [5 empty] | Yemi
| 1. Coordinate and finalise the strategy development |  | x |  |  | Yemi
2. Two Policy board meetings organized - March & November | [5 empty] | Yemi/Tiina
| 1. Overview and coordination | x |  |  | x | Yemi
| 2. Plan and implement practical arrangements | x |  | x |  | Reem
| 3. Travel and budget | x |  | x |  | Onye/Reem
| 4. Coordinate substantive document preparation and the report | x |  | x | x | Tiina
3. Resource mobilization strategy, work plan and budget developed & implemented | [5 empty] | Yemi
| 1. Coordinate resource mobilization and donor contacts |  | x | x | x | Yemi
| Develop business plan for Programme based on strategy |  |  | x |  | Onye/Yemi/Tiina
| 2. UN-REDD budget and work plan | x | x |  | x | Tiina
| 3. Support the Tier-2 process |  |  | x | x | Linda
4. Global Programme effectively coordinated | [5 empty] | Tiina
| 1. Coordinate agencies support for Global Programme development, implementation and monitoring, including the internal GP working group | x | x | x | x | Tiina
| 2. Organize/contribute to workshops on methodological guidance and lessons learned, coordinate the GP website and workspace content, and review technical papers |  | x |  | x | Linda
| 3. Provide information for communication and knowledge sharing tools | x | x | x | x | Linda/Cheryl
| 4. Prepare GP documentation including submission forms for the Policy Board |  | x |  | x | Tiina/Onye
5. National Programmes effectively coordinated | [5 empty] | Clea
| 1. Coordinate agencies support for National Programme (NP) development, implementation and monitoring, including the internal NP working group | x | x | x | x | Clea
| 2. Provide NPs information on NP implementation progress to communications and knowledge sharing tools (website, communication materials, and workspace) | x | x | x | x | Clea/Cheryl
| 3. Coordinate the revision of criteria, forms, templates, submission form and the review process (agencies, secretariat and independent technical review) for NPs |  | x | x |  | Clea
| 4. Participate in efforts to develop a common delivery platform (and its different elements) with FCPF and other partners |  | x | x |  | Clea/Tiina
| 5. Prepare documentation including NP submission forms for the PB meeting | x |  | x |  | Clea/Onye
| 6. Develop National Programme implementation guidelines and framework for assessing impact |  |  | x | x | Clea
6. Communications and knowledge management | [5 empty] | Yemi
| 1. Finalize communications strategy to compliment Programme strategy,develop communication pieces to support strategic activities and coordinate the internal working group on communications | x | x | x | x | Cheryl
| 2. Organize communications activities at the Policy Board and strategic events |  | x | x | x | Cheryl/Reem
| 3. Coordinate support to events and organize side events, including the internal working group on events | x | x | x | x | Reem
| 5. Coordinate the content and improvement of website, workspace and Newsletter |  | x | x | x | Cheryl
| 6. Finalize and support the implementation of the disclosure policy |  | x | x |  | Cheryl
| 7. Coordinate prepartion of year in review |  |  |  |  | Cheryl
7. Quality assurance provided for the programme | [5 empty] | Yemi/Tiina
| 1. Ensure the workflow and manage the preparation of finance administration and related reports |  | x |  | x | Onye
| 2. Coordinate with the MDTF on administrative & organizational matters | x | x | x | x | Onye/Tiina
| 3. Support the establishment of financial monitoring and evaluation |  | x | x | x | Onye
| 4. Coordinate the establishment of the Project Tracker |  | x | x |  | Linda/Onye
8. Internal/external relations & partnerships coordinated | [5 empty] | Yemi
| 1. Coordinate meetings & collaboration with the FCPF, FIP, other REDD partners & initiatives(GEF, UNFF, Congo Basin etc) | x | x | x | x | Yemi/Tiina/Clea
| 2. Follow up UNFCCC negotiations, liaise with the UNFCCC Secretariat, and qnalyze UNFCCC process impacts on the UN-REDD Programme |  | x |  | x | Yemi/Tiina/Clea
| 3. Follow up, engage with and participate in the events and meetings of the Geneva based organizations |  | x | x | x | Linda
| 4. Lead and coordinate internal activities of the Secretariat | x | x | x | x | Yemi