## Slide 1
May
Jun
Dec
Pilot FPIC
Today
Finalization of methodology
Implementation
Revised evaluation methodology (Global Programme)
Preparation for materials (posters, etc)
Jan
Feb
Mar
Apr
Independent evaluation
Implementation
Procurement
ToR prep’n
Contracting of facilitators (NGOs)
Final FPIC methodology for REDD+
Lessons Learned Workshop
= Output
Notes: Based on our discussion, we aim to start FPIC in January -> Need to start “contracting of facilitators” soon
Implementations/Evaluations for FPIC have two parts or an interval in between – one is KPH and the other is National Park

## Slide 2
May
Jun
Dec
District Plans
Today
Jan
Feb
Mar
Apr
Implementation
Procurement
ToR prep’n
Opportunity costs analysis
Preparation of district plans
Socio-Economic analysis
Data support from others (University, UNEP/WCMC)
stakeholder consultations
= Proposal
= Output
Notes: Preparation of Templates is no longer critical, because of the UNEP/WCMC’s work
Initial target date for the district plan proposal was mid-March -> shifted by a month (two months after the opportunity cost analysis officially starts)

## Slide 3
May
Jun
Dec
Capacity Assessment
Today
Jan
Feb
Mar
Apr
Implementation
Procurement
ToR prep’n
Component I: Concept note /Stakeholder Mapping
Phase II: Comprehensive CA and CD Support to Lynchpin Institutions
Phase I: Knowledge and Learning Facility
Component II (Demand): Assessment of REDD+ Knowledge and Learning Needs among Stakeholders
Component III (Supply): Inventory and Mapping of Capacity Suppliers
Component IV: Establishment and Activation of Knowledge and Learning Facility
Briefing note on outcome of discussions
Optional
= Proposal
= Output
Notes: Based on the Ashley’s revised proposal/Recommendation 1
Phase II needs more discussions

## Slide 4
May
Jun
Dec
Harmonized fair and equitable payment mechanism
Today
Jan
Feb
Mar
Apr
Implementation
Procurement
ToR prep’n
FGD/Stakeholder consultations
Development of BDS options for Central Sulawesi (part 1)
Recommendation for a REDD+ BDS
Coordination with REDD+ and FCPF
Discussion with TF and FPCF on harmonized workplan
Development of BDS options for Central Sulawesi (part 2)
= Output
Notes: “Development of Options” (part 1 and 2) are based on the PMU’s Work Plan Q4
Outcome of the coordination component is to be determined